## Cover Page
Project Details
MRWA Project Manager:
Designer:
Items Submitted for Review:
Background Information Provided:
Project Manager's File:
Extent of Review:
Status of Project: | Concept | Concept Close Out | 15% | 15% Close Out | 85% | 85% Close Out | 100% | 100% Close Out | IFC | IFC Close Out
Date Delivered to Reviewer: | xx/xx/2021
Review Details
Reviewers:
Company: | Main Roads WA - Road and Traffic Engineering Branch
Review Reference Number: | R xxx/21
Reviewers File: | 21/5122
Date of Review Completion: | xx/xx/2021
Aspects Considered: | Geometry |  | Road Safety Barrier & Fencing |  | Drainage |  | Signs & Pavement Marking
Design Objectives: | Safety |  | Economy |  | Efficiency & Effectiveness |  | Environmental Sensitivity
Instructions for the Design Review Process
The Reviewer supplies advice only to the Project Manager. This review shall be conducted in accordance with MRWA Design Review Guideline (Doc. No. D16#287778). The Project Manager takes all risk and responsibility for each item beyond the Designer’s “Duty of Care” when they close out the items.
1. Main Roads WA - Road and Traffic Engineering Branch is to review the drawings/documents and provide “Reviewer Comments” in column 5 of the Design Review Table.
2. The Project Manager is to assess the “Reviewer Comments” and accept/reject each one. The PM can add comments in column 8 of the Design Review Table and may close out the items.
3. The Project Manager is to forward the remaining relevant “Reviewer Comments” to the Designer for the Designer to provide responses in column 6 of the Design Review Table.
4. The Designer is to forward the responses to enable close out of each of the “Reviewer Comments” to the Project Manager. The Project Manager can close out the “Designer response” at this stage in column 8.
5. The Project Manager is to forward the remaining (not closed out) “Designer Responses” to the Reviewer for reassessment/advice. The Reviewer is to reply in column 5 (refer to the colour convention) of the Design Review
Table for a second or third round of comment/responses or complete the “Response Status” in column 7.
6. The Project Manager is to determine the final outcome of all review items and add close out comments in column 8 of the Design Review Table.
7. The Project Manager is to forward final outcome/close out to all “Reviewer Comments” to:
• The Designer for design/amendments to proceed.
• Road and Traffic Engineering for record keeping.
8. To ensure that all review comments are acted on, a single review table should be used for all phases of the design review process.
Project Manager |  |  |  | Date
This design review is not to be considered a comprehensive design verification and may not pick-up all the issues. It therefore is not an approval of the presented design. The consultant/designer has the duty of care to ensure that the design is compliant with all the Standards and Guidelines and conforms to the requirements and intent of the design brief and agreed amendments.
Notes
Road and Traffic Engineering
Design Review Report
Project Title:

## Design Review Table
Design Review Table
Importance |  |  |  | Comments & Responses |  | Response Status
1 | Critical issue. Fatal Flaw. |  |  | For second round of comment/response use red text with initials & date. For third round use green text with initials & date. |  | Accepted |  | If resolved
2 | Moderate importance. Non-compliance. |  |  |  |  | Noted |  | If Designer to take responsibility
3 | Observation Only. Minor Issue. |  |  |  |  | Pending |  | If necessary to see the next submission
[6 empty] | PM Directive |  | If PM is to decide the course of action and close out
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 |  |  | Column 8
Item No. | Reviewer Initials | Reference | Importance Reviewer | Reviewer Comments Reviewer | Designer Response Designer | Response Status Reviewer |  |  | Close Out Project Manager (Initial & Date)
[6 empty] | Status | Initials | Date
Concept Design
General
1 | N/A | ROSMA Road Safety Management Systems POLICY | 1 | Has the ROSMA Road Trauma Reduction Process been applied to this project? This response should be provided by the Main Roads Project Manager.
2 | N/A | General | 1 | Has the ROSMA Road Trauma Reduction Process been applied to this project? This response should be provided by the Main Roads Project Manager.
Geometry
Road Safety Barrier and Fencing
Drainage
Signs and Pavement Marking
15% Design
Geometry
Road Safety Barrier and Fencing
Drainage
Signs and Pavement Marking
85% Design
Geometry
Road Safety Barrier and Fencing
Drainage
Signs and Pavement Marking
100% Design
Geometry
Road Safety Barrier and Fencing
Drainage
Signs and Pavement Marking
Issued for Construction
Geometry
Road Safety Barrier and Fencing
Drainage
Signs and Pavement Marking
Reviewers
Signed |  |  |  | Date