## Slide 1: Project Bank Accounts
for Minor Works Contracts
Contractor’s tasks in first 28 days of Contract Award

## Slide 2: Establishing the PBA

## Slide 3: Overview
Within 28 calendar days of contract award, the Contractor needs to have completed and delivered to Main Roads:
PBA Agreement
PBA Trust Deed Poll
Deed of Release or Priority Deed Poll (if required)
Opened an account with the Bank
AND
The PBA Agreement, PBA Trust Deed Poll and Deed of Release / Priority Deed Poll are provided as Attachments 2, 3 & 4 of the Minor Works PBA Pack.

## Slide 4: Timeframe
Contract Award (Day 1)
Within 28 calendar days of Contract Award
PBA must be activated within 10 business days of PBA Trust Deed Poll being signed
Test payment of $1 is made via the PBA to Contractor
PBA Agreement signed by Head Contractor, Main Roads & Bank
PBA Trust Deed Poll executed by Head Contractor & Main Roads
Deed of Release or Priority Deed Poll provided
Letter of Contract Award sent to Contractor

## Slide 5: Within one week of Contract Award
Contact the Bank to open the PBA. As it can take up to 3-4 weeks to open the account, it is important to start the process immediately.
Provide the Bank and authorised signatories within your organisation with a copy of the PBA Trust Deed Poll and PBA Agreement to familiarise themselves with how the PBA will operate. This will also help avoid delays when requesting them to sign these documents.
In order to determine if a deed of release or priority deed poll is required, you will need to conduct a Personal Property Securities Register (PPSR) search to determine whether there are any registered security interests that would extend to the PBA. It is recommended you seek your own independent legal or specialist advice with regard to conducting a PPSR search and analysing the search results.

## Slide 6: Within one week of Contract Award
If you are in the process of engaging subcontractors, you must now notify your Tier 1 subcontractors and suppliers with a contract value equal to or more than $20,000 (incl. GST) that they are bidding for a PBA project and direct them to the PBA page on Main Roads website Project Bank Accounts (PBA) | Main Roads Western Australia. There is no requirement for you to engage subcontractors earlier than normal.
Notify any subcontractors with a contract value less than $20,000 (incl. GST) of their right to “opt-in” to the PBA. You don’t need to notify suppliers with a contract value less than $20,000 (incl. GST) but they can opt-in if they wish to. If these subcontractors and suppliers want to join the PBA trust, you will need to provide them with an Opt-in Notice within seven calendar days. The Opt-in Notice can be found at Schedule 7 of the PBA Trust Deed Poll.
Send signed copies of all Opt-in Notices to the Superintendent.

## Slide 7: Within two weeks of Contract Award
If your organisation has granted a registered security interest to any creditor (other than the Bank establishing the account) that would extend to the PBA (as identified in the “Personal Property Securities Register” maintained pursuant to the Personal Property Securities Act 2009 (Cth)), you will need to obtain either a deed of release or a priority deed poll from each creditor. Only one of these documents is required from each creditor.
If required, contact the Bank to arrange training to ensure your staff are fully aware of how to operate the PBA. The actual training should take place in week three.

## Slide 8: Within three weeks of Contract Award
You should have received the BSB and two account numbers from the Bank – one for the General sub-account and one for the Retention sub-account. Follow up with the Bank immediately if this has not occurred by the middle of week three.
Complete the PBA AP-Supplier Creation Form and return it to Main Roads Finance Branch.
Ensure a signed deed of release or priority deed poll has been obtained from any creditors (other than the Bank) that hold a registered security interest over your organisation that would extend to the PBA. Follow up immediately if these have not been received.
Enter the BSB and two PBA account numbers into the PBA Agreement.
Ensure that the completed PBA Agreement and PBA Trust Deed Poll are signed by authorised signatories in your organisation.

## Slide 9: Within three weeks of Contract Award
Provide the Bank with the signed PBA Agreement and PBA Trust Deed Poll. The Bank will sign the agreement and sight the trust deed poll.
You should have also received tokens from the Bank (electronic devices that generate a random number) which will allow you to operate the PBA. Follow up with the Bank immediately if this has not occurred.
Contact the Super’s Rep to agree the date when your payment claim will be submitted each month (the Contractor is entitled to submit its payment claim on the first calendar day of each month). Notify subcontractors of the date they need to submit their payment claims each month. This should be at least a week before you submit your payment claim to the Superintendent.

## Slide 10: Within three-four weeks of Contract Award
Within 28 calendar days of Contract Award, you must deliver to Main Roads:
  The PBA Trust Deed Poll signed by your organisation;
  The PBA Agreement signed by your organisation and the Bank; and
  If your organisation has granted a registered security interest to any creditor (other than the Bank establishing the account) that would extend to the PBA, either a deed of release or a priority deed poll from each creditor.
  If there are no registered security interests that would extend to the PBA, advise the Superintendent by email.

## Slide 11: Within four weeks of Contract Award
Main Roads will arrange execution of the PBA Agreement and PBA Trust Deed Poll as soon as possible and provide you with a copy of these documents.
Provide the Bank with a copy of both documents, and provide your subcontractors/ suppliers (including any Opt-in subcontractors) with a copy of the PBA Trust Deed Poll.
Within 10 business days of the PBA Trust Deed Poll being signed by Main Roads, you will need to ensure the account is ‘established’. This means the Bank has received the required paperwork and is fully satisfied with the customer details.
You will need to initiate a $1 test payment from Main Roads to the PBA to establish the trust and ensure the payment system functions correctly.
At this time, Main Roads will also provide you with the names and email addresses of Main Roads staff who require viewing access to the PBA through the online banking system.

## Slide 12: Facilitating the $1 test payment
You will need to log into your PBA (through the Bank’s online banking system) and schedule a payment instruction (PPI) for $1 to be transferred from your general PBA sub-account to your non-PBA account. The transfer needs to occur on a working day 5 calendar days after you create the instruction. The bank should have already provided you with training on how to do this.
Provide a PDF copy of the instruction to the Super’s Rep as soon as it is authorised and scheduled. The status of the PPI must be ‘Authorised Scheduled’. Feel free to provide a draft beforehand so we can make sure the document is correct before you authorise and schedule it.
Main Roads will pay $1 into your general PBA sub-account and then according to your instruction, the bank will pay $1 to your non-PBA account. Notify the Super’s Rep once you receive the $1 payment.

## Slide 13: Facilitating the $1 test payment
For the $1 test payment there is no need for:
  the Contractor to issue a payment claim;
  the Superintendent to issue a payment certificate; or
  the Contractor to provide a statutory declaration or payment report.
The $1 payment will be deducted off the monies due and payment to the Contractor as part of the first payment claim.
Assuming that your other contractual obligations have been met, you can now submit your first payment claim.

## Slide 14: Operating the PBA

## Slide 15: Monthly payment process
Overview

## Slide 16: Day 1
The Contractor submits its payment claim on Day 1
The Contractor is entitled to submit their claim for payment on the first day of each month as outlined in GCC 23 and the Annexure.
The Contractor’s payment claim should be structured to align with the Schedule of Rates and/or Bill of Quantities (along with any variations) and any evidence the Superintendent may reasonably require to justify the value of the payment claim.
As outlined in GCC 23, the Contractor must not make any claim for payment until the PBA Trust Deed Poll, PBA Agreement and any required deed of release or priority deed poll have been delivered to Main Roads.

## Slide 17: Day 14
The Superintendent certifies the payment claim on or before Day 14
Subject to provisions of GCC 23.3, the Superintendent is required to assess the payment claim and issue a payment certificate within 12 days.
The Superintendent may reject a payment claim if the Contractor has failed to open and activate the PBA.

## Slide 18: Day 19
The Contractor issues payment documents to the Superintendent on or before Day 19
In accordance with GCC 23.5, on or before Day 20 the Contractor is required to issue to Main Roads:
  a completed Progress Payment Instruction (PPI);
  a Payment Report in the format available on Main Roads website; and
  a Statutory Declaration, signed on the same day or a date after the date the PPI has been authorised and scheduled.
The PPI must be prepared by the Contractor on the Bank’s online banking system in ABA format (ABA file format is used by Australian Bankers Association for batch transactions and the ABA files will have an “.aba” extension. The Contractor must provide a PDF copy of the PPI to Main Roads.

## Slide 19: Day 21
The Payment Report issued by the Contractor must be accurate and tally with the amount (inclusive of GST and to the exact cent) approved in the Payment Certificate. The Superintendent will check the Payment Report is in the correct format and includes any Opt-in Notices as required.
The Statutory Declaration must be in the format set out in Attachment 5 of the PBA Pack, and must be signed on the same day or a date after the date the PPI has been authorised and scheduled. The Contractor may provide either an electronic (scanned) copy or signed original. Note: Signature must be wet signed or DocuSign (by an authenticated signatory platform, ie Adobe)

## Slide 20: Day 28
Main Roads makes payment to the PBA
If all the payment documents are correct, the Superintendent advises the PBA Finance to complete the payment process and schedule payment as per the Processing Date provided on the PPI.
Main Roads will endeavour to factor in weekends and public holidays as no extra time is given when they occur. If the payment becomes due on a weekend or public holiday, Main Roads will endeavour to release the payment on the last working day prior to the weekend or public holiday.
In the event the PPI is inaccurate, Main Roads will notify the Contractor and request withdrawal and replacement of the PPI in accordance with GCC 23.

## Slide 21: Supporting information

## Slide 22: Glossary of Terms
Term | Meaning
Contractor Deposit Instruction (CDI) | Allows the Contractor to pay subcontractors throughout the month except within two days of the scheduled PPI payment date. The Contractor deposits funds into the PBA and it is disbursed to subcontractors and the retention sub-account as required.
Deed of Release / Priority Deed Poll | By signing a deed of release, a creditor agrees to release the PBA from any security interest it holds, giving priority to the trust’s beneficiaries should an insolvency event occur. If the Contractor has not granted any registered security interests that would extend to the PBA, neither document is required.
Progress Payment Report (PPR) | Provides a summary of all payments made through the PBA to subcontractors (including opt-in subcontractors and suppliers) for a particular month. It also includes a running tally of all payments made to date, as well as retention held and retention released.
PBA Agreement | The agreement made between the Contractor, the Bank and Main Roads. It outlines how money will flow in and out of the account.
PBA Trust Deed Poll | Sets out how the Contractor holds money on trust for the benefit of the subcontractors (beneficiaries). The trust deed poll establishes the trust and who the beneficiaries are.
Progress Payment Instruction (PPI) | Instruction to the Bank that sets out how the funds in the PBA are to be disbursed.
Retention Release Instruction | Instruction to the Bank to pay money out of the Retention sub-account directly to the subcontractor or the Contractor.

## Slide 23
PBA AP-Supplier Creation Form
Payment Report Template
PPI Example
PPI Example - $1 test payment
PBA Page on Main Roads website
Documents and links

## Slide 24: Questions