## Risk Assessment Worksheet
Extended Design Domain / Design Exception Risk Assessment and Register
| Project / Location: |  |  | Date: |  | 2018-04-27
Ref No. | Risk Event / Hazard (What can happen?) | Causes of the Event (How can it happen?) | Consequences (What is the Impact if the hazard / deficiency is not mitigated?) | Initial Risk Analysis |  |  | Mitigating Treatment | Residual Risk Analysis
|  |  |  | Consequence | Likelihood | Risk Rating |  | Consequence | Likelihood | Risk Rating
1: Geometric Issues
1 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
2 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
3 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
4 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
5 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
6 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
7 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
8 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
9 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2
10 | Rear end crash | Reduced Sight Distance on vertical curve at SLK 100. Desirable minimum K-value for 110km/h = 97.3. Achievable K-value = 65.0. ' | - Injury - Injury resulting in fatality | Moderate | Possible | Medium 9 | - Provide manouvre sight distance - Provide a wider shoulder | Minor | Rare | Low 2

## Graphs (hidden)
Initial Risk |  | Residual |  | Revised Residual
VH |  | VH |  | VH
H |  | H |  | H
M |  | M |  | M
L |  | L |  | L
| 0 |  | 0 |  | 0

## Sheet1 (hidden)
Rating Term | Risk Rating | Ranking
Rare Insignificant | L | 1 | Catastrophic
Rare Minor | L | 2 | Major
Unlikely Insignificant | L | 2 | Moderate
Unlikely Minor | L | 2 | Minor
Possible Insignificant | L | 3 | Insignificant
Rare Moderate | L | 3
Likely Insignificant | L | 4 | Rare
Rare Major | L | 4 | Unlikely
Almost Certain Insignificant | M | 5 | Possible
Rare Catastrophic | L | 5 | Likely
Possible Minor | L | 6 | Almost Certain
Unlikely Moderate | L | 6
Likely Minor | M | 8
Unlikely Major | M | 8
Possible Moderate | M | 9
Almost Certain Minor | H | 10
Unlikely Catastrophic | H | 10 |  | CONSEQUENCE | LIKELIHOOD
Likely Moderate | H | 12 |  |  | Rare | Unlikely | Possible | Likely | Almost Certain
Possible Major | H | 12 |  | Catastrophic | 5 | 10 | 15 | 20 | 25
Almost Certain Moderate | H | 15 |  | Major | 4 | 8 | 12 | 16 | 20
Possible Catastrophic | H | 15 |  | Moderate | 3 | 6 | 9 | 12 | 15
Likely Major | H | 16 |  | Minor | 2 | 4 | 6 | 8 | 10
Almost Certain Major | VH | 20 |  | Insignificant | 1 | 2 | 3 | 4 | 5
Likely Catastrophic | VH | 20
Almost Certain Catastrophic | VH | 25

## Rating Tables
Likelihood (of an incident occurring) |  |  | Consequence (how severe)
| Frequency | Descriptor
Almost Certain / 5 | More than once per month | The event or consequence may occur only in exeptional circumstances | Catastrophic | Multiple fatalities disruption and effectiveness of MRWA
Likely / 4 | More than once per year | The event or consequence could occur at some tmie | Major | Single fatality or major injuries or severe permanent disablement
Possible / 3 | Once every 1-10 years | The event or consequence might occur at some tmie | Moderate | Medical treatment required or lost time injury
Unlikely / 2 | Once every 10-50 years | The event or consequence will probably occur only in most circumstances | Minor | First aid treament required
Rare / 1 | More than once every 50 years | The event or consequence is expected to occur only in most circumstances | Insignificant | No treatment required
Risk Rating
CONSEQUENCE
LIKELIHOOD | Insignificant | Minor | Moderate | Major | Catastrophic
Almost certain | Low 5 | High 10 | High 15 | Very High 20 | Very High 25
Likely | Low 4 | Medium 8 | High 12 | Very High 16 | Very High 20
Possible | Low 3 | Low 6 | Medium 9 | High 12 | High 15
Unlikely | Low 2 | Low 4 | Low 6 | Medium 8 | High 10
Rare | Low 1 | Low 2 | Low 3 | Low 4 | Medium 7
Risk Rank
RISK ACCEPTANCE CRITERIA | Risk Rating | Level of Risk | Management Oversight
Rating
| Low (1-6) | Risk is generally acceptable | Reviewed and accepted by Risk Owner
| Medium (7-9) | Risk is acceptable with adequate controls. Treatment action plan required if consequence is Catastrophic. | Reviewed and accepted by Risk Owner and Manager
| High (10-15) | Risk may be acceptable with adequate controls. Treatment action plan required to reduce risk level further where possible. | Reviewed and accepted by Risk Owner and Director/ Executive Director/ General Manager/ Manager
| Very High (16-25) | Risk is generally not acceptable. Treatment action plan required to reduce the risk. | Reviewed by Risk Owner, Director/ Executive Director/ General Manager/ Manager and Office of DG or Executive Committee