TABLE OF CONTENTS

SECTION 208	LAND MANAGEMENT	2

208.1	Cadastral Background	2

208.2	Land Dealings Plans	2

208.3	Land Acquisition	3

208.4	Entry onto Land	3

# SECTION 208	LAND MANAGEMENT

## 208.1	Cadastral Background

Cadastral Backgrounds are to be prepared for all design contracts to facilitate identification of land parcels, ownership and any additional requirements for the project.  Cadastral Backgrounds are to be prepared in accordance with Main Roads’ Survey and Mapping Section’s “Verified Cadastral Models” Standard Document No 67-08-49 or obtained from the Department of Land Information’s Spatial Cadastral Data Base if the accuracy is suitable.  Accuracies required are stated in the Main Roads Standard.

## 208.2	Land Dealings Plans

Where the development of the Project requires land additional to that originally planned, or advised as being available at the commencement of the Contract, such findings shall be documented with all necessary supporting details at the earliest opportunity for review at progress meetings.  Where appropriate, alternative designs to minimise or obviate the additional land requirement should be considered by the Consultant.  All alternatives should be presented to the Principal’s Representative at the earliest opportunity for review.

Preliminary Land Dealings Plans shall be produced in strip format showing a widening of the road reserve to XX metres.

<This paragraph may need amending for specific projects particularly where projects pass through existing reserves or public land.>

Preliminary plans shall be prepared at a suitable scale (i.e. 1:2000) and include the existing road centre-line, extent of preliminary design earthworks, fences and any improvements likely to affect land acquisition.  They will be used for verification of land requirements by Main Roads prior to preparation of the final plans.

All land requirements for the project, especially any additional land required outside the current road reserve shall be identified.

When final land requirements are agreed by the Principal, Land Dealings Plans shall be produced for the Nominated Sections only.

The verified digital cadastral model prepared for this project shall be used as a base for the definition of land requirements.

Final Land Dealings Plans shall be produced in accordance with Main Roads Survey and Mapping Section’s “Property Management Graphics” Standard Document No. 67-08-48.

## 208.3	Land Acquisition

When final land requirements are agreed by the Principal, the Consultant may be required to liaise with the affected land owners with respect to land being acquired for the project, and for any associated work such as accommodation works, service relocations and fencing alterations.  The Consultant shall not liaise with the affected landowners without the approval from the Principal’s Representative.

The Consultant shall not attempt to negotiate with the landowner matters relating to the purchase price of the land required for the project or to offset arrangements that cannot be controlled by Main Roads such as road closures.

All information is to be provided to the Principal who will then commence the land acquisition process in accordance with the requirements specified in Main Roads Online Documents ‘Land Acquisition Rural and Land Acquisition Metro’.

## 208.4	Entry onto Land

The Consultant shall only enter Land with the approval of the registered owner or occupier.  If entry is refused the Consultant will report to the Principal’s Representative who will then make formal arrangements for entry.

No disturbance is to take place on any land until approval has been given by the owner or occupier or until the Principal has made formal arrangements.  No disturbance is to take place on Crown Lands until all necessary clearances have been obtained.

GUIDANCE NOTES

DELETE GUIDANCE NOTES FROM FINAL DOCUMENT AFTER USING FOR REFERENCE

All edits to downloaded Briefs shall be tracked (most word processing software allows this to be done automatically).  Deletions shall be struck through e.g. example.  Insertions shall be in italics e.g. example.  If all information relating to a clause is deleted then the clause number should be retained and the words "NOT USED" should be inserted.

The proposed documents with tracked changes shall be submitted to Main Roads for review, prior to printing the final batch of documents.  When this final printing is carried out, changes are saved and the tracked changes option is to be turned off.

The Custodian of this section of the Brief is Mr Frank Lyons (Land Tenure Manager) ph:  9323 4168.