Pre-Development and Concept Work

Mid 2019 Establish project steering committee and stakeholder workshop

November 2019 to June 2020 Constraints and issues mapping to develop preferred alignment

July to September 2020 Community feedback sought

October to November 2020 Determine heritage, urban landscape and design priorities

November to December 2020 Review feedback and provide project updates

July 2020 to January 2021 Commence procurement of alliance contractor

Design Development and Pre-Construction

**January 2021** Alignment options assessment.

January 2021 - Alliance contract awarded.

May 2021 Consultation on alignment options.

June 2021 Design development

July and August 2021 Consultation on bridge aesthetics, heritage, public spaces, walking and cycling paths and construction impacts.

September 2021 Detailed design and pre-construction

October 2021 - Ongoing community and stakeholder engagement.

December 2021 - Information on construction impacts. Pre-construction

2022 to 2025 Construction