Document No. D12#157550				         	         Issue Date 25/05/2004

CORPORATE PROCEDURE

This document is owned and authorised by Executive Director Technology and Environment.

Enquiries should be directed to the delegated custodian, Manager Environment.

#### Printed copies are uncontrolled unless marked otherwise

#### CONTENTS

1.	INTRODUCTION	4

1.1	Purpose	4

1.2	Scope	4

1.3	Application	4

Related Environmental Guidelines	5

1.4	Contacts for more information	5

2.	REVEGETATION	6

2.1	What is revegetation?	6

2.2	Why is revegetation necessary?	8

2.3	Where does revegetation occur?	8

2.4	What is involved in revegetation?	10

3.	KEY ISSUES TO CONSIDER AND FACTORS FOR SUCCESS	11

3.1	Setting objectives	11

3.2	Preparing budgets	11

3.3	Planning	12

3.4	Timing of seeding or planting	13

3.5	Regional differences	14

3.6	Site implementation	15

3.7	Vegetation establishment period	15

3.8	Provision for remedial revegetation works	16

3.9	Expertise	16

3.10	Handover of the revegetation works	16

3.11	Ongoing maintenance of established vegetation	16

4.	PROJECT MANAGEMENT OF REVEGETATION WORKS	17

4.1	General approach	17

4.2	Processes	17

4.3	Process for Stand Alone Revegetation Works	18

4.4	Process for Design and Construct Projects	22

4.5	Process for Standard Roadwork Projects	26

5.	DEFINITION OF TERMS	31

6.	REFERENCES	32

Appendices

| Appendix A | Roadside Vegetation – Management Objectives |
| --- | --- |
| Appendix B | Revegetation Planning –Checklist For Site Assessment |
| Appendix C | Recommended Methods And Techniques |
| Appendix D | Revegetation Benchmark Costs and Sample Bill Of Quantities |
| Appendix E | Typical documents – Suggested Table Of Contents |
| Appendix F | Revegetation - Seed Quantity Calculation Worksheet |
| Appendix G | Examples Of Monitoring Programs For Revegetation Works |

#### REVISION STATUS RECORD

| Revision No. | Revision Date | Description of Key Changes |
| --- | --- | --- |

# INTRODUCTION

## Purpose

Main Roads Western Australia (“Main Roads”) has a policy aim to “protect and enhance the environmental values of road reserves”.  In the process of establishing new roads and upgrading existing roads, there is often a need to undertake revegetation of road reserves or other affected areas.  Additionally, there may be parts of the road reserve that are degraded and would benefit from revegetation.

This document provides guidance on planning and implementing revegetation within road reserves and other areas for which Main Roads is responsible.  It is designed to guide project managers on the steps involved and is intended to support, but not replace, specialist advice on revegetation projects.

## Scope

This document addresses the following areas:

- Definition of what revegetation is and why it is necessary;

- Key issues affecting the planning, implementation and ultimate success of revegetation works;

- Outline of the steps involved in project management of revegetation works, and

- Supporting technical information about revegetation techniques.

The Guideline mainly relates to the establishment of native vegetation on roadsides and other areas.  Landscaping techniques (eg transplanting, grassing and turf establishment, irrigation) and the ongoing maintenance of existing roadside vegetation are not covered in this Guideline.  Specialist advice on landscaping works and ongoing maintenance of vegetation is available from Main Roads’ Environment Branch.

## Application

### Who should use this document?

Those involved with the planning and implementation of revegetation works, including, but not limited to:

- Project Managers;

- Environment Officers; and

- Asset and Contract Managers.

### Responsibilities

Project Managers are responsible for ensuring that Main Roads’ statutory and corporate obligations are met with regard to completion and handover of revegetation works for their projects.

Asset Managers and Maintenance Contract Managers are responsible for ensuring that Main Roads’ statutory and corporate obligations are met with regard to the identification of revegetation requirements and with the ongoing management of roadside vegetation.

### Why should I use this document?

The use of this document helps to manage corporate risk by providing guidance to:

- Ensure revegetation works are planned and conducted to an acceptable standard;

- Minimise the risk of cost over-runs due to failure of revegetation works; and

- Manage consultants and contractors involved in revegetation works.

### How do I use this document?

- Use the information in Sections 2 and 3 for background on revegetation works.

- Apply the project management procedures, Section 4, to ensure compliance with statutory and corporate obligations.

- As needed, use the supporting technical information, checklists and suggested contents for documentation given in the appendices.

### Related documents

Documents to be used in conjunction with this document include, but are not necessarily limited to:

- Main Roads Environmental Policy Statement

# Related Environmental Guidelines

- Main Roads environmental guideline Vegetation Placement within the Road Reserve (D12#157580)

- Main Roads environmental guideline Vegetation Control (in preparation).

Related Environmental Briefs

- Main Roads environmental brief Project Revegetation Plan (in preparation).

- Main Roads environmental brief Revegetation Design (in preparation).

- Main Roads environmental brief Landscape Design (D12#153676).

Related Specifications

- Specification clauses that relate to revegetation works can be found within the following Main Roads’ Tender Document Process (TDP) standard contract specifications:

- Clearing (301),

- Earthworks (302),

- Borrow pits (303) and

- Revegetation and landscaping (304).

## Contacts for more information

Additional support and guidance on revegetation is available from the regional Environment Officer or from the Environment Branch, Don Aitken Centre.

# REVEGETATION

## What is revegetation?

Vegetation (a plant cover of trees, shrubs, herbs or grass) of some type occurs within the road reserve across all regions of the state.  This varies from forests in the South West to the scrublands and spinifex grasslands of the pastoral regions.

Figure 1  Typical examples of roadside vegetation across the State Road Network.

Revegetation refers to the re-establishment of a cover of vegetation suited to the location.

This usually means a cover of local native plants and involves regeneration, direct seeding, and/or planting methods.    Definitions of terms associated with revegetation are given in section 5.

Revegetation involves:

Preparation of finished soil surfaces, eg by ripping or tilling the soil surface and respreading site topsoil and chipped vegetation, to assist regeneration to occur naturally.

Regeneration of vegetation can occur through the seed existing within the site topsoil if this is stripped and respread during the earthworks, or from the seed that is carried in the cleared site vegetation that is chipped and respread over the soil.

In many locations, the additional seeding and planting of vegetation may be necessary within the project area.

Seeding refers to the direct broadcast (by hand or machine) of plant seed onto the prepared soil surface.

Planting refers to the placement of nursery grown plants (in pots or small tubes – “tubestock”) into the soil by hand or machine.

Landscaping refers to revegetation or additional works like grassing and irrigated planting beds, feature paving etc undertaken for functional and amenity objectives, for example at key locations along urban roads and town entries.

## Why is revegetation necessary?

Establishing a vegetation cover helps to prevent soil erosion by rainfall impact and surface water flows.

Established vegetation help maintain the stability of the roadside and road formation.

Roadwork project commitments may include revegetation to meet environmental objectives or to meet ministerial conditions of approval for the project.

Roadside vegetation provides amenity for

road users and adjoining landholders.

## Where does revegetation occur?

Revegetation is an accepted part and practice of roadwork projects.

Revegetation is associated with the following areas:

Cleared areas within roadwork projects (e.g. batter slopes).

| Side tracks and access tracks. |  | Borrow and spoil pits |
| --- | --- | --- |

| Stockpile areas. |  | Redundant pavement areas. |
| --- | --- | --- |

| Acquired land adjoining road reserves. | Drainage basins (batters and surrounds). |
| --- | --- |

| Urban roadsides and medians. |  | Other designated areas (e.g. community or memorial roadside plantings). |
| --- | --- | --- |

Vacant gazetted road reserve.

Existing roadsides in agricultural and pastoral regions

(eg with degraded remnant vegetation or abutting good quality native vegetation).

## What is involved in revegetation?

Effective revegetation practices help to accelerate the natural processes that occur following the clearing of vegetated areas and soil disturbance.

Revegetation requires the prior establishment of soil conditions suitable for plant growth through effective management of topsoil and the control of weeds and other site factors.

All plants require water to establish and grow.  For most locations this means that revegetation, like agricultural cropping, is dependent on the annual rainfall.

Extent of works

Revegetation works may be limited to spreading site mulch (chipped vegetation cleared from the site) to protect an exposed batter surface, or require extensive seeding and planting.  Some projects (eg in urban areas) may require landscaping with irrigated planting beds and grassing.

The methods and techniques used and the management approach will vary with the project size, the timing of the works, the site location, and other specifics of the site.

Management of the existing site topsoil and preparation of the finished soil surface is the accepted basic practice for revegetation across the State, but this is often supplemented by direct seeding and planting timed to occur with the seasonal rains.

Planning

Most importantly, however, successful revegetation requires some level of planning well in advance of any physical activities.  Effective revegetation means identifying and responding to the site constraints and project commitments.   It also involves making the best use of the materials available on site by not wasting the existing soil and vegetation resources.

Some level of community consultation or involvement of stakeholders will often be associated with revegetation works.

Section 3 discusses the key issues to consider and factors for success in planning revegetation works.  The key steps in the revegetation process are summarised below.

- Set objective and budget for the revegetation.

- Prepare a site-specific plan.

- Manage the works (and establish the vegetation).

- Handover the works for ongoing maintenance.

# KEY ISSUES TO CONSIDER AND FACTORS FOR SUCCESS

Failure of revegetation works is often attributed to externalities, such as ‘lack of rain’, or wildfire.  While these externalities may be factors, poor revegetation outcomes can sometimes be traced to lack of planning and inadequate implementation.

The main reasons for the failure of revegetation works are associated with:

- Lack of early planning for revegetation works in the project process,

- Lack of expertise available within the project management and superintendence of the contract works,

- Failure to co-ordinate the revegetation with the clearing and earthworks,

- Inadequate provision for soil preparation and weed control,

- Poor timing of the revegetation works, and

- No follow up care to establish the vegetation.

This section discusses some of the key factors, which determine the success of a revegetation program.  These issues and others are covered more fully in Appendix C (Recommended Revegetation Methods and Techniques).

## Setting objectives

The level of treatment must be determined on a project-specific basis.   Site issues are defined in the site Revegetation Plan (see Section 4).  As a minimum, revegetation should achieve roadside stability and minimise on-going maintenance.  In certain circumstances, additional objectives may be relevant, as summarised in Appendix A (Roadside Vegetation – Management Objectives).

For larger road projects that have been subject to statutory assessment by the Environmental Protection Authority, specific objectives will be set.   Environmental constraints may apply on plant species selection, seed collection and propagation.   The Asset Manager may also set revegetation objectives.  Goals and targets for revegetation must be realistic for the location and project.

In pastoral regions basic topsoil management and weed control would be the expected minimum level of treatment.  In agricultural regions some level of seeding and/or planting and weed control would be the expected minimum level of treatment.   In urban areas a higher standard of revegetation/landscaping is the expected minimum level of treatment.

Direct seeding or regeneration from topsoil is the preferred approach for all regions of the state where re-establishment of ‘natural’ vegetation is the objective.   This may be supplemented by some planting.   Planting alone is not the preferred approach except to achieve roadside stability and amenity objectives for example in urban areas.

The measure of the success of the revegetation is based on monitoring the completion criteria as defined in the project plan.  Examples of completion criteria are provided in Appendix G (Examples of Monitoring Programs for Revegetation Works).

## Preparing budgets

Costs vary with the methods used and the overall size of the project.  Project requirements may vary in size (from hectares to square metres), in the complexity of materials used and in the number of plant species used.

As a guide for large road projects (>$50 M) ~ 3% of the total cost estimate may be considered reasonable, depending on the specific project location and project commitments.   In urban areas at least ~ 5% of the total cost estimate is used for initial estimating purposes in smaller projects.

Some typical costs for revegetation projects from around Australia are given, as benchmark costs, in Appendix D1 (Revegetation Projects – Benchmark Costs).  They range from $2300 - $4200/ha for small areas to $600 - $2200/ha for large areas.  These costs, however, do not include significant earthworks such as topsoil stripping and replacement.

Historical costs for Main Roads’ revegetation work are not currently available but anecdotal information suggests they are higher than these values due to higher site costs when earthworks, formal monitoring and maintenance costs are considered.

A preliminary cost estimate, based on the total area and the type of revegetation works, is determined during the project planning stage.  Appendix D2 provides a sample Bill of Quantities for revegetation works.

Local knowledge and experience in the region must be used where possible to determine the minimum level of treatment and for estimating costs.

Refer to Main Roads’ Environment Branch for advice on estimating costs for revegetation works.

## Planning

Once the need for revegetation work has been identified and a project objective set (see Appendix A), preliminary planning can be carried out.  The checklists shown in Appendix B for site assessment should be used as a basis for preliminary planning but other issues could emerge.

The accepted approach for Main Roads’ revegetation works is to accelerate the natural processes that occur following clearing of vegetation areas and soil disturbance.  This means that successful revegetation projects require careful planning, with the timing of particular activities being critical.  Taking into account the various activities involved in planning and undertaking revegetation, an example timeline for a revegetation project involving planting or direct seeding is given in Figure 2.

Figure 2	Suggested timeline of revegetation work involving seeding or planting – planning, implementation and subsequent monitoring.

Note that:

- Seed collection from site may need to be conducted over an extended period as the seeds of different species mature at different times.  In a year with poor rainfall, seed set may be limited and collection may need to be conducted in the following year;

- Where seed other than that occurring on site is required, seed collectors may require significant advance notice in order to meet the specifications; and

- Several rounds of weed control may be necessary to adequately control the new growth of weed species (from the weed seeds existing in the soil) and reduce the competition on site for the planting or seeding.  Weed control is most effective at particular times of the year.

- Where establishment of self-sustaining native vegetation is the aim, planting is used to supplement direct seeding.  Planting alone does not achieve the required diversity of species and plant forms.

## Timing of seeding or planting

Seeding or planting should occur when the likelihood of survival and establishment is greatest.  This would normally be immediately prior to or at the ‘break of season’ as shown in Table 1.  For example, in jarrah forest rehabilitation after bauxite mining, the best results are achieved when soil preparation and direct seeding both occur by April, with no cultivation occurring after the break of season.  If the earthworks occur later, the soil surface disturbance may potentially kill any germinating seeds present in the topsoil.

Late seeding can reduce the amount of moisture available to germinating seeds and can ultimately lead to failure of seeding.  There is anecdotal evidence that seeding as the first ‘break of season’ rains occur can be very successful.

| Main Roads Region | Optimal Timing |
| --- | --- |
|  | Seeding | Planting |
| Gascoyne | May in south of region; November-December in north of region. | No planting without irrigation. |
| Goldfields-Esperance | April-May. Earlier in south than in north. | No planting without irrigation. |
| Great Southern | April-May throughout region. Seeding during September-October within 30 km of the coast can also be successful due to warm temperatures and spring coastal showers. | May-June. |
| Kimberley | October-December, preferably just before rain. | No planting without irrigation. |
| Metropolitan | April-June. | May-July. |
| Midwest | April-May in south of region; November-December in extreme north of region. | May-June in southern part of region only. |
| Pilbara | November-December but preferably just before rain. | No planting without irrigation. |
| South West | April-June. | May-June. |
| Wheatbelt North | May-June. | June-July. |
| Wheatbelt South | April-June. | May-June. |

Table 1	Optimal seeding and planting times for each Main Roads region.

Planting should be conducted slightly later than seeding, when there is sufficient moisture in the ground to sustain the young plant but not so late that there would be insufficient moisture for establishment.   In wet areas, seeding and planting can be delayed to late spring.

## Regional differences

Climate is an important determinant of the methods used across the state.  Not only does climate determine the timing of activities (see section 3.4) but it can also determine the method used.  Historically in the more arid areas, (i.e. where the rainfall variability is moderate to high) the most cost effective method has proven to be topsoil management along with some direct seeding and allowing natural regeneration to occur over time.

Planting and seeding is generally limited to the Southwest corner of the State where the annual rainfall is reliable (see Figure 3) i.e. where the rainfall variability is low to moderate.

Figure 3	Main Roads network and variability of annual rainfall

(derived from http://www.bom.gov.au/).

Where the rainfall is very low or not reliable, then additional watering is required for any planting.  Planting during the year, other than with the seasonal rains, is limited to locations where irrigation (from scheme water, bore or by tanker) is available to establish the vegetation.

## Site implementation

### Site preparation

The success of a revegetation program will hinge upon the correct preparation of the soil conditions for seeding or planting (see Appendix C, section 2).  Adverse factors for plant establishment must be recognised and the appropriate steps taken to ameliorate their effects.  Examples of seed or planting bed preparation include deep ripping to alleviate soil compaction and mounding to alleviate the potential effects of waterlogging.  In some cases soil amendments (such as adding nutrients) may be necessary.

### Weed control

Seeding or planting of native plants in weed-affected areas, such as former agricultural land and in urban areas, is unlikely to be successful without careful planning for weed control.  Competition from weed species is a major cause in the failure of revegetation projects.

Weeds once established in the soil may inhibit the establishment of native plant species.

Successful weed control may require action at several stages of the project until weed numbers (a store of seed is retained in the topsoil) are reduced to levels that allow native plant seedlings to grow and establish successfully.

### Seed and Planting

Any seed or seedlings used in revegetation work should be of a known quality.  There are steps that can be taken to reduce the risk of obtaining poor stock.  These are discussed in Appendix C and involve certification of the viability of seed and adherence to certain industry standards for the production of seedlings.

There is evidence that different seeding methods can produce markedly different results.  Following consultation with industry personnel and researchers, this appears to be related to seed burial, with seed that is buried too deeply unable to establish.  Small-seeded species are at greater risk of loss through burial than large-seeded species.  Excessive seed burial appears to occur only with some mechanical methods, with hand seeding producing satisfactory results.  If mechanical seeding is to be used, advice should be obtained on this aspect.

## Vegetation establishment period

The revegetation works may only be partially successful in the first year.   Replacement and infill revegetation works may be required for unsuccessful areas within the project area.  Once the initial seeding and planting works have been completed, the new vegetation must also be allowed to establish and grow.   It is essential to allow for a vegetation establishment period with adequate funding, to ensure that follow up works (replacement or infill) are identified and will occur in subsequent years.

Key activities during the vegetation establishment period include regular inspection to monitor the success of the revegetation, to assess need for weed and pest control and to assess the need for follow up revegetation work.  Inspection may highlight losses of seedlings and, indeed, some losses are inevitable.  Control of site factors such as pest infestations may be necessary.  Replacement of seedlings or reseeding of bare areas can be undertaken in the following planting season.  Losses of seedlings will be reduced if a weed-free zone is maintained around them.  Control of any dry or herbaceous weeds is highly desirable as they represent a fire threat, which could kill young plants.  Signage helps to prevent unauthorised access and assists in the promotion of revegetation work.

A minimum Vegetation Establishment Period of at least two summers, following the Practical Completion of the works, is essential to achieve the project objectives, prior to a handover of the revegetation works for ongoing routine roadside maintenance activities.

Contract arrangements must be defined as part of the project planning, to cover the establishment of the new vegetation and any remedial works that may become necessary.

## Provision for remedial revegetation works

Revegetation work that does not meet the expected standards at Final Completion will have to be redone.

For all projects, contractual arrangement should be in place to protect Main Roads’ investment.   Generally, the application of retention monies is not favoured, as it is believed to be inequitable due to the long lead-time of some projects.  The preferred option is a bank guarantee (as a performance bond), which allows the principal to call upon some funds to undertake remedial work if it is necessary and where the contractor is unwilling or unable to undertake the work.  However, this is normally set at only a small proportion of the cost of the revegetation component of a project and would not cover catastrophic failure where major remedial work was necessary.

It is recommended that the provision of a bank guarantee, from 10% to full reinstatement costs of the revegetation works, be based on the Project Manager’s assessment of the risks associated with the project.

## Expertise

Like any road construction activities, the use of appropriate skills and advice is necessary.  This will ensure the critical factors for the specific project are identified and considered in the planning, design and implementation of the revegetation works.  If sufficient expertise is not available from within Main Roads, outside assistance should be sought.  Local experience is particularly valuable.

## Handover of the revegetation works

Once the objectives of the revegetation are achieved, it is important that the handover, from the Project Manager to the Asset Manager, is formalised to ensure that on-going maintenance activities occur.  The site may also need to be monitored for a period after the handover of the contract works to meet ministerial conditions of approval.

## Ongoing maintenance of established vegetation

In practical terms the ongoing maintenance of established roadside vegetation is limited to the clearing zone (along the roadway) and the maintenance zone (along the road reserve boundary).  Refer to figure A1, Appendix A.

Maintenance activities outside these zones are limited to selective noxious weed control, and the removal of dead wood and vegetation growth that is hazardous.  Any infill or replacement plantings that are identified as necessary by the Asset Manager are undertaken as Minor Improvement Works.  This may occur within the regional Term Network Contract (TNC) or via the use of landscape contractors.

# PROJECT MANAGEMENT OF REVEGETATION WORKS

## General approach

Revegetation works occur as part of the project management process.  To be cost effective, revegetation must be based on:

- A project-specific assessment of site conditions, issues and risk factors;

- Timely and appropriate decision-making; and

- The use of appropriate skills and advice.

The details will vary between regions and projects, but the general approach to undertaking revegetation works involves the steps shown in Table 2.

| Stage | Key Points | Reference |
| --- | --- | --- |
| Planning and documentation | Dependent on size and complexity of works Need to clearly identify objective(s) and key factors Specialist assistance may be required | App. A (objectives) App. B (site assessment) App. C (techniques) App. D (benchmark costs) App. E1-3 (documentation) App. F (seed quantity calculation worksheet) Standard Contract Specifications Brief for revegetation plan. Brief for revegetation design. |
| Implementation | Correct timing and surveillance essential Decision support may be required | App. C (techniques) |
| Vegetation establishment | Monitor progress and rectify defects after Practical Completion | App. C (techniques) App. G (examples of monitoring programs) |
| Handover | Handover to include recommended maintenance program | App. E4 (handover report) |

Table 2	General approach to project management of revegetation works.

## Processes

Revegetation may occur as part of a standard roadwork’s project, a design and construct roadwork’s project or as stand-alone revegetation works not directly associated with any roadwork project.   The key steps to ensure successful outcomes in each of the three project management types are summarised as diagrams and guidance notes in the following sections:

- Section 4.3 - Process for stand alone revegetation works project (Figure 4);

- Section 4.4 - Process for revegetation works within Design and Construct projects (Figure 5); and

- Section 4.5 - Process for revegetation works within other roadworks projects     (Figure 6).

## Process for Stand Alone Revegetation Works

Figure 4  Steps in recommended process for stand alone revegetation works projects.

### Project proposal

The project proposal shall include a concise statement of key information (e.g. need/purpose of the revegetation works, objectives, budget and timeframe) to gain approval to proceed with the works.  The need for the works may be based on external pressures for improvements (e.g. public complaints), the project approval conditions, Main Roads’ environmental policy objectives (refer to Corporate Objectives and Targets), or the Asset Management planning process.   Some level of site assessment is necessary, but the requirements are not defined in detail.  An Environment Officer, Asset Management Officer or the nominated Project Manager may prepare the proposal or a consultant may be engaged, if necessary, on an hourly basis (indicative cost < $2 000).  In the absence of other information, a preliminary budget can be determined using the most appropriate benchmark costs given in Appendix D plus a 20% contingency.

### Project Plan

The project plan shall include a Revegetation Plan, which defines the scope and extent of the works; staging and the methods to cost effectively deliver the works.  An assessment of the site conditions is necessary to define relevant site constraints and opportunities.  The level of planning and documentation required for the revegetation is dependent on the size and complexity of the works.   The Revegetation Plan may be simply a clear statement of objectives in the project proposal and the use of Main Roads’ standard specifications or a stand-alone assessment and report prepared for the purpose.

Ideally, the Revegetation Plan should be prepared at least two years before the proposed works are to be undertaken.  An Environment Officer, Asset Management Officer or the nominated Project Manager may prepare the document.  The Project Manager may seek to engage a specialist consultant (indicative cost < $5000) to assess the site issues and prepare the Revegetation Plan.  Refer to Main Roads’ Environment Branch intranet web site for a template of a plan brief.   A brief for the detailed revegetation design may also be prepared at this stage.

Procurement options may include a design and construct package, separate design and construct contracts or by direct Main Roads’ management of contractors.  At this stage, contract arrangements should be decided to cover establishment of the new vegetation and any remedial works.  Options are discussed below in section 4.3.4.  It is also critical to clarify the handover process and ongoing maintenance for the site revegetation works.

### Design and Contract Documentation

The extent of the revegetation works shall be clearly defined by a design and documentation process prior to finalising the contract documents.  The detailed design specifies the requirements to achieve the revegetation objectives and defines completion criteria.  For small projects the detailed requirements can be defined simply from the project plan (e.g. SLK location, plan of area, species list, and standard specification clauses etc).  As the scale and complexity of the revegetation works increases, a stand-alone detailed site assessment and set of documents (drawings, specifications, design report) will be necessary.  This stage includes:

- A detailed site assessment,

- The design process (decision making on the specific site requirements and revegetation techniques to be used),

- Documentation of the works to be undertaken in the contract (drawings and specifications),

- A review of design documents (Environment Officer or Environment Branch can provide support), and

- Tender documentation.

A specialist consultant may be engaged for the purpose.  It is critical that the consultant is conversant with the recommended methods and techniques outlined in Appendix C and can demonstrate competency in the design and documentation of revegetation works.  Refer to Main Roads’ Environment Branch intranet web site for a template of a design brief.

The documents will include the drawings, specifications and design reports as per the brief requirements.  If the necessary expertise is not available within the contract management team to review and evaluate the documents (at preliminary and final design) then a consultant is engaged for the purpose.  The specifications for the works shall be based on Main Roads’ standard specifications.

The project manager must ensure that the revegetation/landscaping strategies are translated into design decisions and documentation for the works.  It is recommended that the same consultant be also engaged to provide design support and advice to the Superintendent during the works.

### Contract Arrangements

Contract arrangements shall cover the establishment of the new vegetation and any remedial works that may become necessary; to assure the project objectives will be met.  The specific arrangements must be based on the Project Manager’s assessment of the risks associated with the project.

If the Project Manager decides to include a Vegetation Establishment Period as part of the initial contract, then contractual arrangements (monitoring, inspections and financial incentives) shall be in place to ensure any required follow up works are undertaken prior to the date of Final Completion.

If the Project Manager decides not to include a Vegetation Establishment Period as part of the initial revegetation contract, then a limited defects period of 13 weeks shall be nominated to consolidate the initial work prior to the date of Final Completion (along with defined completion criteria and inspections and financial incentives).  The establishment of the new vegetation may then be handled as a separate minor works contract or undertaken via a minor improvement works order to the regional TNC.

In some locations, covered under a delegation agreement with the Local Government Authority (LGA), the vegetation establishment may be included in the agreement for the handover of the site to the LGA for ongoing maintenance.

### Construction stage

The revegetation works may contain some or all of the following components.

- Seed collection and plant supply.

- Clearing and stockpiling of vegetation.

- Chipping and re-spreading of vegetation.

- Protection of retained vegetation.

- Weed control.

- Topsoil (strip, stockpile and re-spread).

- Erosion control and batter protection.

- Soil preparation.

- Seeding and planting.

- Maintenance during contract period.

Seed collection and plant supply must be arranged well in advance of any works to allow for the necessary lead-time to collect seed and/or propagate plants.  An exception exists for small-scale landscaping works using plants that are readily available commercially.

Surveillance is essential for the cost effective implementation of the works to ensure that the Contractor employs good industry practices.  It is important that surveillance occurs at key points during the works as identified in the standard specifications.  Often site conditions require decision making by the Superintendent and expert advice required on the implications of necessary changes e.g. plant substitutions, weed control measures, changes to specified materials.  The necessary expertise is provided by the local knowledge and experience of the Main Roads’ Representative or a consultant engaged for the purpose.

Contract requirements must be enforced to ensure compliance and provide value for Main Roads’ investment in revegetation.

### Vegetation Establishment Period

All new vegetation requires a period of several years to establish and grow.  For example, plant roots may dry out due to poor planting technique, due to lack of follow up rains or due to physical damage.  Failure to establish the new vegetation means a loss of the investment made in the project.  A minimum Vegetation Establishment Period of at least two summers, following the Practical Completion of the works, is recommended for most projects.   Key tasks may include:

- Weed control as necessary.

- Replacement of failed planting/seeding, and

- In some cases watering by the contractor.

- Limiting erosion of soil surfaces.

- Limiting access to the areas of revegetation.

During this period, the Contractor must undertake all necessary works to establish the vegetation as nominated in the contract specifications.  This includes monitoring of the works.

An evaluation of the completed works (compared to the contract completion criteria) must occur prior to the issue of the Final Certificate of Completion.  If the necessary expertise is not available within the contract management team, a consultant should be engaged for the purpose.

It is not unusual for the current Superintendent’s Representative, Project Manager and other contract staff to move onto other projects before Final Completion of the works.  It is therefore important to document the status and progress of the works to allow continuity in the administration of the contract revegetation works.

### Handover

Prior to Final Completion it is important to document the completed works.  This provides the basis for the Asset Manager to set the ongoing maintenance program.  The Superintendent’s Representative should prepare a final handover report or engage a consultant for the purpose.  This includes the contract documents, warranties and any outstanding tasks to be completed.

### Ongoing Maintenance

Following handover of the contract works, the Asset Manager will transfer the site for ongoing maintenance as per the regional TNC contract requirements.  The handover of relevant documents should include a maintenance schedule for the site, based on the final handover report and identify any outstanding or additional works to be completed.  The Asset Manager shall prepare the maintenance schedule or engage a consultant for the purpose.   It is also recommended that the Asset Manager initiate a monitoring program for the site at this time to record the effectiveness of the revegetation works and the need for any further remedial works.

## Process for Design and Construct Projects

Figure 5	Steps in recommended process for design and construct road projects.

The process followed for Design and Construct projects is distinct in the terminology used and the required documentation, the steps in the planning phase and the Contractor’s responsibility for both design and construction of the works.  Refer to Major Projects Directorate for examples and templates.    A summary of the required documentation is summarised below as Table 3.

| Document | Timing |
| --- | --- |
| Landscape & Revegetation Strategy Plan | Request for Proposals stage |
| Landscape & Revegetation Management Plan | Project design stage |
| Landscape monitoring program reports | Defects Correction Period |
| Landscape works hand-over report | Handover/Close out stage |

Table 3.	Major Project Directorate - Landscaping and revegetation documentation summary.

### Project proposal

The project charter shall identify the need, scope, extent and preliminary estimate for revegetation and landscaping works in the project.  All relevant project commitments related to revegetation of the project area, as documented in the project Environmental Assessment and Approval Process (EAAP), are included as well as any concept plan(s).  Refer to Major Projects Directorate for more details on the content.

### Request for Proposal

Technical criteria and requirements for the revegetation/landscaping works form part of the Request for Proposal documents provided to the tenderers.  This includes revegetation objectives, completion criteria and general and specific requirements.

A Landscape & Revegetation Strategy Plan is prepared by the Contractor (as tenderer) during the Request for Proposals stage in response to the Technical criteria and requirements and submitted as part of the tender.

### Project Deed

Once the successful tender is accepted the Landscape & Revegetation Strategy Plan forms part of the Project Deed.  The plan defines the site-specific strategies that the contractor will employ to design and construct the revegetation/landscaping works to achieve the revegetation objectives and completion criteria for the project.  The strategy must be more than a general statement of intent.  An assessment of the site conditions is necessary to define relevant site constraints and opportunities.  The actions proposed must be site specific, realistic and relate to the timing of the works.   This provides some quality assurance for the Main Roads’ Representative and a basis for any independent review.  If the necessary expertise is not available within the contract management team to review and evaluate the revegetation/ landscaping strategy plan, then a consultant is engaged for the purpose.

### Design Documentation

The contractor must ensure that the revegetation/landscaping strategies are translated into design decisions and documentation for the works.  At the design and documentation stage the Contractor is required to prepare a Landscape & Revegetation Management Plan.   The set of documents are to specify the revegetation works in detail and advise how the Contractor will manage the site works to achieve the revegetation objectives and completion criteria for the project.

The document set includes the drawings, specifications and design reports as per the contract requirements.  If the necessary expertise is not available within the contract management team to review and evaluate the documents (at preliminary and final design) then a consultant is engaged for the purpose.

Key decisions regarding the site management of the works have major implications for the effectiveness and success of the revegetation.  Integration of the revegetation into the relevant design and specifications of the road, bridge and other components of the works is important to increase the likely success during the construction stage.

### Construction stage

The revegetation/landscaping works will contain some or all of the following components:

- Seed collection and plant supply.

- Clearing and stockpiling of vegetation.

- Chipping and re-spreading of vegetation.

- Protection of retained vegetation.

- Weed control.

- Topsoil (strip, stockpile and re-spread).

- Erosion control and batter protection.

- Soil preparation.

- Seeding and Planting, and

- Maintenance during contract period.

Seed collection and plant supply must be arranged well in advance of any works to allow for the necessary lead-time to collect seed (at the appropriate time of year) and or propagate plants.  An exception exists for small-scale landscaping works using plant materials that are readily available commercially.

The Project Manager may decide (based on the revegetation strategy) to undertake seed collection separately and prior to the main contract.  Issues relate to storage and processing of the seed material.  Transplanting or relocation of selected plant species on site may also form part of the initial works arranged by the Project Manager.  If the necessary expertise is not available within the project management team, a consultant is engaged for the purpose.

Surveillance is essential for the cost effective implementation of the works to ensure that the Contractor employs good industry practices.  It is important that surveillance occurs at key points during the works as identified in the standard specifications.  Often site conditions require decision making by the Superintendent and expert advice is required on the implications of necessary changes, eg plant substitutions, weed control measures, and changes to specified materials.

The necessary expertise is provided by the local knowledge and experience of the Main Roads’ Representative, Surveillance Officers, or the regional Main Roads’ Environment Officer.   A consultant(s) is engaged for the purpose if the expertise is not available within the contract management team.

Contract arrangements must be enforced to ensure compliance and achieve value for Main Roads’ investment in revegetation.

### Vegetation Establishment Period

All new vegetation requires an establishment period to achieve the defined completion criteria.  A Vegetation Establishment Period of at least three years following the Practical Completion of the works is recommended for most Design and Construct projects.

During the Vegetation Establishment Period the Contractor must undertake all necessary works to establish the vegetation as nominated in the specifications.  This includes monitoring of the works by the Contractor.  Monitoring reports prepared by the contractor provide some quality assurance for the Superintendent and a basis for any independent review.

It is not unusual for the current Main Roads’ Representative, Project Manager and other contract management staff to move onto other projects before Final Completion of the works. It is therefore important to document the status and progress of the works to allow continuity in the administration of the contract revegetation works.

### Handover

Prior to Final Completion it is important to document the completed works.  This provides the basis for the Asset Manager to set the ongoing maintenance program.  A final handover report should be prepared by the Main Roads’ Representative or consultant engaged for the purpose.  This includes the contract documents, warranties and any outstanding tasks to be completed.

### Ongoing Maintenance

Following handover of the site works, the Asset Manager will transfer on-going maintenance of the site to the regional Maintenance Program as per the TNC contract requirements.  Any outstanding works or additional works must be identified in the handover of relevant documents.  The Asset Manager should prepare the maintenance schedule for the site or engage a consultant for the purpose.   The maintenance schedule is based on the final handover report.

It is recommended that the Asset Manager, initiate a monitoring program for the site at this time, to record the effectiveness of the works and the need for any further remedial works.

## Process for Standard Roadwork Projects

Figure 6	Steps in recommended process for standard roadwork projects.

### Project proposal

The project proposal shall identify the need, scope, extent and preliminary estimate for revegetation and landscaping works in the project.  All relevant project commitments related to revegetation of the project area (as documented in the project Environmental Assessment) is included as well as any concept plans.  Other issues will include stakeholder consultation, TNC handover and maintenance.  Some level of site assessment is necessary, but the requirements are not defined in detail.  The nominated Project Manager (with advice from the regional Environment Officer as required) prepares the proposal.  A consultant, if necessary, may be engaged on an hourly basis to prepare the proposal (indicative cost < $2 000).  In the absence of other information, a preliminary budget can be determined using the most appropriate benchmark costs given in Appendix D plus a 20% contingency.

### Project Plan

The project plan shall include a Revegetation Plan, which defines the scope and extent of the works; staging and methods to cost effectively deliver the works.  An assessment of the site conditions is necessary to define relevant site constraints and opportunities.  The level of planning and documentation required for the revegetation is dependent on the size and complexity of the works.   The Revegetation Plan may be simply a clear statement of objectives in the project proposal and the use of Main Roads’ standard specifications or a stand-alone assessment and report prepared for the purpose.

Ideally, the Revegetation Plan should be prepared at least two years before the proposed works are to be undertaken.  An Environment Officer, Asset Management Officer or the nominated Project Manager may prepare the document.  The Project Manager may seek to engage a specialist consultant (indicative cost < $5 000) to assess the site issues and prepare the Revegetation Plan.  Refer to Main Roads’ Environment Branch intranet web site for a template of a plan brief.   A brief for the detailed revegetation design may also be prepared at this stage.

The Revegetation Plan must include provision for appropriate measures to stabilise batters and exposed soil surfaces, if there is likely to be a transition period (more than two months) at the end of the earthworks before the seeding or planting can occur.  Control of the on-site surface drainage is important to minimise potential erosion (eg due to rainstorms).

Procurement of the revegetation works shall be completed as a separable potion of the main works contract or as a separate stand-alone contract.   The preferred option is dependant on the specific requirements for the project, the expected timing for the completion of the earthworks and the capability of the main contract tenderers.   It is often practical to complete the seeding and planting (if required) as a separate stand-alone contract.

At this stage, contract arrangements should be decided to cover establishment of the new vegetation and any remedial works.  Options are discussed below in section 4.5.4.  It is also critical to clarify the handover process and ongoing maintenance for the site revegetation works.

### Design Documentation

The extent of the revegetation works shall be clearly defined by a design and documentation process prior to finalising the contract documents.  The detailed design specifies the requirements to achieve the revegetation objectives and defines completion criteria for the works.

For small projects the detailed requirements can be defined simply from the site revegetation plan (e.g. SLK location, plan of area, species list, and standard specification clauses etc).

As the scale and complexity of the revegetation works increases a stand alone detailed site assessment and set of documents (drawings, specifications, design report) will be necessary.  This stage includes:

- A detailed site assessment.

- The design process (decision making on the specific site requirements and revegetation techniques to be used).

- Documentation of the works to be undertaken in the contract (drawings and specifications).

- A review of design documents (Environment Officer or Environment Branch will provide support).

- Tender documentation.

A specialist consultant may be engaged for the purpose.  Refer to Main Roads’ Environment Branch intranet site for a template of a design brief.  The specifications for the works shall be based on Main Roads’ standard specifications.

The documents will include drawings, specifications and design reports as per the contract requirements.  If the necessary expertise is not available within the contract management team to review and evaluate the documents (at preliminary and final design) then a consultant is engaged for the purpose.  The project manager must ensure that the revegetation/landscaping strategies are translated into design decisions and documentation for the works.

Key decisions regarding the site management of the works have major implications for the effectiveness and success of the revegetation.  Integration of the revegetation into the relevant design and specifications of the road, bridge and other components of the works is important to increase the likely success during the construction stage.

It is recommended that the consultant used for the Site Revegetation Plan also be engaged to provide design support and advice to the Superintendent during the works.

### Contract Arrangements

Contract arrangements shall cover the establishment of the new vegetation and any remedial works that may become necessary to assure the project objectives will be met.  The specific arrangements must be based on the Project Manager’s assessment of the risks associated with the project.

If the Project Manager decides to include a Vegetation Establishment Period as part of the initial contract, then contractual arrangements (monitoring, inspections and financial incentives) shall be in place to ensure any required follow up works are undertaken prior to the date of Final Completion.

If the Project Manager decides not to include a Vegetation Establishment Period as part of the initial revegetation contract, then a limited defects period of 13 weeks shall be nominated to consolidate the initial work prior to the date of Final Completion (along with defined completion criteria and inspections and financial incentives).  The establishment of the new vegetation may then be handled as a separate minor works contract or undertaken via a minor improvement works order to the regional TNC.

In some locations, covered under a delegation agreement with the Local Government Authority (LGA), the vegetation establishment may be included in the agreement for the handover of the site to the LGA for ongoing maintenance.

### Construction stage

The main roadworks contract will contain some or all of the following components.

- Clearing and stockpiling of vegetation

- Chipping and re-spreading of vegetation.

- Protection of retained vegetation.

- Weed control.

- Topsoil (strip, stockpile and respread).

- Erosion control and batter protection.

- Soil preparation, and

- Maintenance during contract period.

The separable portion of the contract (revegetation) will contain some or all of the following:

- Seed collection and plant supply.

- Protection of retained vegetation.

- Weed control.

- Soil preparation.

- Seeding and planting, and

- Maintenance during the contract period.

Seed collection and plant supply must be arranged well in advance of any works to allow for the necessary lead-time to collect seed and or propagate plants.  An exception exists for small-scale works landscaping works using plant materials that are readily available commercially.  The Project Manager may decide (based on the site revegetation plan) to undertake the seed collection and plant supply separately and prior to the main contract.  Issues relate to storage and processing of the seed material.  Transplanting or relocation of selected plant species on site may also form part of the initial works arranged by the Project Manager.

If the necessary expertise is not available within the project management team, a consultant is engaged for the purpose.

Surveillance is essential for the cost effective implementation of the works to ensure that the Contractor employs good industry practices.  It is important that surveillance occurs at key points during the works as identified in the standard specifications.  Often site conditions require decision making by the Superintendent and expert advice required on the implications of necessary changes e.g. plant substitutions, weed control measures or changes to specified materials.  The necessary expertise is provided by the local knowledge and experience of the Superintendent’s Representative, Surveillance Officers, Main Roads’ regional Environment Officer, or a consultant engaged for the purpose.

Contract requirements must be enforced to ensure compliance and provide value for Main Roads’ investment in revegetation.

### Vegetation Establishment Period

All new vegetation requires a period of several years to establish and grow.  For example, plant roots may dry out due to poor planting technique, lack of follow up rains or physical damage.  Failure to establish the new vegetation means a loss of the investment in the project.  A minimum Vegetation Establishment Period of at least two summers, following the Practical Completion of the works, is recommended for most projects.  Key tasks may include:

- Weed control as necessary.

- Replacement of failed planting/seeding.

- In some cases watering by the contractor.

- Limiting erosion of soil surfaces.

- Limiting access to the areas of revegetation.

During this period the Contractor must undertake all necessary works to establish the vegetation as nominated in the contract specifications.  This includes monitoring of the works.

An evaluation of the completed works (compared to the contract completion criteria) must occur prior to the issue of the Final Certificate of Completion.  If the necessary expertise is not available within the contract a consultant should be engaged for the purpose.

It is not unusual for the current Superintendent’s Representative, Project Manager and other contract staff to move onto other projects before Final Completion of the works.  It is therefore important to document the status and progress of the works to allow continuity in the administration of the contract works.

### Handover

Prior to Final Completion it is important to document the completed works.  This provides the basis for the Asset Manager to set the ongoing maintenance program.  A final handover report should be prepared by the Superintendent’s Representative or consultant engaged for the purpose.  This includes the contract documents, warranties and any outstanding tasks to be completed.   Appendix E4 provides a table of headings as an example.

### Ongoing Maintenance

Following handover of the contract works, the Asset Manager will transfer the site for ongoing maintenance as per the regional TNC contract requirements.  The handover of relevant documents should include a maintenance schedule for the site, based on the final handover report and identify any outstanding or additional works to be completed.  The Asset Manager shall prepare the maintenance schedule or engage a consultant for the purpose.

It is also recommended that the Asset Manager initiate a monitoring program for the site at this time to record the effectiveness of the revegetation works and the need for any further remedial works.

# DEFINITION OF TERMS

Revegetation refers to the re-establishment of a cover of vegetation suited to the location.  This usually means a cover of local native plants and involves regeneration, direct seeding, and/or planting methods.

Rehabilitation refers to earthworks associated with revegetation work and includes removal and replacement of topsoil.  In this document, the term ‘revegetation’ is used to cover both the establishment of vegetation and the preceding physical processes.

Regeneration describes situations where vegetation can be established from in situ seed banks contained within either topsoil or seed-bearing mulch.  Regeneration is a revegetation technique that can be used in isolation or with other techniques.  If used in isolation, it is usually in the more remote areas where other methods may not be suitable.

Landscaping refers to the establishment of special roadside treatments to meet functional or aesthetic objectives, which may include native or non-native vegetation (including grass turf) as well as other surface treatments or built elements.  In most cases, this vegetation will be irrigated and will have establishment and maintenance requirements (e.g. mowing and pruning) well above those associated with most roadsides.  Landscaping is generally limited to urban areas.  This guideline does not cover landscaping per se.

Restoration refers to the return of an area to a state that is, in form and composition, as similar as practicable to its pristine condition.  It is not covered in this Guideline and specialist advice would be required where restoration is an objective.

Direct seeding is a method of re-establishing vegetation through the establishment of a seed bed and the introduction of seeds of the desired species.  Seeding can be either by mechanical means using agricultural equipment or by hand.  It is used in many parts of the State as a means of establishing a wide range of species.

Planting refers to the re-establishment of vegetation by creating favourable soil conditions and planting seedlings of the desired species.  It may or may not involve irrigation.  Without irrigation, it is used only in those areas where there is sufficient reliable rainfall and where an outcome is required that cannot be achieved by other means.  The required outcome may relate to particular visual objectives, or may involve the establishment of species for which sufficient seed for direct seeding is not readily available.

# REFERENCES

Planning and Site Assessment

Bicknell, D., Baxter, A. and Denham, R. (1998). Site assessment for successful revegetation for agricultural regions with less than 600 mm rainfall. Dept of Agriculture Western Australia, Farmnote 36/98.

Grein, S.B. (1994). Native Vegetation Handbook for the Shire of Wagin. Western Australian Department of Agriculture. (note similar publications exist for about twenty wheatbelt shires).

Schirmer, J. and Field, J. (2000). The Cost of Revegetation – Final Report. ANU Forestry and Greening Australia.

Species Selection

Mortlock, W. and Lloyd, M. (eds.) (2001). Floradata – a guide to collection, storage and propagation of Australian native plant seed. Australian Centre for Mining Environmental Research Ltd, Kenmore, Queensland.

McQuoid, N. and Holt, C. (2000). Pioneer plants in revegetation. Agriculture Western Australia Farmnote 46/2000.

Regeneration

Rokich, D.P., Dixon, K.W., Sivasithamparam, K. and Meney, K.A. (2002). Smoke, Mulch, and Seed Broadcasting Effects on Woodland Restoration in Western Australia. Restoration Ecology 10, 185-194.

Direct Seeding

Anon (1998). Direct Seeding - Revegetation of Farms Information Kit. Agriculture Western Australia, July 1998.

Hein, D., Knight, A. and Beale, P. (2000). Direct seeding of native trees and shrubs on non-wetting sands. Primary Industries and Resources SA Fact Sheet, March 2000.

Hinz, R. (1990). Direct seeding in the Top End. In Proceedings of 'Sowing the Seeds' Direct Seeding and Natural Regeneration Conference, pp 117-120, Greening Australia Ltd.

Holt, C. (1998). Direct seeding of native plants for revegetation. Dept of Agriculture Western Australia, Farmnote 40/98.

Sun, D. and Dickinson, G. (1995). Direct Seeding for Rehabilitation of Degraded Lands in North-East Queensland. Australian Journal of Soil and Water Conservation 8, 14-17.

Planting

Mortlock, W., Grime, P., Bradby, K. and Ovens, N. (1993). Field Planting of Trees and Shrubs – A Guide for Landowners and Developers in the Shires of Serpentine-Jarrahdale and Murray. Community Catchment Centre, Pinjarra.

Mullan, G.D. and White, P.J. (2002). Seedling quality – making informed choices. Bushcare and the Department of Conservation and Land Management.

Site Preparation

Main Roads WA (2001). Environmental Management of Pits and Quarries for Road Building Materials (Draft). Main Roads WA, Environment Branch, June 2001.

Mullan, G.D. and White, P.J. (2002). Revegetation site-preparation in the WA Wheatbelt – Ripping and Mound ploughing. Bushcare and the Department of Conservation and Land Management, Western Australia.

Topsoil Management

Rokich, D.P., Dixon, K.W., Sivasithamparam, K. and Meney, K.A. (2000). Topsoil Handling and Storage Effects on Woodland Restoration in Western Australia. Restoration Ecology 8, 196-208.

Cotter, A., Kingery, J., and Ross, G. (2003). Topsoil Application for Revegetation of Roadsides, Roadside Revegetation Handbook, Department of Rangeland Ecology and Management, University of Idaho, and the Idaho Transportation Department.

Soil Types and Amendments

Austroads (2002). Guide to the Selection and Use of Bitumen Emulsions. Austroads Report AP-G73/02.

Fosberry, G. and Howell, M.R. (1985). Gypsum improves soil stability. Department of Agriculture Western Australia, Farmnote 32/85.

Weed and Pest Control

Agriculture Western Australia (1998). Weed control for successful revegetation for agricultural regions with less than 600 mm rainfall. Farmnote 47/98.

Brown, K and Brooks, K (2003). Bushland Weeds: a practical guide to their management. With case studies from the Swan Coastal Plain and beyond. Environmental Weeds Action Network, Perth.

Disease Control

Department of Conservation and Land Management (2003). Phytophthora cinnamomi and disease caused by it - Vol. 2: Interpreter's Guidelines for Detection, Diagnosis and Mapping.

Dieback Working Group (2000). Managing Phytophthora Dieback – Guidelines for Local Government.

Hanold, D., Stukely, M. and Randles, J.W. (2002). Mundulla Yellows - a new tree-dieback threat. Landscope 17, 41-47.

Maintenance

Denham, R. and MacDonald, S. (2000). Fire Management and Revegetation. Agriculture Western Australia Farmnote 87/2000.

Succession

Barbour, M.G., Burk, J.H., Pitts, W.D., Gillam, F.S. & Schwartz, M.W. 1999, Terrestrial Plant Ecology, 3rd edition, Addison Wesley Longman, Menlo Park, CA.

Krebs, C. (2001). Ecology. 5th ed., Benjamin Cummings, San Francisco, CA.

General

Dixon, G. and Napier, A. (1999). Roadside flora care - a manual for conserving and re-establishing native plant life. Unpublished report for Main Roads Western Australia.

Greg Barrett & Associates (2003). Roadside Revegetation Methods – Literature Review and Summary of Consultation Program.  Report for Main Roads Western Australia, September 2003, GBA00903E.

Norman, D.K., Wampler, P.J., Throop, A.H., Schnitzer, E.F. and Roloff, J.M. (1997). Best Management Practices for Reclaiming Surface Mines in Washington and Oregon. Washington Division of Geology and Earth Resources Open File Report 96-2, December 1997.

Tyler, J., Bauer, D., Vellacott, S., Fritz, S. and Mitchell, A. (1990). Revegetation with Pilbara Seed. Published by Dampier Salt.

Walden, J.F. (1982). Conservation and Regeneration Techniques. Main Roads Western Australia.

Appendix A

Roadside Vegetation – Management Objectives

| Objective | Applicability | Comments |
| --- | --- | --- |
| Roadside stability and maintenance minimisation. | All roadsides. | Established vegetation helps to maintain the stability of the roadside and road formation. The vegetation cover helps to prevent soil erosion by rainfall impact and surface water flows. Roadside vegetation should meet Main Roads’ requirements in respect of lateral clearances and other requirements (see Figure A1 and refer to Main Roads’ environmental guideline Vegetation Placement Within the Road Reserve (Doc. No. 6707/022). Roadside vegetation should be similar in structure and content to comparable naturally occurring vegetation in the local area. Exceptions occur in urban areas, where non-native species can be used for particular purposes. Vegetation cover should be such that it discourages the establishment of weeds, which in turn, reduces costs associated with the verge maintenance. |
| Conservation and biodiversity. | Where local conservation values are high (eg roadsides abutting conservation reserves). | Roadsides can play an important role in conserving local biodiversity values. There are numerous instances where rare native flora occurs within the road reserve. Roadsides can also act as corridors for wildlife, especially in areas where the surrounding lands are substantially cleared. In particular, they can provide a connection with otherwise isolated reserves. Where roadside vegetation has a high conservation value, project approval conditions may require revegetation as offsets for vegetation clearing. Revegetation, in these instances, should be as similar as possible in structure and content to existing local native vegetation. |
| Amenity and aesthetics | Case-by-case where particular roadside vegetation is deemed important for amenity or aesthetic reasons (eg urban medians, town entries). | The roadside should meet reasonable community expectations related to local amenity and aesthetics. This may include landscaping of the median and roadside, and screening of adjoining areas for visual and noise reasons. Conversely, this may include instances where revegetation excludes trees and tall shrubs to allow desirable views beyond the road reserve. Many roads are also promoted for tourism purposes (eg designated tourist drives). |
| Other purposes | Case-by-case basis. | Where revegetation of land outside the road reserve is required, e.g. borrow pits, objectives may be set in consultation with the landholder and, in agricultural areas, could include establishment of commercial crops or even seed banks for future revegetation work. Similarly, other authorities and organizations with an interest in the land, including the Departments of Conservation and Land Management and Agriculture, TransWA, Local Government Authorities, Catchment Groups, and Land Conservation District Committees (LCDCs) may seek input into the desired revegetation objectives. |

Figure A1.  Typical roadside and functional management zones.

Appendix B

Appendix B1

Annotated Checklist for Site Assessment

Physical and chemical parameters

| Parameter | Details | Comments |
| --- | --- | --- |
| Soil type | May range from clays to sands, with several types potentially occurring within a project area. Consider the likely benefit of soil amendments such as gypsum in clay soils or lime in acidic soils. Check if the need for soil amendments. Check the potential for the reuse of materials, including spoil, in the revegetation work. |  |
| Soil depth | Soils may be duplex or contain a hardpan that can affect the establishment and survival of plants. |  |
| Soil chemical and nutrient status | Consider soil acidity/alkalinity, salinity and major nutrients such as nitrogen and phosphorus. |  |
| Soil compaction | Consider compaction and road base under median strips which may not allow root penetration. |  |
| Soil contamination | Check for presence of any chemical or industrial contamination that may require removal or in-situ treatment before successful revegetation can occur. |  |
| Groundwater quality and levels | Consider depth and quality of groundwater, which can be an important determinant of revegetation success. Consider seasonal changes (e.g. waterlogging in winter, or occurrence of perched water tables) and longer term trends (e.g. rising water tables in areas affected by dryland salinity). |  |
| Prevailing winds | Consider potential impacts of wind, such as sandblasting, on establishing seedlings. |  |
| Likely traffic impacts | Consider likely or potential traffic impacts - for example, median strips on high speed heavy haulage routes are often exposed to wind from trucks. |  |
| Likely off-site erosion | Consider potential for wind and water erosion from adjacent agricultural or other land. |  |
| Site drainage | Consider whether the areas to be revegetated are water-shedding or water-accumulating. |  |
| Climate | Consider average temperature and rainfall patterns for likely significant impacts on revegetation program. |  |
| Other | Presence of outcropping rocks, stumps and other site characteristics likely to affect earthworks. |  |

Biological parameters

| Parameter | Details | Comments |
| --- | --- | --- |
| Existing flora and vegetation | Consider the condition and content of any existing vegetation. It is particularly important, through careful planning, to optimise the preservation of any existing native vegetation where realignments are being considered. Take note of any unusual local varieties of plants for which locally collected seed should be used. Semi-quantitative data on numbers of plants per unit area will assist with designing revegetation programs. |  |
| Existence of any Threatened Flora | These include Declared Rare Flora (DRF), Priority Flora and Threatened Ecological Communities (TEC’s) and are common in some regions. Work undertaken should protect and enhance these populations and communities. |  |
| Desirable species | Consider which species should be included in any direct seedling or planting work proposed. Species selection should consider the objective of the work (see Appendix A) and practical considerations such as the availability of seed. |  |
| Weed status | Consider existing weed status, especially the presence of Declared Plants and those weeds that are going to seriously impact remaining native vegetation and revegetation efforts. Estimate the likely weed seed bank in topsoil and determine whether weed emergence will require control. Be aware that some weeds may not be evident at certain times of the year but are still present. If control is required and the weed seed bank is significant, consider whether scalping is a better control option than herbicide control. Also consider the likelihood of invasion of weeds from adjoining land. |  |
| Pest status | Consider the likely pressure on establishing vegetation from insect and vertebrate pests and what control mechanisms may be necessary throughout the revegetation project. |  |
| Conservation value of adjoining land | Ensure revegetation work complements, in both form and function, nearby or adjacent land of conservation value. It is particularly important when considering species selection and seed source. |  |
| Significant trees | Identify any existing objects, such as trees, which are of historical or habitat significance (e.g. trees with nesting hollows present) and ensure revegetation work complements the trees. Also, identify any trees of special significance e.g. grasstrees, that could be salvaged ahead of clearing for transplantation to revegetated sites. |  |
| Likely dieback status | Consider the likely status of the soil with respect to dieback disease and consider what, if any, precautions with topsoil management or species selection might be required. |  |

Other parameters

| Parameter | Details | Comments |
| --- | --- | --- |
| Land status | Consider the status of the area to be revegetated and any future maintenance requirements. For example, revegetation of borrow pits may be purpose-specific and entail future management by a private landholder. Check width of road reserve. |  |
| Local land use | Consider local land uses (e.g. agricultural, water catchment area) and how they may impact the establishment and future management of the vegetation. |  |
| Acquisitions required | For revegetation work to be effective it may need to be preceded by acquisition of adjoining land. |  |
| Site infrastructure | Identify services eg power lines (overhead or buried), and other underground services that could be affected by earthworks. |  |
| Heritage values | Consider any Aboriginal or European heritage values that may be affected by the revegetation work. |  |
| Views and vistas | Consider any particular views or vistas that the road may have and take into account when planning revegetation work to ensure that outstanding views or vistas are enhanced and not screened. |  |
| Consultation and community involvement | Consider the value of conducting consultation about the proposed revegetation project and taking into account community opinion. Consultation could include local authorities and other relevant land managers, such as the Department of Conservation and Land Management. Consider opportunities for community involvement and / or integration of the project with plans developed by local landcare groups or other interested parties (while maintaining Main Roads’ own objectives). |  |
| Main Roads guidelines | Refer to guidelines that dictate parameters such as setbacks and sightlines. Identify areas not to be revegetated e.g. around bridge abutments. |  |
| Landscaping | Identify need for any additional landscaping works e.g. grassing. |  |
| Irrigation | Consider availability of water source if irrigation is likely to be a requirement. |  |

Appendix B2

Checklist for Site Assessment

Physical and chemical parameters

| □ | Soil type |
| --- | --- |
| □ | Soil depth |
| □ | Soil chemical and nutrient status |
| □ | Soil compaction |
| □ | Soil contamination |
| □ | Groundwater quality and levels |
| □ | Prevailing winds |
| □ | Likely traffic impacts |
| □ | Likely off-site erosion |
| □ | Site drainage |
| □ | Climate |
| □ | Other |

Biological parameters

| □ | Existing flora and vegetation |
| --- | --- |
| □ | Existence of any Threatened Flora |
| □ | Desirable species |
| □ | Weed status |
| □ | Pest status |
| □ | Conservation value of adjoining land |
| □ | Significant trees |
| □ | Likely dieback status |

Other parameters

| □ | Land status |
| --- | --- |
| □ | Local land use |
| □ | Acquisitions required |
| □ | Site infrastructure |
| □ | Heritage values |
| □ | Views and vistas |
| □ | Consultation and community involvement |
| □ | Main Roads guidelines |
| □ | Landscaping |
| □ | Irrigation |

APPENDIX C

RECOMMENDED REVEGETATION METHODS AND TECHNIQUES

KEY REVEGETATION METHODS

Regeneration from topsoil

In some instances, establishment of a satisfactory revegetation outcome can be achieved through management of existing seed banks or the use of seed banks contained within topsoil ‘grafted’ from elsewhere.  In situ seed banks can be used where the topsoil is largely intact and weed seed numbers are low.  Regeneration can be encouraged by scarification of the soil.  This method may be particularly suitable for very small areas.

Where regeneration from existing topsoil alone will be inadequate, there may be the opportunity to apply a fresh topsoil containing seed of target plant species.  Within reason, topsoil can be spread more thinly when reapplied to cover a larger area than originally stripped.

Be aware of the potential for dieback infection when handling soils (see section C.2.10).

Regeneration from seed-bearing mulch

Where vegetation has been stripped and mulched, the returned material can be an important source of seed and organic material.  If cleared vegetation is to be used as a source of seed, it must be mulched immediately.  Only those species that carry their seed in the canopy (bradysporous species) can be re-established in this manner.

Laying of freshly-cut brush (‘brushing’) can be used to introduce bradysporous species without mulching.  The sand mining industry has obtained good results with this method.  It is not the same as brushwood layering where stems are encouraged to take root.  Western Australian species are not amenable to layering.

Caution should be taken when collected or applying mulch to ensure weeds are excluded.

Direct seeding

Direct seeding involves distributing seed directly onto sites that have been suitably prepared to encourage germination and growth.  In the past, Main Roads has had considerable success with revegetating areas using direct seeding.  In the more arid parts of the State, successful establishment can be expected to take longer and be less reliable.

Planting

While direct seeding can be carried out in any part of the State, tree and shrub planting is only likely to be successful in those areas that experience reliable rainfall (see Figure 1).  This restricts planting without irrigation to the south-west corner of the State.

Where establishment of self-sustaining native vegetation is the aim, planting is only used to supplement direct seeding.  For example in some locations, tree species may be planted and the understorey layer direct seeded.   Spacing of plantings varies between projects and species but should reflect naturally-occurring densities in the local area.

Planting alone is usually limited to urban roads and streets to achieve amenity and roadside stability objectives.

Selection of technique

Each of the above techniques has its advantages and disadvantages.  Key factors to consider are outlined in Table C.1.

| Method | Advantages | Disadvantages |
| --- | --- | --- |
| Regeneration from topsoil | Low cost Can be used in addition to other methods Reliable source of local species and provenance seed if topsoil is in good condition. | Limited to species in soil seed bank. Topsoil must be fresh or only stored for a short time for best results. Can result in the spread of weed seed. |
| Application of seed-bearing mulch | Low cost if suitable equipment available. Will contribute more species than topsoil alone if seed stored in canopy. | Can only be used where native vegetation with low weed content is present. Cannot be stockpiled. Poor availability of equipment in some regions. Only some species carry seed in canopy. |
| Direct seeding | Costs less than planting. Seed is easier to handle than seedlings. Seed mixtures give a more ‘natural’ distribution of plants. More species available as seed. Better root growth than plantings and therefore potentially better survival. Higher diversity and similarity to local native plant communities. | Higher cost than regeneration from topsoil or mulch application. Less reliable establishment on low rainfall sites. Results less reliable on sandy sites due to sand blasting and drying of the soil profile. Weed management can be labour-intensive and timing may be critical. More time required than planting to determine if successful. |
| Planting | Immediate visual result. Complete control over what occurs where. Most suitable method to establish amenity plants. Water can be applied if necessary to enhance survival. Best method to establish plants for which seed is hard to get or difficult to germinate. | Only suitable in south-western corner of State (without irrigation). Probably the most expensive approach but depends on species selected. Labour intensive and slower than direct seeding (4 ha/day versus up to 50 ha/day) Mature plants may be susceptible to wind blow. |

Table C.1	Advantages and disadvantages of the various revegetation techniques.

SITE PREPARATION

Preliminary Earthworks

Setting out

Within any given site earmarked for revegetation work, there may be a number of distinct areas which are planned to receive different physical treatments or seed mixes, used for temporary topsoil storage, or have some other particular requirement.  It will often be necessary to physically peg sites to ensure activities proceed in line with those planned.

Topsoil management

Where revegetation is not being conducted on in situ soils, soil profiles can be created from stockpiled materials.  Topsoil, in particular, is very valuable both as a seed source (see Section C.1.1) and as a suitable seed bed for establishing new plants.

If topsoil is relatively weed-free, the two major factors that affect its utility in revegetation work are depth of stripping and duration of storage.  Shallow (<100 mm) stripping of topsoil leads to better seedling recruitment than deeper (300 mm) stripping as the seed bank is diluted with non-seed bearing soil.  As the seed bank is usually contained within the top few centimetres, it is only this material which will yield new seedlings.  If the aim of the project is to optimise recruitment of seedlings from the seed bank, there is a distinct advantage in separate stripping, storage and re-use of the soil containing the seed bank and the underlying topsoil and subsoil.

While fresh topsoil is clearly preferable to optimise revegetation outcomes, temporary stockpiling of topsoil may be unavoidable.  Researchers have found that stockpiling of topsoil leads to a significant decline in seedling recruitment over time.  Immediate re-use is always desirable.  When stockpiling is necessary, windrows up to 1m in height is the preferred method.  Stabilisation of stockpiles with mulch or vegetation should be considered if the stockpiles are expected to be required for more than a few months before reuse.

Timing is also important in topsoil management.  For jarrah forest rehabilitation, topsoil was collected in summer, when the seed bank is at its highest.  Soils are best handled when dry and stripping and spreading topsoil in winter in the south-west depresses seedling recruitment compared with autumn.

‘Scalping’ of soils may be necessary where weeds are a problem (see Section C.2.8.2).

Erosion Control and Water Harvesting

Uncontrolled erosion has the potential to damage revegetation work and requires expensive remedial works.  Most revegetation work will require preparation of a seed bed and this would normally involve ripping along the contour.

Grader formation of level banks can be used to harvest water in some situations.  Caution should be taken to ensure dispersive (sodic) materials are not used to construct banks or contours as breakthroughs can readily occur.

Steep Slopes and Batters

Cuttings and batters in the south west of the State are often gravelled rather than topsoiled.  This gives batters more stability while still allowing revegetation.  There are some successful examples, however, where topsoil has been used and its success is probably dependent on the length of slope, aspect and other environmental variables.  Where rocky material is present, an option is to leave steps with natural ledges and projections and topsoil lightly for revegetation.

On steep sandy slopes through cuttings or around flyovers, gravel and mulch, including hydromulch, can be used to stabilise the surface.   Mulch should be incorporated into the soil to provide resistance to erosion.

Existing Pavements and Gravel Road Surfaces

Where disused pavements and gravel roads occur, good revegetation has been established when the material has been deep ripped but otherwise left in situ.  The ‘rocky’ surface appears to act as a moisture trap and promotes seedling establishment.  This practice may not be acceptable in some situations where there is high visibility and stakeholder interest.

Waterlogged or Saline Soils

Rising water tables are a serious issue with implications for roadside revegetation.  Where roadside vegetation occurs in areas that are salt-affected or prone to waterlogging, mounding can be used.  Mounding usually consists of producing a raised strip of soil in a ‘M’ shape into which seedlings can be planted or seed sown.  In loamy or heavy soils, mounding should be carried out immediately prior to revegetation.  Earlier preparation may allow salts to accumulate at the surface.

Mounds can be constructed using a grader but specially constructed mounders and ripper/mounders are available.

Soil Amendments

During the site assessment process, the need for soil amendments may be identified.  These can be incorporated into the soil during the site preparation.

There can be significant costs associated with soil amendments and the benefits should be justified.  This can only be done on a case-by-case basis.  Additionally, caution should be exercised over the use of soil amendments that will significantly alter native soils, potentially impeding the establishment of local native vegetation and encouraging weed species.

Mulch

Mulching with organic matter, wood chips or rocks slows the movement of water across the soil surface and reduces evaporation.  Research has shown that surface mulch will improve the establishment of plants from seed but only if the mulch application is not too thick (< 3 cm) and if seeding is conducted prior to mulching.  Mulch that is too thick and has seed applied over the top of mulch will reduce seedling recruitment.

If the mulch is to be incorporated into the soil, however, seeding can be conducted after mulching.  Indeed, mulching is most effective on slopes if incorporated into the soil, especially sandy soils, rather than laid across the surface.  Incorporation can be readily achieved using a rotary hoe.

The costs and benefits of mulching vegetation on site compared with the importation of mulch from elsewhere should be considered.  While mulching vegetation on site may be more expensive, if it contains seed-bearing material it may assist with the establishment of local native vegetation.  Again, the relative costs and benefits should be considered.

Brush thatching can be also used on steep banks to control erosion, protect seedlings and reduce evaporation.  A stone mulch has been used in the Pilbara to stabilise soils and retain moisture.  Where high pH clays occur, mulching has been used to create a more favourable environment for planting seedlings.

Mulch can be also be used to improve the survival of seedlings.  Drought stress has been found to be a major cause of poor performance in woody plants in sandy loam soils and recommended incorporation of ‘compost’ into soils to improve survival.

If freshly mulched material needs to be stockpiled, it should not be stockpiled to heights greater than 750 mm due to the risk of ignition.

Generally, straw mulches are not used by Main Roads.  Some mulches, such as shredded karri bark, can be a fire hazard and should be used with caution.  Most Main Roads’ contracts require mulching for embankments greater than 3m in height.

Application of mulch material by hydromulching is commonly used to help provide short term stabilisation of slopes and other erosion-prone areas.  The mulch can contain seed, usually grass seed which forms a rapid but temporary cover.  It is probably not suitable for application of fine native plant seed.  Paper-based mulches can have an adverse impact on soil moisture content, particularly in sandy soils, as they form a seal over the surface.

Fertiliser

Fertiliser can be used with caution to improve revegetation outcomes.  Fertiliser can improve the establishment of native plants, especially in very low nutrient environments such as borrow pits or deep sands, but incorrect types and quantities can encourage weed growth and adversely affect native plants.  High phosphorous fertilisers should be avoided and slow release is preferred.  Nitrogenous fertiliser has been shown to delay successional processes (see Section C.8) by allowing the dominance of annuals for a longer period.  Mulched soils, however, can experience a nitrogen shortage as organic material breaks down.  Fertiliser requirements, therefore, will need to be assessed on a case-by-case basis but, in the absence of other information, the suggested usage is shown in Table C.2.

| Revegetation Method | Previous Land Use | Suggested Fertiliser Usage |
| --- | --- | --- |
| Topsoil regeneration only | Pastoral / native vegetation | Nil |
| Direct seeding | Native vegetation | 100-200 kg/ha of slow release NPK with trace elements. |
|  | Agriculture | Nil |
| Tree planting | Native vegetation | 1 x 10-20g slow release NPK tablet per tree |
|  | Agriculture | Nil |

Table C.2	Suggested fertiliser usage for revegetation projects.

Care needs to be taken around waterways as fertiliser runoff may impact the water quality.

Gypsum

Gypsum is commonly used to improve water infiltration in hard-setting heavy clay soils.  Gypsum-responsive soils typically have clay contents ranging from less than 15% to more than 25%.  The techniques outlined in Fosberry and Howell (1985) can be used to determine whether gypsum is likely to provide a beneficial effect.  If gypsum is applied, application rates up to 2.5 t/ha are used, with no benefit from greater applications.

Gravel

Gravel can act in the same manner as a mulch in that it traps and retains moisture, reduces erosion and may also raise soil temperature.  Gravel covers have been shown to promote roadside revegetation.  Studies have shown, however, that their effectiveness depends on fragment size, degree of incorporation into the soil and ambient conditions.  Smaller, loose fragments appear to promote water infiltration and vegetation establishment better than larger, stony material.

Clay

There have been instances where clay has been successfully used as a cover over sandy soils to improve moisture retention.  However, experience has shown that it must be applied evenly and incorporated into the surface soils to be effective.  Poor results have resulted where this has not been done.

Lime

Lime is a suitable amendment for acidic soils but is not commonly used within Main Roads.  Some soils are naturally acidic and, if using local native plant species, amendment with lime should not be necessary.

Wetting agents

Wetting agents can be very useful in non-wetting sandy soils.  They can be added prior to and at the time of planting to encourage water infiltration.

Cover crops

Cereal rye has been used successfully as a ‘nurse crop’ for direct-seeded native plants.  A nurse crop can protect small seedlings against strong winds and can assist with soil stabilisation while perennial vegetation is establishing.

Mycorrhiza

Mycorrhiza is symbiotic soil fungi that can improve the nutrient status and survival of seedlings.  They can be contained within fresh topsoil but decline under stockpile conditions.  Where fresh topsoil can be retained and a mycorrhiza presence maintained, research suggests that revegetated sites may be able to progress more quickly towards a climax community.   Research has been conducted over some years in Western Australia to develop an inoculum for mine soils (see www.clr.uwa.edu.au).  To date, this methodology has not been used in Main Roads but the potential to use it will increase as research progresses.

Other

Various other amendments may be available locally and may warrant consideration.  Examples include sewage sludge and ‘red mud’ (bauxite residue).

Ripping and Other Methods of Seed Bed Establishment

Seed bed establishment is a key element to a successful revegetation program.  The methods used, however, depend on the site characteristics.  For example, Table C.3 shows examples of recommended site preparation on different soil types prior to planting and highlights the different approaches to different soils.

| Soil type | Ploughing / rotary hoeing | Ripping to 0.5 m | Mounding (if wet) | Furrowing (if dry) | Weed control |
| --- | --- | --- | --- | --- | --- |
| Deep sands | - | (( | ( | ( | (( |
| Sands over clay | ( | (( | ( | ( | (( |
| Heavy clays | (( | (( | (( | - | (( |
| Gravels and clays | - | (( | - | - | (( |

Table C.3	Suggested preparation for different soil types prior to planting. Key: (= advised, (( = essential.

Ripping using a single tine at intervals of 1m is a common method of alleviating compaction and creating a seedbed.  The development of deep root systems may be critical to long term plant survival and soil impedance needs to be alleviated in reconstructed soils.  Deep ripping of soils should be conducted to at least 400mm, more if a hardpan exists.  Similarly, a fine tilth in clay soils (as opposed to ‘blocky’ or cloddy fragments) is important for good seed to soil contact.  Winged tines have been used with success in the mining industry to alleviate soil compaction and create opportunity for lateral root growth from rip lines.

Ripping is best carried out dry to maximise the shattering effect within the soil.  Ripping should occur before the break of season with seeding following immediately afterwards, allowing sufficient time for some moisture to infiltrate the rip lines.  Ripping after the break of season may destroy any germinating seeds in the topsoil.  A good overall coverage of ripping for seed and seedling establishment is given in Mullan and White (2002a).

Where the material is very hard, e.g. base of gravel pits, cross hatch ripping is required to encourage 360( root growth as plants with roots only along a rip line may be prone to wind damage.  Ripping is less important in sandy soils but should still be conducted.

Once established, contour rip lines can act as a trap for wind-blown seed.

Rotary hoeing is also used after ripping but prior to seeding or planting in some areas.  This will improve water infiltration and the ability for seedlings to establish lateral roots.  Ripping may result in the establishment of furrows but specialist-furrowing equipment can be used if necessary.

Weed Control

Failure to control weeds during revegetation work can lead to numerous problems including ongoing maintenance costs in weed control, poor public perception of Main Roads’ revegetation efforts, and the potential failure of revegetated sites and subsequent costs of reworks.  Pests are less often a problem but can also have a significant impact.

Cultivation

Annual weeds can be controlled through repeated cultivation of weed-affected soils.  This method is less effective for perennial weeds.  A lead time of at least one year is required prior to revegetation.  Cultivation alone, however, is generally not recommended and needs to be used in conjunction with herbicides.

Scalping

Where soils are seriously weed-infested, a substantial weed seed bank is likely to exist and will compete with native species sown or planted.  Removal and disposal of the top layer of soil (‘scalping’) can remove the weed seed bank and greatly reduce the competition from weeds that can occur.    As an example, in the Great Southern region, scalping 50-60mm of weed-infested topsoil gave 10,000-15,000 stems/ha as opposed to 200-1,500 using herbicide and cultivation only.   Scalping can also be used to treat water-repellent soils but, for whatever purpose it is conducted, it will be necessary to address the loss of organic matter and nutrients and increased potential for water and wind erosion.  These issues can be addressed by undertaking scalping immediately before seedbed preparation, utilising a fast-growing cover crop and incorporating mulch into the seedbed.

Some Main Roads’ guidelines have required scalping up to a depth of 120mm.  The depth required will depend on local conditions.  Scalped layers can be transferred to farmland borrow pits, used as a topsoil on salt scalds, or used to backfill gully erosion or otherwise buried.  If these options are not available then the scalped layers can be placed in windrows and used to assist with water management but they may be an ongoing source of weed seed until revegetation is well advanced.  Scalping should not be conducted too long prior to revegetation as reinfestation with weeds can occur.

Scalping may not be suitable for some soils if soil zones unfavourable to plant establishment are exposed.  Chemical control is best in these circumstances.

Chemical Control

All sites apart from some supporting intact native vegetation are likely to require some chemical control of weeds prior to revegetation.  When establishing seedlings, Department of Agriculture studies suggest that the best results are obtained by using a combination of knockdown and high residual herbicides.  The time of application is critical and needs to be after most weed seed has germinated, but before the early germinants can flower and seed again.  More than one pre-sowing or planting application may be necessary.

Selection and application of herbicides requires experienced advice.  The Environmental Guideline on Vegetation Control covers this issue in detail. The site assessment data should be used to determine the most appropriate methods of control.

Information about Weed Control

Other than the Main Roads’ environmental guideline for Vegetation Control, there is a large amount of information available on weeds and their management.  The information can be located through a number of useful websites, of which the following are the most directly applicable:

- Department of Agriculture (http://agspsrv38.agric.wa.gov.au/)

- Environmental Weeds Action Network (http://members.iinet.net.au/~ewan/)

- Plant Protection Society of Western Australia (http://members.iinet.net.au/~weeds/)

- Bay of Plenty Regional Council, Weeds in New Zealand (http://www.boprc.govt.nz/Weeds/Weed-Index.asp).

Pest Control

Redlegged earth mite (Halotydeus destructor) can be a problem in agricultural soils where they can eat germinating seedlings.  In Western Australia, the presence of capeweed is an indicator of when they may be present.  Le-Mat( is used for control.  More information can be found at the following website:

- Department of Agriculture (http://agspsrv38.agric.wa.gov.au/)

Wingless grasshoppers can be a problem on the coastal sandplains if grasslands are present.  If the surrounding vegetation is predominantly native they will probably not occur in numbers.  Control is by a diesel/pyrethrum mix.  Snails can also be a problem on the coastal sandplains.  In the Kimberley’s, ants may eat or bury seed.  Control can be achieved by not sowing too far in advance of significant rain.

In several Main Roads’ regions, rabbits were recorded as a pest that will damage young plants.  Baiting can be conducted with which the Department of Agriculture may assist.  Plant/tree guards are regularly used in urban locations as a control measure.   Other vertebrate pests that can significantly impact on revegetation are goats, restricted to parts of the pastoral regions, and kangaroos.

Disease Control

Many road projects and revegetation works will involve the movement of soils materials.  In some areas, this can lead to the risk of spread of dieback and is an important consideration in undertaking revegetation work.  Where this risk exists, Main Roads uses a document by the Dieback Working Group (2000) as a key reference and management guideline.

Phytophthora - background

Dieback is the common term used to describe the effect of Phytophthora spp. on our native flora.  Phytophthora are introduced soil-borne pathogens (water mould) that kill a wide selection of plant species of the south west of Western Australia. The most common and aggressive Phytophthora that causes disease in the native vegetation of the south west of Western Australia is Phytophthora cinnamomi, however there are eight different species of Phytophthora that have the potential to impact on our native vegetation and over two hundred that have been identified throughout the world.

In Western Australia, P. cinnamomi will establish and spread under favourable environmental conditions as outlined in Table C.4.

As a general rule of thumb, dieback-susceptible areas can be regarded as being south of a line from Geraldton to Esperance but infections can occur elsewhere.

| Factor | Favourable Conditions | Unfavourable Conditions |
| --- | --- | --- |
| Temperature | 15-30(C | < 0(C and > 35(C |
| Soil type | pH 5-6 (most forested areas), siliceous sands in water gaining flats, infertile soils with texture allowing good lateral movement of water. | Alkaline pH, coastal calcareous sands. |
| Annual Rainfall | > 800 mm | < 600 mm (unless in areas where water is concentrated) |

Table C.4	Conditions favourable and unfavourable to the establishment and spread of the soil pathogen Phytophthora cinnamomi.

Some of the affected native plant species are useful indicators for the early detection of P. cinnamomi infections and some key indicator species are also shown in Table C.5.  Other key indicator species include grass trees (Xanthorrhoea spp.).  A full list of known indicator species is given within Department of Conservation and Land Management (2003).

| Plant Family | Species Susceptibility (%) | Key Indicator Species |
| --- | --- | --- |
| Heaths (Epacridaceae) | 80 | Beard heaths (Leucopogon spp.). |
| Banksias (Proteaceae) | 92 | Banksias (especially B. grandis, B. littoralis and B. attenuata). |
| Peas (Papilionaceae) | 57 | Bossiaea aquifolium |
| Eucalypts (Myrtaceae) | 16 | Jarrah (Eucalyptus marginata). |

Table C.5	Plant families with high levels of susceptibility to infestation by Phytophthora cinnamomi and key indicator species.

While many plant species are adversely affected by Phytophthora, some species, e.g. prickly moses (Acacia pulchella), are believed to exude chemicals that may suppress it.

Management of Phytophthora

Detection of Phytophthora within susceptible sites is best achieved through the observation of indicator species health and patterns within susceptible vegetation communities that can be associated with Phytophthora disease.

Soil and root tissue samples can be taken from suspect sites and processed in any of a small number of laboratory facilities that specialise in the isolation of Phytophthora from such a medium.  This is routinely done for major road projects in susceptible areas and in forest areas is managed in consultation with the Department of Conservation and Land Management (refer to Dieback Working Group (2000) guidelines).

Other plant diseases

Another pathogen affecting native tree and shrub species is Mundulla Yellows.  As the name suggests, it causes yellowing and loss of foliage.  Mundulla Yellows occurs extensively in South Australia and has spread to Western Australia in recent years having been observed along the Mitchell Freeway. The mechanisms by which the pathogen spreads are not well understood yet but it is apparently not soil-borne so will have different control mechanisms to those required for Phytophthora spp.

SPECIES SELECTION

General Approach

Whether using direct seeding or planting methods, great care must be taken over species selection.  The decisions made at this stage are likely to be apparent for many years to come.  The species selected should be consistent with the objective(s) determined and should match the soil and other conditions identified in the site assessment.  In some instances, species selection may be subject to statutory requirements.  A number of different seed mixes may be required for any one project.

Species selection for a direct seeding program will depend on the objective of the program.  Where an outcome similar in structure and function to the original vegetation is sought, forty or more species may be selected for use, depending on the target community and the degree to which it is sought to replicate it.  As a minimum, it would include the most common local trees and shrubs matched with soil type.  In the revegetation of areas of conservation importance, the project may seek to establish as many of the locally-occurring species as possible.  Species numbers can be reduced if, for example, revegetation of a narrow strip as a windbreak or screen is being attempted.  In this case, only 8-10 species may be appropriate.

The biology of individual species may have an impact on the ability to collect and sow seeds in revegetation programs.  In the banksias, for example, some species are killed by fire and can only reproduce from seed while other species can resprout after fire.  Species killed by fire tend to set significant amounts of seed while ‘resprouters’ set less seed.

Use of locally-occurring species

Background

Most species used in revegetation work will be locally-occurring provenance native plants.  Native plants, and particularly locally-occurring species, are preferable over other species because of:

- their generally better survival and growth in the local environment,

- reduced likelihood to become invasive,

- their indirect and direct biodiversity value, and

- their contribution to a local ‘sense of place’.

Particular species can be identified from site-specific flora surveys or from various other sources including:

- local knowledge of revegetation contractors and botanists, and regional staff within the Departments of Agriculture, and Conservation and Land Management (CALM),

- various databases, including

REX (Revegetation Expert - available from the Department of Agriculture), and

Floradata (from the Australian Centre for Mining Environmental Research),

CALM Florabase (http://www.calm.wa.gov.au/florabase/index.html) and

- published information (e.g. Wheatbelt vegetation data that covers over twenty Shires).

In considering the objectives of roadside revegetation, however, there is scope for the use of non-local, and indeed non-native plants, and many are used for specific purposes.  These purposes include erosion control, maintenance of sight distances, and visual amenity.  If non-local or non-native plants are to be used, care must be taken to ensure they can survive without excessive intervention and, equally, that they do not have the capacity to become invasive.

Defining provenance

A number of contracts for road projects have required that provenance seed only be used in revegetation work.  This objective may arise from within Main Roads itself or from environmental conditions placed on it by statutory authorities.  Provenance refers to:

“seed collected from a natural population…….and is also used to describe patterns of genetic variation exhibited by a species over its geographic range. These patterns are often closely associated with the ecological conditions in which the species has evolved. When a number of provenances of a species are planted out at the same site it is usual to find differences in survival and growth performance (and possibly other characteristics) between provenances. Because the patterns of genetic diversity can be difficult to quantify and delineate, provenance is difficult to define in a precise geographical way” (Mortlock et al, 1999).

While provenance, therefore, cannot be defined in a purely geographical sense, the best way to ensure provenance requirements are met is to use seed collected in the local area.  Where this is not possible, Watson (1991) recommends the use of “climate, habitat matching and common sense” as ways of delineating provenance.  In other words, provenance requirements could be met by using:

- plants occurring within the same biogeographic region (see Figure C.1), and

- with no other obvious differences (from locally-occurring plants) noticeable in the field.

Note that if local variants occur, they must be used ahead of collections from elsewhere.

The following definitions are used:

Provenance seed is seed collected from within the same biogeographic region as the project area and from a similar habitat.  It has been collected from plants that contain no obvious differences to locally-occurring plants of the same species.

Locally-occurring seed is provenance seed collected from the project area or from similar habitat occurring nearby.

Drawbacks of local seed collections

Unbending adherence to a tight geographic definition of provenance for seed collection purposes could lead to unsustainable levels of seed collections from local populations.  Furthermore, sourcing locally-collected species may be very difficult in heavily cleared areas.  Where a local seed supply is required but is very limited in availability, production of tubestock from seed may be a better option than using the seed for direct seeding.

Guideline for use of local provenance seed and seedlings

The objective of a revegetation project is the major factor in determining the source of seed and seedlings to be used.  Table C.6 provides a guideline as to the extent to which locally-occurring and provenance seed should be used.

For example, for projects seeking to achieve roadside stability and maintenance minimisation, at least 90% of the seed used should be provenance, of which at least 20% should be locally-occurring.

It is appreciated that in some areas that have been heavily cleared, such as parts of the Wheatbelt, it may be difficult to rigorously apply these guidelines.  Alternatives may need to be sought or seed collections spread over a number of years.

Figure C.1	Western Australian biogeographical regions (from http://www.ea.gov.au/).

| Objective | Proportion of provenance seed (%) | Proportion of seed collected locally (%) | Proportion of seed from other sources (%) |
| --- | --- | --- | --- |
| Roadside stability and maintenance minimisation | > 90 | > 20 | < 10 |
| Conservation and biodiversity | 100 | > 50 | 0 |
| Amenity and aesthetics | > 80 | > 20 | < 20 |
| Other purposes | Provenance seed preferred but decided on a case-by-case basis. |

Table C.6	Guideline for use of locally-occurring and provenance seed in revegetation projects.

Other factors

Having satisfied any requirements for local occurrence and provenance, there is a wide range of other issues, which could be a basis for the selection, or omission, of particular species.  The following are some examples:

- Availability of viable seed.  The biology of some species may mean germinable seed is not readily available, either for use in direct seeding or for raising seedlings.

- Early successional species.  It is desirable to include some early successional species within a seed mix for direct seeding.  These species may not be apparent in local mature vegetation.  Local advice about suitable species should be obtained. See section C.8 for further discussion on succession.

- It has been observed that many, though not all, eucalypt species establish better and are less prone to insect attack if sown with understorey species.  Therefore, a program with the aim of establishing eucalypts should include understorey species. Understorey plants are also important for erosion control as erosion can occur between established trees.

- Future maintenance requirements, e.g. pruning, must be considered.  Species that are likely to require future pruning or particular maintenance should be avoided.

- Fire tolerance – in certain circumstances, species having greater fire tolerance might be a priority.

- Price and availability – having identified certain species as desirable, they may not be available or may be prohibitively expensive.

- Some species may have allelopathic qualities, that is, they inhibit the establishment of other species in their immediate vicinity through the release of root or leaf exudates.  Where specific species are known to have this feature and they meet other requirements, they could be used to minimise roadside maintenance requirements be restricting weed growth.

- For deep, water-repellent sands, acacias are very useful as a colonising species.

- New developments, such as tissue culture, may make it possible to establish plants for which viable seeds or seedlings were not previously available.  Similarly, research into groups of plants, such as native grasses, may result in them being more commercially available than they have been previously.

SOURCING SEED AND PLANT MATERIAL

Seedlings

Seedlings must be of good quality to produce a reliable result.  The nursery industry now has an accreditation system under which nurseries agree to adhere to best practice guidelines for nursery management and plant production (although there are no specific product quality standards specified).  The accreditation is operated under the Nursery Industry Accreditation Scheme, Australia (NIASA)  (http://www.ngia.com.au/).  As at September 2003, about thirty Western Australian nurseries were accredited.  They are listed at the above website.

It is desirable for Main Roads to obtain their plants from accredited nurseries only.  Where this is not possible, adherence to NIASA best practice guidelines can be made a contractual requirement.  If supply problems still exist, exceptions can be made on a case-by-case basis.

The acquisition of stock from an accredited nursery does not preclude the need for their careful inspection prior to planting.  Seedlings should:

- be 10-15 cm high,

- have a well-developed root system,

- be ‘hardened’ (exposed to full sun and a reduced watering regime for at least one month), and

- be of a generally healthy appearance and free of pests and diseases.

Useful further reading on assessing quality in seedlings occurs in Mullan and White (2002b).

Some thought should be given to the delivery arrangements so that it coincides as close as possible to the time of planting.  This will avoid any problems associated with the temporary storage and maintenance of the seedlings.

Seeds

Supply

No formal system of ensuring seed quality exists.  As a minimum, however, seed merchants should be able to supply the following:

- A current Commercial Purposes Licence issued under the Wildlife Conservation Act 1950.

- Confirmation that their collection, handling and storage methods are in accordance with good industry practice.

- Details of the origin of the seed (date and area collected).

- Proof of current seed germinability through viability testing.

Potential problems can be minimised through the use of established, well-known seed merchants with a record of success in revegetation projects.  It is also important to verify that the seed ordered matches that used for the task.

Procedures related to seed handling can be optimised by reference to guidelines provided by Florabank (see Table C.7).  While these guidelines are aimed at community-based rather than commercial activities, they do provide sound guidance to the basic level of management that can be expected.

The website (http://www.florabank.org.au/) also includes a model code of practice.

| Guideline | Subject |
| --- | --- |
| 1 | Native seed storage for revegetation |
| 2 | Basic methods for drying, extraction and cleaning native plant seed |
| 3 | Improving on basic native seed storage |
| 4 | Keeping records on native seed |
| 5 | Seed collection from woody plants for local revegetation |
| 6 | Native seed collection methods |
| 7 | Seed production areas for woody native plant species |
| 8 | Basic germination and viability tests for native plant seed |
| 9 | Using native grass seed in revegetation |
| 10 | Seed collection ranges for revegetation |

Table C.7	Florabank guidelines for handling of native seed (http://www.florabank.org.au/).

Note that stored seed will lose viability over time.  Florabank suggest that, with good storage practices, a storage period of five years is achievable without significant loss of viability but this will vary between species.  If seed is to be purchased in advance for a future project then sound storage practices are essential and evidence that viability has been maintained should be provided.

It is desirable to develop a seed list for a project in consultation with the chosen supplier.  This will avoid problems when requesting amounts of seed or seed of particular species that are very difficult to collect and will therefore be very costly.

The names of reputable seed suppliers can be obtained from regional offices of the Departments of Conservation and Land Management, and Agriculture.  On no account should imported seed be used, regardless of whether it is of a native species or not.

Seed Pre-treatment

Many seeds require some form of pre-treatment to promote germination.  Failure to provide this pre-treatment in advance of sowing will result in failure to germinate although, in most cases, the seed may remain in the seed bank and could potentially germinate when dormancy has been broken.  Those seeds remaining in the seed bank, however, may be subject to insect predation or other degrading mechanisms.

Table C.8 shows a summary of some well-known seed pre-treatments.  Of the pre-treatment shown, boiled water/heat and smoke-related chemicals are readily applied to commercial quantities of seed and seed treated in this manner can usually be obtained upon request.

Other pre-treatments are more specialised and are more likely to be undertaken on a case-by-case basis.

Smoke treatment, in particular, has been shown to reduce seed dormancy in a wide range of species and is a very valuable method of establishing a much wider range of species than was previously possible.  While research on the effects of smoke on seed dormancy tends to be restricted to species from the Swan Coastal Plain and jarrah forest, smoke treatment of seed has not been shown to have a negative impact on germination in any species.  Furthermore, it may reduce seed predation in the field.

Of the above, boiled water and smoke treatments are recommended as standard treatments for the relevant species.  The other treatments should be considered on a case-by-case basis.

In the past, some practitioners have applied boiled water or scarification treatments to only a portion of the seed to be broadcast and have left the remainder untreated.  In theory, this provides a back-up seed bank in case, for some reason, the treated seed fails.  As seed mixes are designed to achieve a certain level of germination and not to simply create a seed bank, this approach is not recommended as standard practice.  It may, however, warrant consideration in some areas where the rainfall is unpredictable.  Local advice should be obtained about the value of this practice.

| Pre-treatment | Comments |
| --- | --- |
| Aging and after-ripening | Some seeds require further aging after reaching full development to obtain full germinability. Long term storage improves germinability in some native grass seed and enzymes can be used to simulate the aging process in some seeds. Storage, however, reduces germinability in many other species. |
| Boiled water and heat | Immersion in boiled water promotes germination in most Acacia and Oxylobium seeds but can damage some other hard seeds with thinner coats (Kennedia, Senna). These seeds can still be treated but water must be cooler and the duration of exposure reduced. Seed merchants should be able to advise on the most suitable treatment for each species. |
| Leaching or washing | Germinability promoted by the removal of water-soluble inhibitory chemicals in Eremophila. |
| Aerosol smoke / water-based smoke chemicals | Smoke and water–based smoke chemicals has been shown to alleviate dormancy in a wide range of seeds. Commonly specified as a pre-treatment for Main Roads’ revegetation work. |
| Scarification | Removal of part of the testa (seed coat) or fruit can alleviate physical dormancy but often needs to be at a particular location on the seed to be effective (‘precision’ scarification’). Achieves a similar result to immersion in boiled water. Some Main Roads’ contracts have required only a portion of the seed (e.g. 60%) of particular species be scarified. |
| Priming | Exposure of the seed to non-toxic osmotic concentrations prior to broadcasting can accelerate germination in the field. Has been used with mixed results for improving establishment in eucalypts. |
| Removal of ancillary structures | Removal of the palea and lemma on native grass seed promotes germinability and also allows the bare seed (naked caryopsis) to be broadcast through agricultural seeders. |

Table C.8	Summary of some well known seed pre-treatments.

SEEDING RATES AND PLANTING DENSITIES

Determining Seed Quantities

Having determined the species required, it is necessary to calculate the amounts of seed required.  As seed can be very expensive and some species may be difficult to collect, a methodical approach is required to determine the correct amount required.  These amounts can be calculated using the following formula:

Sowing rate (g/ha) = A / (B x C), where:

A = No. of plants desired/ha

B = Expected establishment of plants from seed (%)

C = Expected no. of germinable seeds/g.

Variable A is based on the expected outcome of the revegetation program and is likely to reflect values occurring in mature vegetation.  Bear in mind, however, that some species used in the seed mix will be early successional and will not appear in mature vegetation (see Section C.8).

Of the seeds sown, only a portion will survive to produce a mature plant.  This surviving portion is Variable B.  It can be difficult to estimate but, as a general rule of thumb, 0.5% establishment for small-seeded species and 5% establishment for large-seeded species can be used in the absence of other information.  As experience is gained with revegetation work, these values can be adjusted.

Variable C equates with seed viability and should include allowance for non-seed material e.g. the ‘frass’ associated with eucalypt seed.  Seed suppliers should be able to provide a good estimate of Variable C.

As a general rule, seed quantities do not usually exceed 5 kg/ha but it will depend on the particular program developed.

Likely recruitment of seedlings from the seed bank in topsoil, if present, should also be considered.  Allowance for early successional species, which will give way to other species, should also be made. These early successional species include acacias and other species common after disturbance.  Seeding should accommodate changes to the composition of the revegetation that will occur over time (see comments on succession in Section C.8).

A spreadsheet for calculating seed quantities is given in Appendix F.

Planting densities

Planting densities may be specified within the contract.  The densities should approximate the expected density when the plants are mature, with some allowance for losses.

SEEDING METHODS

Seed application

Having determined the species and quantities of seed, and prepared a suitable seed bed, the seed needs to be broadcast.  The method by which this is done can be by hand (for small areas only) or by a wide range of agricultural equipment, including niche seeders.  Mechanical seeding equipment is readily available in the agricultural regions but elsewhere seeding is predominantly carried out by hand.  Where mechanical seeders are used, they usually have seed boxes that can be adjusted to accommodate small-seeded native species.  Depending on the seeding mechanism, several passes with different sized seed may be necessary.

Vermiculite is commonly used as the seed carrier but sand, sawdust and fertiliser have also been used.  Seeding should be conducted when wind speeds are less than 10 km/h to avoid losses.

Seed burial

Seed burial appears to be a critical factor in revegetation success.  Agricultural equipment such as harrows can be used to ensure there is good seed-to-soil contact for larger seed but, in the absence of this equipment, seed burial can occur through the action of wind and water.  Use of harrows may bury some fine seed too deeply and adequate burial has been achieved through dragging chaff bags over them.  Research suggests that burial to less than 1 mm may give the best results in species with small seeds and that, as a general rule of thumb, all seed should be buried to a depth no greater than the diameter of the seed.  Seeds buried more deeply are unlikely to result in seedlings. There is evidence that this is a common reason for failure of direct seeding projects.

PLANTING METHODS

Planting

Planting can be undertaken by hand or by using a mechanical planter (for larger projects in the higher rainfall areas).

Survival will be enhanced by the minimisation of transplant stress and the creation of favourable conditions wherever possible.  Experience suggests that, where practicable, holes should be dug and well watered a week prior to planting and watered again at planting.  This will provide a reservoir of moisture for the plant as it adjusts to field conditions although it not practicable for mechanical planting.  Plantings on slopes should encourage some runoff into the shallow basin around the seedling.

For hand planting projects in some areas, it may not be practical to establish holes and water in advance.  Good survival may still be achievable with a reduced watering regime.  Local advice should be sought.

When planting the seedling, any tangled roots should be loosened and good soil to plant contact made.  Figure C.2 shows some of the common errors made when planting seedlings.

Figure C.2	Common planting errors (from Norman et al, 1997).

A success rate of 60-80% can normally be expected.  Provision needs to be made for the replacement of failures.

Protection and maintenance of plants

Polyethylene tree guards can be used for protection against high winds (especially passing trucks in roadside plantings) and rabbits.  The humid atmosphere within the guards can encourage early rapid growth but should be removed before summer.  Fencing may be necessary in some circumstances to prevent grazing by larger animals.

A weed-free zone should be maintained around seedlings to reduce competition from other plants.  Tree guards can interfere with weed control – if this is the case, the guards should be removed.

SUCCESSION IN REVEGETATED AREAS

Succession is defined as the sequential development of changes within an ecosystem as it progresses towards a self-perpetuating climax community.  There is a wide range of models and theories on succession but they generally follow the process shown in Figure C.3.

Figure C.3	Generalised view of successional processes.

It is generally recognised that that roadside revegetation work will pass through a series of successional, or ‘seral’, stages to reach a stable, or climax, form.  Often, this will be in the form of an early dominance of certain species, e.g. acacias, which, in due course, give way to other species.  They establish a seed bank during their period of dominance, which can be utilised if a major disturbance, such as fire, occurs.

Some caution needs to be exercised over the relative proportion of early successional species such as acacias as Main Roads’ experience has shown if they are too dominant they may suppress other desirable species.  Thus, what initially appears to be a satisfactory revegetation outcome may prove unsatisfactory once the early successional species decline.

Despite the fact that some species can dominate in the early stages of revegetation, accepted practice for revegetation projects within Main Roads is accelerated climax community development.   This is where all species desired for the mature vegetation community are seeded or planted ‘up front’.  Recent research into breaking dormancy in many native species should mean earlier and more reliable progress towards climax communities in revegetation.  However, it is important to make allowances for successional processes in monitoring programs where, initially at least, there may be short-term dominance of a small number of species.  Some important differences between early and late successional species are outlined in Table C.9.

Important aspects of succession in revegetated areas for project managers to note are:

- Early successional species may initially dominate some revegetated areas,

- Late successional species should become more dominant over time, and

- Disturbances such as fire may create a feedback loop where succession is retarded.

| Characteristic | Early Successional Plants | Late Successional Plants |
| --- | --- | --- |
| Seed numbers | Many | Few |
| Seed size | Small | Large |
| Longevity | Short | Long |
| Growth rate | Rapid | Slow |
| Root-to-shoot ratio | Low | High |
| Size | Small | Large |

Table C.9	Comparative features of early and late successional plants.

In some situations, sowing a cover crop as an initial step can stabilise soils and provide organic material for use by later successional species.  For example, cereal rye (at rates of 50-150 kg/ha) has been used as a short-lived cover crop to provide short term erosion protection in the south-west of the State and sorghum has been used for a similar purpose in the Kimberley’s.  This is most often done when the potential for significant erosion exists.

MONITORING

Overview

In the past, Main Roads has employed a variety of methods to assess the success of revegetation work.  The methods used are summarised in Table C.10 and are generally dictated by the size and location of the project, when it was undertaken and whether an external organisation, such as the Environmental Protection Authority, has a role in determining what the target outcomes shall be.

Larger projects tend to involve more sophisticated monitoring methods, both to satisfy community demand and to allow for intervention and remedial work should it be required.  Smaller projects, where the cost of a failure may not be as great, may have very little monitoring conducted.  Overall, however, monitoring methods are becoming more sophisticated and detailed with the passage of time as more assurance is sought about revegetation outcomes than has been in the past.

Criteria

The simplest form of monitoring comprises the use of input criteria.  Essentially, this involves ensuring that the revegetation works have been implemented as planned.  This is no more than basic project management and may be the only monitoring required for some revegetation work.

Many revegetation projects, however, will warrant monitoring involving the use of output criteria.  These will be some predetermined parameters used to assess whether the works have achieved what was intended.  This criteria may be quantitative or semi quantitative  (ranking on some predetermined scale).  Examples of suggested indicators are shown in Table C.11 and Appendix G.  Note that it is entirely appropriate to devise and implement project-specific indicators linked to the objective of the project.  Any one indicator may also have a number of ‘milestones’ to assess at an early stage whether the desired indicator is likely to be achieved (see Appendix G).

Historically, Main Roads has used attribute-based monitoring where some attribute of the site, such as vegetation cover, is assessed.  All of the indicators shown in Table C.11 and Appendix G are attribute-based.  It is also possible to used indicators of function that determine whether the desired ecological processes are being achieved.

Ecosystem Function Analysis (EFA), as developed by CSIRO, is an example of function-based monitoring.  Function-based indicators, with repeated measurements, give a trajectory towards a sustainable ecosystem while attribute-based indicators are defined ‘end-points’.  The two types of indicators can also be used in conjunction with one another.

| Monitoring / Assessment Methods | Comments |
| --- | --- |
| A. Input criteria | Involves checking that work has been done, e.g. ripping and seeding actually conducted, without any follow up monitoring. |
| B. Input criteria with informal assessment | Method A method plus monitoring involving an informal visual assessment. May involve photographic records. |
| C. Input criteria with semi-quantitative outcome criteria | Method A plus some outcomes, e.g. seedling survival, plant cover, weed cover etc., may be ranked on a predetermined scale. Usually includes photographic records. Minimum performance levels may be stated in contractual documentation. |
| D. Input criteria with quantitative outcome criteria. | Method A plus quantitative monitoring at various intervals of predetermined key success criteria. Criteria may include plant cover, species richness, seedling survival, weed cover and/or surface stability. Usually includes photographic records. Minimum performance levels usually stated in contractual documentation. Success criteria may be set by external bodies e.g. Environmental Protection Authority. |

Table C.10	Summary of various methods used within Main Roads for monitoring and assessing revegetation success.

Design of monitoring programs

Many revegetation projects will have formal monitoring requirements.  The results of monitoring will have significant implications for contract managers and contractors alike. This being the case, it is critical all monitoring programs should be designed in a manner that is consistent with good scientific and statistical practices so that the results of the monitoring program will be sound and reproducible.  The following are some of the key issues that must be considered:

Sample size – the sample size, in terms of both the size and number of sample plots, must be adequate.  The requirements will vary from site to site but, essentially, the sample plot size should be appropriate to size and distribution of the units being measured.  When additional sampling produces little or no additional information, then the number of sample plots is adequate.

Stratified sampling – it is critical to recognise distinctly different variables at the site and to design the monitoring program accordingly.  For example, there may be differences in topography (slopes vs. flat areas), soil types, and revegetation treatments (e.g. seed mixes), each of which potentially produces a different outcome.  Sampling should consider each of these individual areas with sample sizes in proportion to the size of the overall area.  If this is correctly done, it will help identify the areas in which there are problems and distinguish them from other areas that are progressing satisfactorily.

Random sampling – all plots should be placed at random.  Random number tables are usually used for this purpose.  This will remove any bias the sampler may have in selecting the location of sample plots.

All formal monitoring reports should outline and justify the methodology used.

| Criterion | Indicator | Values | Target |
| --- | --- | --- | --- |
| Input | Site preparation completed as per Revegetation Plan | Yes/No | Yes |
|  | Seed mix applied as per Revegetation Plan | Yes/No | Yes |
|  | Seedlings planted as per Revegetation Plan | Yes/No | Yes |
| Output (Informal) | Visual inspection | Progress acceptable/ not acceptable | Acceptable |
|  | Photographic records | Progress acceptable/ not acceptable | Acceptable |
| Output (Semi-quantitative) | Mean foliage cover excluding weeds | 0-5 | >4 |
|  | Mean foliage cover – weeds | 0-5 | <1 |
|  | Plant health | 0-5 | >4 |
| Output (Quantitative) | Mean foliage cover excluding weeds | % | Site specific |
|  | Mean foliage cover – weeds | % | Site specific |
|  | Mean no. of individual plants/ m2 | n | Site specific |
|  | Mean no. of individual plants of key species/ m2 | n | Site specific |
|  | Species richness | n | Site specific |
|  | No. of bare areas > 100 m2 | n | Site specific |
|  | No. of erosion gullies > 200 mm in depth | n | Site specific |
|  | Seedling survival | % | 80 (or as otherwise agreed) |

Table C.11	Suggested revegetation project monitoring indicators.

REFERENCES

Department of Conservation and Land Management (2003). Phytophthora cinnamomi and disease caused by it - Vol. 2: Interpreter's Guidelines for Detection, Diagnosis and Mapping.

Dieback Working Group (2000). Managing Phytophthora Dieback - Guidelines for Local Government.

Fosberry, G. and Howell, M.R. (1985). Gypsum improves soil stability. Department of Agriculture Western Australia, Farmnote 32/85.

Holt, C. (1998). Direct seeding of native plants for revegetation. Dept of Agriculture Western Australia, Farmnote 40/98.

Mortlock, W., Grime, P., Bradby, K. and Ovens, N. (1993). Field Planting of Trees and Shrubs - A Guide for Landowners and Developers in the Shires of Serpentine-Jarrahdale and Murray. Community Catchment Centre, Pinjarra.

Mortlock, W., Vercoe, T. and McDonald, M. (1999). Guideline 5: Seed Collection from Woody Plants for Local Revegetation. Florabank, ACT.

Mullan, G.D. and White, P.J. (2002a). Revegetation site-preparation in the WA Wheatbelt - Ripping and Mound ploughing. Bushcare and the Department of Conservation and Land Management, Western Australia.

Mullan, G.D. and White, P.J. (2002b). Seedling quality – making informed choices. Bushcare and the Department of Conservation and Land Management.

Norman, D.K., Wampler, P.J., Throop, A.H., Schnitzer, E.F. and Roloff, J.M. (1997). Best Management Practices for Reclaiming Surface Mines in Washington and Oregon. Washington Division of Geology and Earth Resources Open File Report 96-2, December 1997.

Schirmer, J. and Field, J. (2000). The Cost of Revegetation - Final Report. ANU Forestry and Greening Australia.

Watson, R. (1991). How local is local? In “Proceedings of Growback '91: a forum for the exchange of information and ideas relating to managing remnant vegetation and re-establishing native vegetation in the Australian landscape”. Growback Publications, Fitzroy, Victoria.

APPENDIX D 1

Revegetation Projects – Benchmark Costs

| No. | Revegetation Project Type | Total Cost/ha ($) |
| --- | --- | --- |
|  |  | 1 ha | 10 ha | 50 ha |
| 1 | Assisted natural regeneration in a warm moist temperate region | 2300 | 900 | 600 |
| 2 | Direct seeding on ex-pasture site in warm moist temperate region | 3200 | 1500 | 1200 |
| 3 | Speedlings with same fencing, stocking etc. as tubestock project 4 | 2400 | 1500 | 1300 |
| 4 | Tubestock in semi-arid region | 2600 | 1900 | 1700 |
| 5 | Speedlings on ex-pasture in warm moist temperate region with contract planting and fertiliser | 4200 | 2500 | 2200 |

Table D1  Indicative costs of revegetation projects.

Note:

- Based on a range of Australian projects reviewed by Schirmer and Field  (2000) from costs incurred in 1999.  Dollar values have been rounded to aid comparisons.

- The costs include ripping and seedbed establishment but do not include earthmoving costs, such as topsoil stripping and replacement, and significant site drainage works.

- These costs are based mainly on revegetation carried out on farms.  Main Roads’ personnel advise that the costs associated with roadside revegetation are generally higher.  If using this data as a basis for cost estimation, the addition of a 20% contingency is recommended.

Appendix D2

Revegetation - Sample Bill of Quantities

Note: Above example was prepared for a South West road location.  The cost items will vary by region and road location.

APPENDIX E

Typical Documents- Suggested Tables of Contents

Appendix E1

Revegetation Proposal- Suggested Table of Contents

- BACKGROUND (rationale for project, objective)

- DESCRIPTION OF AREA (location by SLK, summary of preliminary site assessment)

- STAKEHOLDERS

- REQUIREMENT FOR REVEGETATION (preliminary review of key factors, likely methods, desirable species)

- LIKELY TIMING AND RESOURCING

- PRELIMINARY BUDGET

Appendix E2

Revegetation Plan – Suggested Table of Contents

EXECUTIVE SUMMARY (inc. recommended actions and budget)

- PROJECT OUTLINE

- RELEVANT ISSUES

- KEY SITE BIOPHYSICAL FACTORS (soil, vegetation etc)

- REVEGETATION PLAN (objectives, methods, contract arrangements etc)

- ESTIMATE OF PROBABLE COSTS

- SUCCESS CRITERIA

- IMPLEMENTATION ISSUES

- VEGETATION ESTABLISHMENT

- MONITORING

- RECOMMENDED MANAGEMENT ACTIONS

ATTACHMENTS

Refer to the Main Roads Environment Branch intranet web site for a template of a plan brief.

Refer to the Main Roads Environment Branch intranet site for a template of a design brief.

Appendix E3

Weed Management Plan - Suggested Table of Contents

Components of weed management for a project are:

- Weed Assessment (description and distribution of weeds on site)

- Control Program (the control work to be undertaken)

- Monitoring (effectiveness of control and need for follow up).

A Weed Management Plan should include the following:

- Project site plan with all road verges broken into conservation value (1 to 5 degraded to intact native vegetation).

- Complete description of weeds on site and summary of distribution.

- Any declared weeds and control recommendations.

- Areas for priority treatment.

- Topsoil management recommendations for the project that take into account, declared weeds, pest weeds, normal weeds and conserved vegetation.

- Control program with total areas (ha), chemical types, application methods, safety data sheets, application timing, and application rates, complete with an estimate of cost to deliver the required control program.  Program timeframes and number of applications required.

- Monitoring program.

Appendix E4

Revegetation Handover Report - Suggested Table of Contents

- PROJECT OUTLINE

  - Background

  - Description of area

  - Stakeholders

  - Objectives

  - Key Factors

  - Timing of works

- SUMMARY OF WORKS

  - Site preparation

  - Revegetation method(s)

  - Species and quantities used

- MONITORING

  - Details to date

  - Future monitoring

- RECOMMENDED ONGOING MAINTENANCE ACTIONS

APPENDIX F

Revegetation Programs - Seed Quantity Calculation Worksheet

| Species | Target coverage (stems ha-1)1 | Seed Requirement for Revegetation |
| --- | --- | --- |
|  |  | Expected recruitment from topsoil (stems ha-1)2 | Recruitment required from seed (stems ha-1) | Expected establishment from seed (%)3 | Expected no. of germinants (seeds g-1)4 | Sowing rate (g ha-1) | Area to be Revegetated (ha) | Total Seed Requirement (g) |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |
|  |  |  | (2) – (3) |  |  | (4) / ((5) x (6)) |  | (7) x (8) |
| Example 1 (Acacia acuminata) | 1,000 | 200 | 800 | 5 | 65 | 246.2 | 6.7 | 1649.2 |
| Example 2 (Anigozanthos manglesii) | 500 | 0 | 500 | 1 | 480 | 104.2 | 6.7 | 697.9 |

APPENDIX G

Examples of Monitoring Programs for Revegetation Works

Example 1

Objective: Roadside stability and maintenance minimisation.

Targets: Based on adjacent undisturbed vegetation.

Revegetation method: Regeneration from topsoil.

Monitoring method: Visual assessment.

| Criterion | Target | After three months | After one year | After three years |
| --- | --- | --- | --- | --- |
| Mean vegetation foliage cover (%) excluding weeds | >75 | NA | 50 | 60 |
| Mean weed foliage cover (%) | <10 | <10 | <10 | <10 |
| Species richness (n) | 5 | 3 | 4 | 5 |
| No. of bare areas > 100m2 | 0 | 0 | 0 | 0 |
| No. of erosion gullies greater than 200 mm in depth | 0 | 0 | 0 | 0 |

Example 2

Objective: Conservation and biodiversity.

Targets: Based on vegetation in adjoining conservation reserve. Key species is dominant tree species in reserve.

Revegetation method: Direct seeding.

Monitoring method: Quantitative by quadrats.

| Criterion | Target | After three months | After one year | After three years |
| --- | --- | --- | --- | --- |
| Mean vegetation foliage cover (%) excluding weeds | >75 | NA | 50 | 60 |
| Mean weed foliage cover (%) | <10 | <10 | <10 | <10 |
| Mean no. of individual plants/m2 (n) | 4 | 6 | 4 | 4 |
| Mean no. of individual plants of key species/m2 (n) | 0.25 | 0.25 | 0.25 | 0.25 |
| Species richness (n) excluding weeds | 40 | 20 | 30 | 35 |
| No. of weed species (n) | <3 | <5 | <5 | <3 |
| No. of bare areas > 100m2 | 0 | 0 | 0 | 0 |
| No. of erosion gullies greater than 200 mm in depth | 0 | 0 | 0 | 0 |

Example 3

Objective: Amenity and aesthetics.

Targets: Based on local community expectations.

Revegetation method: Planting.

Monitoring method: Quantitative and semi-quantitative by quadrat.

| Criterion | Target | After three months | After one year | After three years |
| --- | --- | --- | --- | --- |
| Mean vegetation foliage cover (%) excluding weeds | >50 | NA | 30 | 50 |
| Mean weed foliage cover (%) | <10 | <10 | <10 | <10 |
| Plant survival (%) | 85 | 90 | 85 | 85 |
| Plant health (1-4) | 85% at 3 or better | 90% at 3 or better | 90% at 3 or better | 85% at 3 or better |
| Species richness (n) | 8 | 8 | 8 | 8 |
| No. of bare areas > 100m2 | 0 | 0 | 0 | 0 |
| No. of erosion gullies greater than 200 mm in depth | 0 | 0 | 0 | 0 |

# Footnotes

Information drawn from consultation within Main Roads and Holt (1998).

From Mortlock et al (1993).

‘Speedlings’ are small seedlings grown in cells in a tray as opposed to seedlings in individual pots. If available, they are usually cheaper per unit than seedlings.

‘Tubestock’ refers to seedlings grown in individual pots.

1 Estimate based on naturally-occurring native vegetation to be provided in Revegetation Plan.

2 Estimate to be provided in Revegetation Plan.

3 As for 2.  If not known, the following default values can be used: large-seeded species e.g. acacias (5%), small-seeded species, e.g. eucalypts (0.5%).

4 From seed supplier.

Based on a semi-quantitative score where 1 = poor and 4 = healthy.

# Text boxes

Environmental Guideline

REVEGETATION PLANNING AND TECHNIQUES