SPECIFICATION 304

Landscaping & Revegetation

Copyright MAIN ROADS Western Australia

| REVISION REGISTER |  |  |  |
| --- | --- | --- | --- |
| Clause Number | Description of Revision | Authorised By | Issued Date |
| Whole Document | Major revision – refer to D18#755580 | ME | 21/10/2019 |
| 304.02, 304.27, 304.30, 304.34, 304.35, 304.36, 304.38, 304.39, 304.42 & 304.45. | Amended | LA | 03 Aug 07 |
| 304.06.14 | Deleted (refer Clause 304.45) |  |  |
| Guidance Note 4 | Tables updated |  |  |
| 304.02, 304.08, 304.27, 304.29, 304.30, 304.34, 304.35, 304.36, 304.38 & 304.39. | Various amendments including the addition of some new sub-clauses and the transfer of topsoil respread, soil surface preparation and soil improvement requirements to Specification 302 Earthworks | LA | 07 May 07 |
| Whole document | Complete revision of Issue 3.0 to new format | MCP | 01 Aug 06 |

CONTENTS

Clause	Page No

GENERAL	4

304.01	Scope	4

304.02	References	4

304.03	Definitions	5

304.04	Other Requirements	5

PRODUCTS AND MATERIALS	6

304.05	General Products and Materials	6

304.06	Hard Landscaping	7

304.07	Mulch, Weed and Erosion Control Matting	7

304.08	Hydro-Mulching and Hydro-Seeding  Materials	8

304.09	Plant Materials	9

304.10	Irrigation Materials	12

CONSTRUCTION	12

304.11	Sequence of Operations	12

304.12	Weed Control	13

304.13	Clearing of Site	13

304.14	Transplant and Salvage of Existing Vegetation	13

304.15	Irrigation System	14

304.16	Trickle Irrigation	17

304.17	Hard Landscaping	17

304.18	Preparation of Batters and Ground Surfaces	17

304.19	Topsoil Respread	18

304.20	Soil Improvements	19

304.21	Weed Control Matting	19

304.22	Erosion Control	19

304.23	Mulch Respread	20

304.24	Hydro-Mulching and Hydro-Seeding	21

304.25	Direct Seeding	23

304.26	Planting	26

304.27	Grassing	32

304.28	Watering System	35

304.29	Revegetation Signs	36

Establishment Period	36

304.30	Completion of Works	36

304.31	Vegetation Establishment	37

304.32	Monitoring Program	38

304.33–304.80	NOT USED	39

AS BUILT AND HANDOVER requirements	39

304.81	Handover Requirements	39

304.82	Final Completion	39

304.83– 304.90	NOT USED	40

CONTRACT SPECIFIC REQUIREMENTS	40

304.91– 304.99	NOT USED	40

ANNEXURE 304A – SPECIFIC REQUIREMENTS	41

ANNEXURE 304B – MATERIAL REQUIREMENTS	42

ANNEXURE 304C – COMPLETION CRITERIA	46

SPECIFICATION 304

LANDSCAPING & REVEGETATION

| GENERAL |  |
| --- | --- |
| 304.01 SCOPE |  |
| 1. The work under this specification consists of the supply of all products, materials and equipment, all preparation and construction and all revegetation and landscaping operations required to complete the Works as shown in the Drawings or specified in the Contract. |  |
| 304.02 REFERENCES |  |
| 1. Australian Standards, MAIN ROADS Western Australia Standards and MAIN ROADS Western Australia Test Methods are referred to in abbreviated form (e.g. AS 1234, MRS 67-08-43 or WA 123). For convenience, the full titles are given below: |  |
| Australian Standards |  |
| AS 2032 Installation of UPVC Pipe Systems |  |
| AS 2303 Tree Stock for Landscape Use |  |
| AS 3743 Potting Mixes |  |
| AS 4419 Soils for Landscaping and Garden Use |  |
| AS 4454 Composts, soil conditioners and mulches |  |
| Australian/New Zealand Standards |  |
| AS/NZS 3500 Part 1.2 Water Supply – Acceptable Solutions |  |
| Other Publications |  |
| Health (Pesticides) Regulations, 1956 NATSPEC Guide: Specifying Trees, ISBN 0 9586187 7 1. |  |
| MAIN ROADS Test methods |  |
| WA 0.1 Random Sample Site Location |  |
| MAIN ROADS Standard Drawings |  |
| Segmental Paving Details Drawing No. 200331-154, -155 & -156 |  |
| Guide Sign - Roadside Revegetation. Standard Drawing No. MR-GM-14 |  |
| Main Roads Specifications |  |
| Specification 202 TRAFFIC |  |
| Specification 204 ENVIRONMENTAL MANAGEMENT |  |
| Specification 301 VEGETATION CLEARING AND DEMOLITION |  |
| Specification 302 EARTHWORKS |  |
| Specification 406 ROCK PROTECTION |  |
| Specification 505 SEGMENTAL PAVING |  |
| Specification 601 SIGNS |  |
| 304.03 DEFINITIONS |  |
| 1. The Installation Period shall mean the period starting from the commencement through to the end of the revegetation and landscaping works as specified in the Contract. | Installation Period |
| 2. The Establishment Period shall mean the period starting from the completion of the revegetation and landscaping works and extending for a duration as nominated in Annexure 304A of this Specification. | Establishment Period |
| 3. "Establishment" shall mean the continuing care and maintenance of the revegetation and landscaping works by accepted horticultural practises, as well as rectifying any defects that become apparent in the works under normal use. For the duration of the Establishment Period the Contractor is fully responsible for the continuing good appearance of the works. | Establishment |
| 4. The Contractor is required to carry out all activities necessary to establish and promote the growth of all plant materials and maintain all works in good order and functional condition during the Installation Period. |  |
| 304.04 other requirements |  |
| 304.04.01 personnel |  |
| 1. The Contractor must ensure that personnel under the sole responsibility and supervision of the Contractor must be competent, experienced, and skilled in all aspects of the required landscape installation and establishment practices. | Skilled Personnel |
| 304.04.02 traffic management |  |
| 1. The Contractor must ensure that all traffic management and control measures necessary to undertake the works are implemented in accordance with Specification 202 TRAFFIC. | Traffic Management |
| PRODUCTS AND MATERIALS |  |
| 304.05 GENERAL PRODUCTS AND MATERIALS |  |
| 1. The manufacturer’s published product details and instructions for use must be provided to the Superintendent upon request. | General |
| 2. Water used to establish and maintain vegetation must be potable water where available or obtained from a source containing no substances detrimental to seed germination or vegetation growth. | Water |
| 3. Only pesticides registered for the treatment of pests and weeds in Western Australia can be used for the Works. The supply, storage, handling and use of any product must comply with regulations, restrictions and government policy, relating to pesticides and in accordance with manufacturer’s published specification. | Pesticides |
| 4. Fertiliser(s) specified in the Contract must be delivered on site in unopened bags or containers bearing the manufacturer’s description, analysis of constituents and quantity. Fertiliser(s) must be stored in waterproof sealed bags and sheltered away from water and direct sunlight. | Fertiliser |
| 5. Unless otherwise specified in the Contract, the fertiliser(s) must be manufactured for the purpose used in the Contract and must be stored, handled and applied in accordance with the manufacturer’s published specification. |  |
| 6. Timed-release water (water storage crystals/gel) if specified must be manufactured for the purpose and delivered on site in sealed containers. | Timed- Release Water |
| 7. Soil wetting agents must be active in the soil for a minimum of six months, must be non-ionic, non-toxic, pH neutral range of 6-8 and must be applied in accordance with the manufacturer’s published specifications. | Soil Additives |
| 8. Soil bio-amendments and inoculates must be free of any substances detrimental to plant life, and only be applied in accordance with the manufacturer’s published specifications. |  |
| 9. Unless otherwise specified in the Contract, soil conditioners must comply with AS 4454 and be applied in accordance with the manufacturer’s published specifications. The Contractor must supply to the Superintendent certified test reports that the soil conditioners to be used in the Works comply with AS 4454. | Soil Conditioners |
| 10. The phosphate content of soil conditioners must not exceed three percent and the pH must be in the neutral range of 6-8. |  |
| 11. The Contractor must use all topsoil stockpiled on site that has been nominated for re-use as topsoil in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION. | Insitu Topsoil |
| 12. Imported material for use as topsoil must comply with AS 4419. The Contractor must supply to the Superintendent an analysis of its content undertaken by a laboratory to confirm that the imported topsoils to be used in the Works are Dieback Free and comply with AS 4419. | Imported Topsoil |
| 13. Selected fill material to be used in the Works must be clean embankment quality material in accordance with Specification 302 EARTHWORKS and must be free of any matter with a particle size greater than 50 mm, weeds and materials toxic to plant growth. Contaminated soil must not be used as fill within the Works. | Selected Fill |
| 14. Suitable spoil material to be used in the Works must be clean material in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION and must be free of any weeds and materials toxic to plant growth. Contaminated soil must not be used as fill within the Works. | Suitable Spoil |
| 15. The Contractor must nominate, prepare and manage all stockpiles of topsoil and/or mulch materials in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION. | Stockpiles of Topsoil or Mulch |
| 304.06 HARD LANDSCAPING |  |
| 1. Unless otherwise specified in the Drawings, all materials used for fixed items such as, but not limited to, rock pitching, segmental paving, concrete surfacing, bollards, fencing, screen walls and other hard landscaping elements must be in accordance with the relevant Main Roads specifications. |  |
| 2. Any large feature rocks or boulders retained for use in the landscaping must be placed as shown in the Drawings ensuring they are not scarred or broken by equipment during placement. | Placement of Large Rocks and Boulders |
| 3. Unless specified otherwise in the Drawings, each rock or boulder placed for the purpose of restricting access must be buried 10-30% below finished soil levels. |  |
| 304.07 MULCH, WEED AND EROSION CONTROL MATTING |  |
| 1. Mulch refers to any chipped site vegetation, composted organic materials or inorganic materials such as crushed rock, coarse aggregate, river pebbles, or pea gravel, spread as a soil surface protection measure and or decorative surface treatment. | Definition |
| 2. Mulch materials must be clean of any weed, grass stolons, seeds and other extraneous materials and free from all matter and substances toxic to plant growth. | General |
| 3. Inorganic mulch must be clean and washed free of fines, screened and composed of particle sizes in even proportions as shown in the Drawings. | Inorganic Mulch |
| 4. Stockpiled chipped site vegetation or uncontaminated chipped vegetative material naturally occurring within the local area must be approved as suitable by the Superintendent, prior to use as mulch. | Site Vegetation Mulch |
| 5. All imported un-composted chipped vegetation material must be aged for at least three months, be free of fine or fibrous particles, live grass stolons, be Dieback and Weed Free and approved as suitable for use as mulch by the Superintendent. | Imported Vegetation Mulch |
| 6. All imported composted mulch materials must comply with AS 4454. The Contractor must supply to the Superintendent an analysis of its content undertaken by a certified laboratory to confirm that the imported mulch to be used in the Works are Dieback and Weed Free. | Imported Composted Mulch |
| 7. Unless specified otherwise in the Drawings or in Annexure 304B, the mulch material must be an average size of between 15 mm to 50 mm, with no individual pieces greater than 100 mm. | Mulch Size |
| 8. Straw for use in hydro-mulch operations, weed control or erosion control must be derived from cereal crops and certified free of viable seed and cured to less than 20% moisture content by weight. | Straw |
| 9. Mulch control netting must be a lightweight woven biodegradable mesh product manufactured for the purpose of holding organic mulch surfaces in place. | Mulch Control Netting |
| 10. Weed control matting must be manufactured for weed suppression and made from stable long-life materials such as polypropylene fabric, heavy weight jute or coir. | Weed Control Matting |
| 11. Unless detailed otherwise in the Drawings, all erosion control matting, blanket, or netting must be manufactured from organic fibre products and be biodegradable, permeable to air and water and remain intact when wet and in contact with the soil. | Erosion Control Matting/ Blankets |
| 12. Erosion control cells and products designed to be placed on slopes to hold topsoil and mulch must be manufactured from non-degradable, UV stabilised materials. | Erosion Control Cells |
| 304.08 HYDRO-MULCHING AND HYDRO-SEEDING MATERIALS |  |
| 1. Cellulose fibre must be biodegradable, free of any contaminated materials and suitable for use in hydro-seeding and hydro-mulching to form a slope stabilisation mat. | Cellulose Fibre |
| 2. Binders, tacifiers, or emulsions used must be manufactured for the purpose of hydro-seeding and hydro-mulching used in the Contract and must be miscible in water, free from components toxic to seed germination, plant growth or aquatic life and applied according the manufacturer’s published instructions for use. | Binder |
| 3. All water used in hydro-seeding and hydro-mulching must be free from materials likely to be toxic to plant growth. | Water |
| 4. Coloured dye used to aid visual application of hydro-seeding and hydro-mulching must be a non-toxic water-soluble biodegradable dye. | Dye |
| 5. Dispersing agents must be free from components toxic to seed germination, plant growth or aquatic life and mixed according the manufacturer’s published instructions for use. | Dispersing Agent |
| 6. Equipment for the mixing and application of hydro-mulching and hydro-seeding must have the operating capacity to allow for the mixing of materials in continuous agitation to produce a homogeneous mixture and a discharge system to apply the mixture at a continuous and uniform rate. The Contractor must demonstrate the capacity of the equipment to the Superintendent upon request. | Equipment |
| 7. All machinery must be in good working order to uniformly mix and apply hydro-mulch and hydro-seed and the calibration of the equipment must be demonstrated to the Superintendent upon request. | Calibration |
| 304.09 PLANT MATERIALS |  |
| 304.09.01 SEED |  |
| 1. The Contractor must undertake the collection and or purchase of all seed stock for use in direct seeding of the species and quantities listed in Annexure 304B. | Seed List |
| 2. The Contractor must notify the Superintendent 28 days prior to the collection of any seed stock to be supplied by the Principal. | Seed Supplied by Principal |
| 3. Prior to any seed collection the Contractor must ensure that all seed suppliers are holders of appropriate and current seed collection/supply licences. | Seed Collection Licence |
| 4. All seed collected and or supplied by the Contractor must be clean and dry to accepted industry practices for seed processing, and free from mould, pest and disease. | Seed Material |
| 5. Seed must be supplied with a certificate from the Contractor detailing the names of the suppliers, species as nominated in Annexure 304B, date and origin of seed collection and a guarantee that the seed is free of declared noxious plant seed or foreign vegetative parts. | Seed Quality Control |
| 6. Where specified, certified test reports signed by the Contractor must be supplied for each batch of seed detailing the seed purity using accepted industry practices for seed testing. | Seed Purity Testing |
| 7. Where specified, certified test reports signed by the Contractor must be supplied for each batch of seed detailing the seed viability using accepted industry practices for seed testing. | Seed Viability Testing |
| 8. The Contractor must store all seed in secure, dry, well-ventilated storage facilities protected from temperature extremes. The seed material must be stored in vermin proof containers above ground level. Seed must be inspected for pest damage, mould and fungus on a regular basis and action taken to avoid seed deterioration. | Seed Storage |
| 9. Where specified, the seed must be sourced to meet the provenance requirements of the project if nominated in Annexure 304B. Any variation must be confirmed with the Superintendent. | Seed Provenance |
| 304.09.02 PLANTS |  |
| 1. The Contractor must supply plants of the species, size and number as shown in the Drawings or specified in Annexure 304B. The Contractor must order or arrange for the propagation of all plant species and quantities to ensure that the correct numbers of plants will be available by the projected date of planting. | Plant List & Propagation |
| 2. All plants supplied by the Contractor must be obtained from nurseries operating under the Nursery Industry Accreditation Scheme of Australia. | Plant Supply |
| 3. Plant seed must be germinated and cuttings sown in sufficient time to ensure the suitable maturity of the stock for mass planting at the optimum planting time for the Region as nominated in Annexure 304B. All seed used, either in the initial supply or for substituted species, must meet the provenance requirements of the project if nominated in Annexure 304B. Any proposed variation to the nominated plant species must be submitted to the Superintendent for approval. |  |
| 4. Plants must be grown in potting mix meeting the requirements of AS 3743 Potting mixes and supplied in industry-approved containers. Soil in containers at the time of delivery must be free of weeds, insects and disease. |  |
| 5. All plants must have been grown in their final containers for not less than eight weeks, be true to species name, be well-formed and hardened off nursery stock. |  |
| 6. The Superintendent reserves the right to inspect the development of seedlings during the period of propagation. The Superintendent reserves the right to inspect 100% of the total number of seedlings to be used in the Works. The presence of declared weeds in the soil accompanying plants or at the nursery will be a cause for rejection of any or all plants. | Inspection of Nursery |
| 7. All plants must be hardened off by growing in open areas receiving sun for around 75% of the day for at least eight weeks prior to delivery on site and reducing fertiliser at least two weeks prior to delivery on site. | Hardening off |
| 8. The Contractor must ensure all supplied plants are in good condition and: | Plant Condition |
| a) The root system must be fibrous and firmly established but not root bound and with no large roots growing out of the container. |  |
| b) The root mass must retain its shape and hold 90% of the root ball material when removed from the container. |  |
| c) Leaves must be of normal size, colour and texture for the specified species. |  |
| d) The quality of all supplied tree species must conform to the requirements in AS 2303 Tree Stock for Landscape Use. |  |
| 9. The Contractor must obtain written warrants from the nursery suppliers attesting that the plants are true to the specified species, size and free from disease, pests and weeds and forward the warrants to the Superintendent upon request. | Warranty for Plants |
| 10. The Superintendent must be notified of any plant supply delays. No extension of time for Practical Completion will be granted if plant materials are not available due to late ordering. | Delay in Plant Supply |
| 11. No substitutions shall be made without written approval from the Superintendent. Any proposed substitutions shall include details of the species, size, number and be forwarded to the Superintendent for approval. Should the Superintendent consider the substitutions not adequate then the originally specified plants must be grown and planted in the following planting season. | Substitution |
| 12. All individual plant containers and trays of plants must have nametags that are water resistant and tied securely to the plant or inserted into the plant container/trays. Labelled trays must contain only one species of plant. | Plant Labels, |
| 13. Unless otherwise specified in the Drawings, all stakes must be durable, straight, free from knots and twists and pointed at one end, stakes must not be made of metal. Plant ties must be a minimum 25 mm rubber or hessian cloth, rubber ring lock or other approved non-abrasive material. | Stakes and Ties |
| 304.09.03 GRASS |  |
| 1. Grass (turf, stolons or seed) supplied by the Contractor must be of the species, variety and quantities listed in Annexure 304B. | Grass |
| 2. All grass materials must be free from weeds, fungus, insect pest, or other deleterious matter. The Contractor must obtain a written warranty from the grass suppliers attesting that the grass is true to the specified species, size and free from disease, pests and weeds and forward the warrants to the Superintendent upon request. | Warranty for Grass |
| 3. Only grass turf that is older than 10 months must be supplied for use in the Contract. The grass turf must be sourced from a commercial supplier and certified true to the specified variety, the age and quality and date the turf was cut. The turf must be machine cut to a uniform thickness of 16 mm or more excluding the top growth and thatch in segments no less than 1 square metre of surface area. Broken pieces, torn or uneven ends must not be accepted by the Superintendent. | Turf |
| 4. Grass stolons (runners, sprigs or rhizomes) must be derived from shredded turf and must be well-established fibrous length of 50 – 100 mm with healthy leaf material. The Supplier must certify that the grass stolons are true to specified variety and the date on which the cuttings were taken. | Stolons |
| 5. Turf and grass stolons must be kept continuously moist during transport and must be planted within 24 hours of being cut. | Transport |
| 6. Grass seed for use in hydro-mulching or direct seeding must be certified to be not older than 18 months prior to the planting date and delivered on site in a standard sealed container labelled with the name of the supplier, species and variety of seed by weight, percent pure live seed, date of testing, origin of seed. The seed must not be sprouting, mouldy, or show evidence of having been wet or damaged. | Grass Seed |
| 7. Turf, stolons or seed not meeting the specifications and deemed unsuitable by the Superintendent will not be accepted. Rejected materials must be replaced by approved stock at no additional cost to the Principal. | Rejection of Grass |
| 304.10 IRRIGATION MATERIALS |  |
| 1. The Contractor must supply all equipment, materials and accessories required in this Contract to conform to AS/NZS 3500 Part 1.2 and AS 2032 and comply with Local, State and Federal Authorities requirements. | Irrigation Materials |
| CONSTRUCTION |  |
| 304.11 SEQUENCE OF OPERATIONS |  |
| 1. Unless otherwise detailed the sequence of operations must be: | Sequence of Operations |
| a) Weed control. |  |
| b) Clearing and topsoil stripping. |  |
| c) Irrigation and hard landscaping. |  |
| d) Preparation of batters and ground surfaces, including additional weed control. |  |
| e) Seeding, grassing and planting. |  |
| f) Establishment of vegetation. |  |
| Any changes to the sequence of operations must be confirmed with the Superintendent. |  |
| 2. The revegetation and landscaping works must commence as early as practicable after completion of the earthworks, and within the optimum time of year as nominated in Annexure 304B, to minimise soil erosion and ensure the effective revegetation of all disturbed soil areas. The Contractor must be responsible for ensuring adequate additional watering for any grassing operations undertaken outside this period at the Contractor’s expense. | Timing of Works |
| 304.12 WEED CONTROL |  |
| 1. Revegetation and Landscaping operations must be undertaken to meet the requirements for weed control as specified in Specification 204 ENVIRONMENTAL MANAGEMENT and in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION. |  |
| 2. The Contractor must implement an approved weed control program as nominated in Annexure 304B, and as necessary to control all weed species prior to undertaking any other works. |  |
| 3. Any changes to the timing and sequence of weed control operations must be confirmed with the Superintendent. |  |
| 4. Existing plants to be retained and new planting areas must be protected during any herbicide spraying if necessary by fitting guards onto spray units or around existing plants. | Protection of Existing Vegetation |
| 5. The Contractor must exercise absolute care in the application of herbicide to avoid spray drift onto private property or public thoroughfares. | Protection of Other Areas |
| 6. For spot spraying a non-toxic, water-soluble, biodegradable coloured dye must be added to the herbicide spray mix that will be clearly visible for at least 48 hours after the herbicide application. | Dye |
| 7. Treated areas must remain undisturbed for two weeks or as recommended by the herbicide manufacturer. | Disturbance |
| 8. Treated areas must display signs of dying off within 14 days of application as evidence of compliance. If weed mortality rate is less than 100% the Contractor must repeat the application at their own expense until the desired mortality rate is achieved. | Compliance |
| 304.13 CLEARING OF SITE |  |
| 1. Existing vegetation must be removed where nominated in the Drawings. All clearing, stockpiling and treatment of cleared vegetation must be undertaken in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION. | Clearing |
| 304.14 Transplant & Salvage OF EXISTING VEGETATION |  |
| 1. Where nominated in the Drawings or as specified in 301 VEGETATION CLEARING AND DEMOLITION Annexure 301A, the Contractor must undertake the lifting, transport and storage of selected vegetation using accepted industry practices. The replanting of this vegetation must be in accordance with this Specification at the locations as shown in the Drawings or in Annexure 304B. | Transplanting |
| 2. The Contractor must remove tree trunks nominated for salvage as specified in the Drawings or in 301 VEGETATION CLEARING AND DEMOLITION Annexure 301A, and ensure that the tree trunks are not broken by equipment during removal, transport or placement. | Salvage of Tree Trunks |
| 3. Unless specified otherwise in the Drawings or in Annexure 304B, the Contractor must place nominated tree trunks salvaged from clearing operations and retained for use as fauna habitat logs or in the landscaping works parallel to the contours. | Placement of Tree Trunks |
| 304.15 IRRIGATION SYSTEM |  |
| 304.15.01 GENERAL |  |
| 1. The Contractor must install, flush, test and commission an irrigation system as shown in the Drawings and specified in the Contract. |  |
| 2. All water supply connections, bores and related work must be installed in accordance with AS/NZS 3500 Part 1.2. | Connection |
| 3. Prior to commencing any installation works the Contractor must undertake flow and pressure testing to verify the flow rates and pressure. | Flow Rates |
| 4. The Contractor must arrange for any necessary permits as required to install water connections and pay any application fees or charges. |  |
| 5. All piping installation, connections and fittings and the use of primer and solvents for piping connections must be in accordance with the manufacturer’s recommendations and comply with AS 2032 Installation of UPVC pipe systems. | Piping Installation |
| 6. Thrust blocks must be placed at all points of deflection in the mainline and installed in accordance with the manufacturer’s specifications. Piping must be laid in parallel straight lines without excessive bending of pipes and changes in the direction must be with standard fittings. |  |
| 7. Crossings of existing roads, paths or paved areas must be installed by horizontal boring using an approved heavy duty conduit of sufficient diameter to allow easy installation and removal of pipes, wiring and other necessary lines. Conduits must extend at least one metre beyond the toe of any embankments. The ends of conduits must project one metre above the ground surface in preparation for subsequent work. | Crossings |
| 304.15.02 EXCAVATION AND TRENCHING |  |
| 1. Prior to any excavation and trenching the Contractor must certify to the Superintendent that: | HOLD POINT |
| a) All existing services are marked on the ground and the Contractor has liaised with relevant authorities as required to locate services. |  |
| b) The run of pipes, valve locations, sprinkler heads and other components as shown in the Drawings are pegged on the site. |  |
| c) Completed surface levels are in accordance with the Drawings. |  |
| 2. The Contractor must not carry out any excavations within the drip line canopy of all existing trees and care must be taken to avoid any damage to tree roots exposed in trenches. The Contractor must seek the direction of the Superintendent if any tree roots (greater than 50 mm diameter) are in conflict with the installation of the irrigation system. | Damage to Tree Roots |
| 3. The Contractor must excavate by hand within one metre of any existing underground services. | Trenches near Services |
| 4. Under no circumstances will trenching running parallel to a road be allowed closer than one metre from the rear face of the kerb or road shoulder. |  |
| 5. The Contractor must notify and seek approval of the Superintendent of any necessary rock excavation in trenches that cannot be ripped and excavated by standard trench digging equipment. | Difficult Excavation |
| 6. The Contractor must fill any over excavation below the required depth with embankment quality material as detailed in specification 302 EARTHWORKS. | Over Excavations |
| 7. Topsoil from excavation must be stripped and windrowed/ stockpiled separately on site and not mixed with any excavated subsoil material. | Stripping Topsoil |
| 8. Trenches must be excavated to provide a minimum soil cover of 450 mm over all pipe work. Should laterals cross the mainline the trench depth must be such that the lateral has a minimum of 200 mm cover over the mainline and 450 mm cover from the finished surface levels. | Cover |
| 9. The trench bottom must be continuous, firm, smooth and free from rocks, rubble and sharp objects. | Trenching |
| 10. The Contractor must install and connect all fixtures in a neat waterproof manner and in accordance with standards and the manufacturer’s published specifications. Spacing of sprinklers must be as shown in the Drawings unless otherwise approved by the Superintendent. | Installation of Fixtures |
| 11. The Contractor must set the top level of all sprinklers flush with the adjacent finished ground level or as shown in the Drawings. The Contractor must undertake all replacement and connections to existing irrigation system components as shown in the Drawings. |  |
| 304.15.03 FLUSHING AND TESTING |  |
| 1. Prior to backfilling the completed pipe work the Contractor must certify that the entire system is flushed clean and tested in accordance with the Contract. | HOLD POINT |
| 2. Prior to testing of the completed irrigation system | Testing of System |
| a) The Contractor must flush the system. |  |
| b) Each water outlet device must be set/removed to ensure that debris is flushed from the system. |  |
| c) All joints and connections are to remain visible during the flushing and testing. |  |
| d) All sections (high pressure and low pressure) of the irrigation system must be tested to design operating for a minimum period of 30 minutes unless specified otherwise in the Contract. |  |
| e) The operation of each solenoid valve must be tested from the controller. |  |
| 3. Following acceptance, the Contractor must undertake all backfilling, compaction and levelling of trenches. Trenches installed on batters must be compacted sufficiently to ensure no water erosion occurs. | Backfilling and Compaction |
| 4. The Contractor must notify the Superintendent if the soil excavated from the trenches is not suitable as backfill and await approval to continue with the backfilling operation. The unsuitable and surplus excavated soil must be disposed offsite in accordance with Specification 301 VEGETATION CLEARING AND DEMOLITION. | Unsuitable Backfill |
| 5. Backfill material in contact with and immediately adjacent to pipes must be clean sand free from rocks, rubble or sharp objects. | Pipes |
| 6. Only selected fill material in accordance with Specification 302 EARTHWORKS, and approved by the Superintendent must be used as backfill to replace the unsuitable excavated soil. | Replacement Backfill |
| 7. Subsidence of trenches after completion of the works must be rectified at the expense of the Contractor. | Subsidence |
| 304.15.04 TUNING AND COMMISSIONING |  |
| 1. The irrigation system must be tuned and balanced so that each outlet device delivers the designed quantity of water with the controller set at automatic operation, or as specified. | Tuning and Commissioning |
| 2. During the commissioning period the Contractor must be responsible for the repair of all leaks, equipment malfunction, surface erosion or any damage resulting from the operation of the system. |  |
| 3. Any station affected by repairs to the system must be re-flushed out and re-tested after reinstatement. |  |
| 304.16 TRICKLE IRRIGATION |  |
| 1. Where specified in the Drawings, the Contractor must install a temporary trickle irrigation system connected to a water supply outlet. |  |
| 2. Prior to the commencement of the work the Contractor must test and verify the location of the nominated pressure water main and the performance of the water supply. If connected to pressure water mains, the irrigation system must be capable of withstanding pressure surges associated with Water Authority rated services. |  |
| 3. The Contractor must supply all the necessary pipes, fittings, drippers and bubblers capable of suppling water to each plant at the nominal rate specified in the Drawings. If not specified the flow rate will be a nominal rate of 2 litres per hour. |  |
| 4. Unless detailed otherwise in the Drawings, temporary trickle irrigation piping must be laid on the ground surface. |  |
| 304.17 HARD LANDSCAPING |  |
| 1. Unless otherwise specified in the Contract, all hard landscaping elements must be installed as detailed in the Drawings and constructed in accordance with the relevant Main Roads specifications. |  |
| 2. Garden edging for shrub beds, tree wells and lawn areas must be installed as detailed in the Drawings. All garden edging must be set vertical with the top of the edging set flush or just below the adjoining surface or pavement. Curves where shown in the drawings must be smooth and even. Edging must be protected from damage during subsequent works under the Contract. | Garden Edging |
| 304.18 PREPARATION OF BATTERS AND GROUND SURFACES |  |
| 1. All areas nominated for revegetation and or landscaping must be cleared of all surface rubbish and any material that may hinder plant growth before any further surface preparation works are commenced. | Clearing Surface |
| 2. The Contractor must prepare all nominated finished soil surfaces where necessary by ripping, disking, harrowing, tilling, mounding, furrowing, raking, tracking or other means to form a loose and roughened surface in preparation for other revegetation and landscaping works to a depth of 500 mm and at not more than 500 mm spacing or as otherwise specified in the Drawings or Revegetation Plan. | Surface Preparation |
| 3. Surface preparation must be carried out along the contour unless ripping a redundant road/track or detailed otherwise in the Drawings or Revegetation Plan. Ripping along a redundant road/track must be in a manner that prevents channelling of runoff along the road/track. |  |
| 4. Surface preparation must be carried out by hand within 500 mm of paths, kerbs or structures and within the drip line of any retained vegetation. |  |
| 5. Unless specified otherwise in the Drawings or in Annexure 304B all batter surfaces with a slope of 3 Horizontal in 1 Vertical or flatter, including medians or traffic islands nominated for revegetation, and more than one metre from a shoulder or rear face of kerb must be prepared, to a minimum depth of 300 mm to alleviate compaction and prepare a loose surface. Benched and stepped batters must not be ripped prior to topsoil/mulch respread. | Depth of Cultivation on Batters |
| 6. Batter slopes in hard ground must be ripped and reinstated in accordance with this Specification unless the Contractor can demonstrate that the material meets the requirements for the definition for rock in accordance with Specification 302 EARTHWORKS. | Rocky Ground |
| 7. The Contractor must protect all finished and prepared soil surfaces from soil erosion and weed infestation as necessary, in accordance with Specification 204 ENVIRONMENTAL MANAGEMENT until further revegetation and landscaping works as nominated can occur or a Certificate of Practical Completion has been issued. | Temporary Protection Measures |
| 304.19 TOPSOIL RESPREAD |  |
| 1. Approved site suitable topsoil and/or imported topsoil (as specified) must be respread as soon as practical following construction operations with regard for the weed control program as nominated in Annexure 304B. Where suitable spoil has been identified from the works this must be spread first, followed by the topsoil. | Timing |
| 2. Topsoil must be uniformly spread over the nominated finished and prepared ground surfaces to the depth, levels and slope as shown in the Drawings or in accordance with Annexure 304B. | Respreading Topsoil |
| 3. If not specified in the Drawings or Annexure 304B a nominal depth of 75 mm of topsoil but not more than 100 mm must be placed before any planting. | Topsoil Depth |
| 4. The finished surface of the placed topsoil must be free from large stones, lumps and clods. |  |
| 304.20 SOIL IMPROVEMENTS |  |
| 1. Unless detailed otherwise in the Drawings or in Annexure 304B the Contractor must incorporate soil conditioner into the top soil surface layer as necessary to prepare all nominated areas for seeding, planting or grassing, in accordance with Specification 302 EARTHWORKS. | Soil Conditioner |
| 2. The Contractor must incorporate soil additives in the topsoil and or individual planting holes, as specified in the Drawings or in Annexure 304B, in accordance with the manufacturer’s published specifications. | Soil Additives |
| 3. The Contractor must incorporate chipped vegetation mulch as an improvement to sand or other suitable soils, as detailed in the Drawings or in Annexure 304B. Unless specified otherwise, the chipped vegetation mulch must be spread on the soil surface to the nominated depth with suitable equipment. On steep batter slopes the chipped vegetation mulch must be tracked into the soil by a tracked vehicle running perpendicular to the contour. | Improvement of Sandy Soil Surfaces |
| 304.21 WEED CONTROL MATTING |  |
| 1. Weed control matting sheets must be placed and fixed in accordance with the manufacturer’s published specifications. |  |
| 2. Surface obstructions and protuberances must be removed prior to laying out the matting. The matting sheets must be laid loosely to make good contact with the soil surface and not stretched taut over the surface. The matting must be laid to provide a complete cover over the finished surfaces with sufficient overlap along joins to ensure no open spaces between sheets of matting. Matting around individual plants must be cut and placed as detailed in the Drawings. | Laying of matting |
| 3. Unless detailed otherwise in the Drawings, the Contractor must spread a complete cover of suitable mulch over the matting sheets to a nominal depth of 50 mm. | Mulch Cover |
| 304.22 EROSION CONTROL |  |
| 1. Revegetation and Landscaping operations must be undertaken to meet the requirements for erosion and sedimentation control as specified in Specification 204 ENVIRONMENTAL MANAGEMENT. |  |
| 2. The Contractor must implement erosion control measures as detailed in the Drawings or Annexure 304B. | Erosion Control Measures |
| 3. The product must be installed in accordance with the manufacturer’s published instructions for the required site application and a copy must be provided to the Superintendent prior to installation. |  |
| 4. Unless detailed otherwise in the Drawings or Annexure 304B, the Contractor must place the matting within 24 hours of surface preparation. |  |
| 5. If a rainfall event occurs before the matting can be installed and results in soil erosion, the Contractor must replace the eroded material and prepare the soil surface before installing the matting. |  |
| 6. Erosion control matting sheets must be anchored, rolled out down slopes or along open drains, overlapped and fixed in accordance with the manufacturer’s published specifications. | Installation of Erosion Control Matting |
| 7. Disturbance of adjoining soil surfaces must be minimised during installation. |  |
| 8. All surface obstructions and protuberances must be removed prior to laying out the matting. The matting sheets must be laid loosely to make good contact with the soil surface and not stretched taut over the surface. The matting must be laid to provide a complete cover over the finished surfaces with sufficient overlap along joins between sheets of matting. | Laying of Matting |
| 9. Fixing intervals must be sufficient for the steepness and slope to maximise contact between the matting and soil and prevent runoff flows beneath the matting. |  |
| 10. Unless detailed otherwise in the Drawings or Annexure 304B, the Contractor must apply a binding agent and or a complete cover of approved mulch over the matting sheets to a nominal depth of 50 mm. |  |
| 304.23 MULCH RESPREAD |  |
| 1. Unless detailed otherwise in the Drawings or Annexure 304B, the Contractor must spread approved mulch (as specified) as soon as is practical after surface preparation, topsoiling, soil improvements, and the placement of weed control or erosion control matting. | Timing |
| 2. Unless otherwise specified or detailed in the Drawings, mulch must be placed before any planting. |  |
| 3. If a rainfall event occurs before the mulch can be spread, creating soil erosion, the Contractor must replace the eroded material and prepare the soil surface before spreading the mulch. |  |
| 4. If not specified in the Drawings or Annexure 304B a nominal depth of 75 mm of mulch but not more than 100 mm must be placed. | Mulch Depth |
| 5. Mulch must be uniformly spread over the ground surface to an even depth by hand, machine or blower unit and if required the surface raked to present an even surface. | Even Depth of Mulch |
| 6. Unless specified otherwise the Contractor must apply fertiliser over mulch that has not been aged for at least three months, to neutralise any potential soil nitrogen loss. | Fertiliser |
| 7. Unless specified otherwise in the Drawings or if being used as a soil improver, mulch must not be mixed in with the in situ soil or buried in the soil during the spreading operations. | Avoid Mixing Mulch |
| 8. The Contractor must avoid spreading mulch on plants, structures, roadways, and paths, road shoulders and grassed areas and leave the site in a neat, clean condition. Mulch must not be placed closer than 250 mm from the stem of any existing vegetation or new plantings. Existing vegetation or new plants accidentally covered by mulch must be uncovered as soon as possible. | Avoid Over Spreading Mulch |
| 304.24 HYDRO-MULCHING AND HYDRO-SEEDING |  |
| 304.24.01 GENERAL |  |
| 1. The Contractor must carry out hydro-mulching and hydro-seeding operations where nominated in the Drawings using revegetation industry best practice and equipment. |  |
| 2. Hydro-mulching and hydro-seeding mixes and rates must be as specified in Annexure 304B. |  |
| 3. Hydro-mulching and hydro-seeding operations must be carried out as soon as practical following preparation of finished soil surfaces, at the optimal time for the Region as nominated in Annexure 304B to match seasonal rainfall and as soon as the local weather conditions are optimal. | Timing |
| 4. Prior to commencing any operations the Contractor must assess the risk of surface runoff flows causing damage to any areas to be treated and confirm there are no obstruction, obstacle, hazard or factor likely to cause delays or failures of the operations. The Contractor must notify the Superintendent of any necessary works required to minimise the risk of delays or failures of the operations. | Obstruction |
| 5. Not less than 5 working days prior to commencing any hydro-mulching and hydro-seeding operations on site, the Contractor must certify to the Superintendent that: | HOLD POINT |
| a) The nominated areas are correctly defined. |  |
| b) No obstructions, obstacles, hazards or factors likely to cause delays or failures of the operations have been identified. |  |
| c) The soil surfaces are ready for the hydro-mulching and hydro-seeding operations. |  |
| d) The soil moisture content is conducive to seed germination. |  |
| e) Details of the procedures, materials and equipment to be used are documented and have been submitted for approval. |  |
| f) Equipment has been calibrated to mix and discharge a homogeneous mixture at a continuous and uniform rate. |  |
| g) A program for the hydro-mulching and hydro-seeding operations is documented and submitted for approval. |  |
| The Contractor must confirm with the Superintendent any changes to the operations that may be necessary following approval. |  |
| 304.24.02 HYDRO-MULCH |  |
| 1. Unless specified otherwise in Annexure 304B, the hydro-mulch must consist of water, cellulose fibre mulch, binder and dispersing agents. |  |
| 304.24.03 HYDRO-SEED |  |
| 1. Seed species (grass, native plants or other nominated plant species) and other materials as specified must be added to the hydro-mulch slurry at the rates nominated in Annexure 304B or in the Drawings. | Hydro-seeding |
| 2. Seed must be pre-treated as nominated in Annexure 304B. |  |
| 304.24.04 HYDRO-MULCH AND HYDRO-SEED OPERATIONS |  |
| 1. The Contractor must delineate areas on site nominated for hydro-mulch and hydro-seed by the use of stakes or site features or other means, to suit the project site conditions and specified mix requirements, so that the areas are clearly marked prior to the start of operations. | Delineation of Areas |
| 2. The soil surface must be prepared in response to the site soil conditions to provide a suitable soil surface environment for the hydro-mulching and hydro-seeding operations. | Soil Preparation |
| 3. Unless detailed otherwise in Annexure 304B, all materials making up the hydro-mulch and hydro-seed slurry must be mixed on site. The Superintendent may request a review of all proposed ingredients and mixing prior to the start of operations. | Mixing |
| 4. The hydro-mulch and hydro-seed slurry mix must be kept continuously agitated so the ingredients are kept uniformly dispersed throughout the slurry prior to the application. |  |
| 5. The hydro-mulch and hydro-seed slurry mix must be uniformly applied to suit the size and location of the site area, the slope and soil and local weather conditions. | Application |
| 6. The hydro-mulch and hydro-seed slurry mix must be applied in a uniform and continuous motion in overlapping passes to achieve an unbroken surface, with no bare or incomplete areas and to prevent over saturation of the soil surface and minimise soil movement. |  |
| 7. The Contractor must ensure that all reasonable precautions are taken to avoid over spraying onto adjacent vegetation, paths and sealed surfaces. |  |
| 8. Unless otherwise detailed in the Annexure 304B the thickness of the hydro-mulch must be a minimum of 3 mm and no more than 5 mm. | Thickness |
| 9. Areas subject to concentrated surface runoff flows must be treated with thicker applications of hydro-mulch, or higher concentration of binder as specified. |  |
| 10. Hydro-mulch must not be applied in heavy rain or when the wind speed exceeds 25 km per hour except by direct hand held hose application. | Heavy Rain or Wind |
| 11. The Contractor must ensure seeded areas are not disturbed by equipment and vehicles, or by pedestrians and animal traffic during the seeding operations and during the Establishment Period. | Disturbance of Seeded Areas |
| 304.25 DIRECT SEEDING |  |
| 304.25.01 GENERAL |  |
| 1. The Contractor must carry out direct seeding operations where nominated in the Drawings, using horticultural/revegetation industry accepted practice and equipment, to achieve the completion criteria as specified in Annexure 304C. |  |
| 2. Seed mixes and rates to be used in the direct seeding operations must be as specified in the Drawings or Annexure 304B. |  |
| 3. Seeding must be undertaken as soon as practical following construction activities, at the optimal time for the Region as nominated in Annexure 304B and to match seasonal rainfall. | Timing |
| 304.25.02 PREPARATION OF SEED MATERIALS |  |
| 1. Seed must be pre-treated to break seed dormancy mechanisms in preparation for sowing, using generally accepted industry practices or as specified in Annexure 304B. | Seed Pre-treatment |
| 2. Seed, in separate labelled bags for each species, must be delivered for batching into the nominated seed mixes as nominated in Annexure 304B. | Seed Batching |
| 3. The Contractor must give the Superintendent not less than 5 working days notice when and where the batching of seed is to occur. The Superintendent reserves the right to attend this seed batching. |  |
| 4. The prepared seed mixes must be delivered on site, in containers labelled to identify seed mix and weight, ready for use in the direct seeding operations. |  |
| 5. Seed mixes must be blended with a carrier-bulking agent (such as clean washed sand, vermiculite, or similar) in the proportions by volume of bulking agent to seed, to suit the project requirements and allow for the even spreading of seed. | Bulking of Seed Mixes |
| 6. Fertiliser as specified in Annexure 304B must either be mixed with the bulking agent or uniformly applied over the soil surface, as a separate operation, at the time of sowing. | Fertiliser |
| 7. Unless specified otherwise only a granular, low phosphorous, slow release, fertiliser suitable for native plants must be used in the direct seeding operations. |  |
| 304.25.03 SEEDING OPERATIONS |  |
| 1. Prior to commencing any operations the Contractor must assess the presence of weed species, the soil moisture and the risk of surface runoff flows causing damage to any areas to be treated and confirm there are no obstruction, obstacle, hazard or factor likely to cause delays or failures of the operations. The Contractor must notify the Superintendent of any necessary works required to minimise the risk of delays or failures of the operations. | Obstruction |
| 2. Not less than 5 working days prior to commencing any direct seeding operations on site, the Contractor must certify to the Superintendent that: | HOLD POINT |
| a) The nominated areas are correctly defined. |  |
| b) No obstructions, obstacles, hazards or factors likely to cause delays or failures of the operations have been identified. |  |
| c) The soil surfaces are ready for cultivation. |  |
| d) Details of the seed pre-treatment and batching of the seed mixes are documented. |  |
| e) Certificates of seed purity and viability are provided for each batch, if specified. |  |
| f) Details of the procedures, materials and any equipment to be used are documented. |  |
| g) Equipment (if required to be used) has been calibrated to uniformly apply the nominated seed. |  |
| h) A program for the direct seeding operations is documented and submitted for approval. |  |
| The Contractor must confirm with the Superintendent any changes to the operations that may be necessary following approval. |  |
| 3. The Contractor must delineate areas on site nominated for direct seeding by the use of stakes or site features or other means, to suit the project site conditions and specified mix requirements, so that the areas are clearly marked prior to the start of operations. | Delineation of Areas to be Seeded |
| 4. The soil surface must be prepared in response to the site soil conditions to provide a suitable soil surface environment for seed germination and unless specified otherwise, the soil surface must be lightly cultivated immediately prior to seeding to form a loose and roughened surface. | Soil Preparation |
| 5. Seed must be sown uniformly in overlapping passes to allow for complete seed coverage of the prepared surfaces, within the marked areas. | Seeding |
| 6. Unless detailed otherwise in the Annexure 304B, hand broadcasting, farm machinery, calibrated blower or spreader (handheld or mechanical) may be used as necessary to suit the size and location of the area to be seeded, the slope and soil and local weather conditions. |  |
| 7. Seeding must not occur when the wind speed exceeds 25 km per hour, or in heavy rain if a mechanical blower or spreader is used. | Heavy Rain or Wind |
| 8. Unless otherwise detailed in the in the Drawings or Annexure 304B seed on batter surfaces with a slope equal to or steeper than 6 Horizontal in 1 Vertical must be covered by light harrowing, rolling, scarifying, dragging or raking of the seeded area as soon as practical and within 24 hours of seeding. | Covering of Seed |
| 9. Unless detailed otherwise in the Drawings or in Annexure 304B, mulch must not be spread over any areas of direct seeding. | No Mulch Over Seed |
| 10. All machinery must be in good working order to uniformly apply seed and the calibration of the equipment must be demonstrated to the Superintendent upon request. | Calibration |
| 11. The Contractor must ensure that no disturbance of seeded areas, by equipment and vehicles, or by pedestrians and animal traffic occurs during the operations and the Establishment Period. | Disturbance of Seeded Areas |
| 304.26 PLANTING |  |
| 304.26.01 General |  |
| 1. The Contractor must carry out the planting operations as specified, using accepted industry practices and equipment, to achieve the completion criteria as specified in Annexure 304C. | Completion Criteria |
| 2. The Contractor must ensure that all staff engaged in the planting operations are competent, and skilled in the required works. Staff must be supervised during the Works by an experienced supervisor competent and skilled in the required landscape installation and establishment practices. | Supervision of Staff |
| 3. The Contractor must undertake planting where nominated in the Drawings using the species and numbers as nominated in Annexure 304B. | Species and Numbers |
| 4. Prior to purchase the Contractor must supply a list of proposed sources for all the specified plants for the Superintendents approval. | Ordering and Purchase |
| 5. The list of proposed sources must include; the name of supplier, contact details, and conformation from the nursery stating the list of plants to be supplied and the date of supply. |  |
| 6. The purchase of plants must not occur until the Superintendent approves the list of plant supply. | HOLD POINT |
| 7. The Contractor must reinstate at no cost to the Principal any other site works disturbed or damaged during the planting works. | Damage |
| 8. Unless specified otherwise in Annexure 304B, planting operations must be undertaken following construction activities, at the optimum time to match seasonal rainfall in the Region and the effectiveness of the weed control. | Timing |
| 9. The Contractor must obtain approval from the Superintendent in writing prior to commencing any planting works outside this period. |  |
| 10. Prior to commencing any operations the Contractor must assess the presence of weed species, feral animals, the soil moisture and the risk of surface runoff flows causing damage to any areas to be planted and confirm there are no obstruction, obstacle, hazard or factor likely to cause delays or failures of the operations. | Obstruction |
| 11. The Contractor must notify the Superintendent of any necessary works required to minimise the risk of delays or failures of the operations. |  |
| 12. Not less than 5 working days prior to commencing any planting operations on site, the Contractor must certify to the Superintendent that: | HOLD POINT |
| a) The nominated areas for planting are correctly defined. |  |
| b) No obstructions, obstacles, hazards or factors likely to cause delays or failures of the operations have been identified. |  |
| c) The soil surfaces are ready for the planting operations. |  |
| d) Adequate soil moisture content at planting depth is present. |  |
| e) All staff are competent, experienced, and skilled in planting operations. |  |
| f) A program for the planting operations is documented and submitted for approval. |  |
| The Contractor must confirm with the Superintendent any changes to the operations that may be necessary following approval. |  |
| 304.26.02 DELIVERY ON SITE |  |
| 1. Plants must be delivered to the Site and where no onsite storage exists planted immediately and before the end of the same day. | Delivery |
| 2. The Superintendent must be notified at least 24 hours before each scheduled delivery of plants to site, the Superintendent reserves the right to inspect the plant material. |  |
| 3. Plants must not be damaged or allowed to dry out during transport. On arrival at the Site if not left in the transport vehicle/trailer, plants must be placed in a sheltered position and thoroughly watered from a suitable water supply and not allowed to dry out until required for planting. | Transport |
| 4. If an on-site storage area for plants is necessary, the Contractor must provide details (including location, fencing and watering regime) of the proposed storage area in writing to the Superintendent for approval. | Onsite Storage |
| 5. Any on-site nursery for holding plants prior to planting must be a vermin proof compound of sufficient size, with provision for watering of plants and adequately protected from sun, wind, storm, theft and accidental damage by workers etc. |  |
| 6. The Contractor must maintain any plants in an onsite storage area in the condition as supplied by the nursery. |  |
| 7. Transplanted trees and other plant material to be replanted within the Site must receive root pruning and or preparation in accordance with accepted industry transplanting practice to ensure delivery on Site in good condition and ready for placement. | Transplanted Stock |
| 8. The Superintendent reserves the right to inspect and reject any plants not meeting the requirements of this Specification. Root bound containers and plants that do not retain the root mass can be rejected by the Superintendent. Rejected plants must be replaced by approved stock at no additional cost to the Principal. | Rejecting Plants |
| 304.26.03 PREPARATION OF PLANTING AREAS |  |
| 1. The Contractor must ensure the accurate marking out of all planting areas, zones and edges of planting beds prior to beginning any planting operations, in accordance with the Drawings. | Marking out Planting Areas |
| 2. The Contractor must confirm that adequate soil moisture is present at a minimum depth of 100 mm prior to starting any planting operations. | Soil Moisture |
| 3. Planting areas nominated in the Drawings for cultivation must be improved by the application of topsoil, fertiliser, soil additives and/or soil conditioners to the soil surface as specified and thoroughly mixed by rotor tilling the soil to 150 mm minimum depth to achieve a loose and friable condition, suitable for fine grading and planting. | Cultivated Planting Areas/Beds |
| 4. In confined spaces, or close to irrigation fixtures, the cultivation must be by hand. |  |
| 5. Weed control matting and or mulch as specified must be applied over the cultivated surfaces of planting beds. |  |
| 6. Where only individual planting holes are nominated in the Drawings, no cultivation is to occur. | Individual Planting Holes |
| 7. Only the individual planting hole must be excavated and topsoil, soil conditioner, fertiliser and soil additives as specified must be added with the backfill. |  |
| 8. Where specified weed control mats and/or mulch must be installed around each plant. |  |
| 9. Areas nominated for ripline planting must be ripped to a minimum depth of 500 mm and at not more than 500 mm spacing and if specified mounds formed above the riplines at the spacing and layout shown in the Drawings. | Areas for Ripline Planting |
| 10. Unless detailed otherwise in the Drawings the planting mounds must be a minimum 300 mm in height in wet areas and in dry areas 150 mm in height at the spacing and layout shown in the Drawings. | Mounding |
| 304.26.04 SETTING OUT OF PLANTING |  |
| 1. The Contractor must set out individual plants within a planting area in accordance with the spacings, layout and setbacks shown in the Drawings. | Setting Out Planting |
| 2. For plants which have been given location coordinates, setting out will be to a tolerance of + or – 100 mm. |  |
| 3. If not specified otherwise individual plants must typically be setback in accordance with Table 304.01 below. The Contractor must have regard for clear zone distances when planting non-frangible species where no safety barrier is present. | Planting Setbacks |

TABLE 304.01 TYPICAL PLANTING SETBACKS

| Features | Shrubs or Ground Covers | Trees |
| --- | --- | --- |
| Dual use paths. | 2 metres | 3 metres |
| Boundary fence. | 3 metres | 5 metres |
| Painted edge line or kerb. | 5 metres | 10 metres |
| Structures, roadside furniture and light standards. Excludes timber bridges which is a minimum 10 setback for all plantings. | 3 metres | 5 metres |

| 4. If the placement of transplanted materials or advanced plants is not nominated in the Drawings, the Contractor must request the Superintendent for direction on Site prior to setting out and planting. | Advanced Plants |  |
| --- | --- | --- |
| 304.26.05 PLANTING OUT |  |  |
| 1. Prior to any planting into weed control matting, each individual planting hole must be prepared by first slitting open and laying back the matting to allow for each planting hole to be excavated and prepared for planting. | Planting in Weed Control Matting |  |
| 2. Prior to any planting into mulch, each individual planting hole must be prepared by first moving clear sufficient mulch to allow for each planting hole to be excavated and prepared for planting and space for the excavated soil. | Planting in Mulch |  |
| 3. For each planting hole any substandard excavated material or excess soil must be spread evenly around the planting hole, used to create a watering well around the plant or disposed of as specified. | Planting Hole |  |
| 4. If not detailed in the Drawings, the planting hole must be excavated vertically to accommodate the root ball of the plant, such that the top of the plant root ball finishes below the existing ground surface and creates a watering saucer suitable for the size of the plant. |  |  |
| 5. If necessary the base of the hole must be broken up to a minimum depth of 100 mm and the sides of the planting hole loosened. |  |  |
| 6. Individual plants must be removed from containers so as to minimise damage to leaves, stem and root ball. | Handling of Plants |  |
| 7. The root ball of plants must not be left exposed or allowed to dry out and planted without delay. |  |  |
| 8. Plants must not be planted into standing water within an individual plant hole. |  |  |
| 9. Individual plants must be placed in the centre of the planting hole and set plumb. The backfill must be firmed progressively after placing to eliminate air pockets and minimize settlement. |  |  |
| 10. After firming and settlement the top of the root ball must be covered with soil and sit below the finished lowest level of the surrounding watering saucer shaped during planting. |  |  |
| 11 The outside lip of the watering saucer must be approximately three times the diameter of the plant container and capable of holding a sufficient volume of water necessary for any follow-up watering for the plant container size. | Watering Saucer |  |
| 12. When planting on batter slopes a raised horizontal terrace must be formed as a watering saucer, down slope and equal to the diameter of the planting hole. | Sloping Ground |  |
| 13. Frayed or broken roots of bare rooted plants must be cut cleanly before planting. | Bare Roots |  |
| 14. Fertiliser as specified must be applied to each plant in accordance with good horticultural practice. Unless specified otherwise in Annexure 304B only a granular, low phosphorous, slow release fertiliser suitable for native plants must be used for tube stock plantings. | Fertiliser |  |
| 15. Mulch must be respread so that the mulch tapers down to soil level 50 mm from the stem of the plant. | Mulch |  |
| 16. Plant guards must be installed in accordance with the manufacturer’s instructions. | Guards |  |
| 17. Where specified individual plants must be secured by plant ties to stakes complying with this Specification. Once completed any stakes and ties that were holding the plant from the nursery must be removed. | Stakes and Ties |  |
| 18. Where specified, individual weed control mats must be placed around each planting hole in accordance with the manufacturer’s published instructions. | Weed Control Mats |  |
| 19. Unless specified otherwise, plants larger than one litre container size must be watered in immediately after planting sufficient to thoroughly saturate the soil to twice the area of the root ball. | Watering In |  |
| 20. The Contractor must protect all plantings from trespass and traffic until the plants are well established. Protective fencing must be clearly visible to all traffic day and night, and not constitute a safety hazard. | Protection of Plantings |  |
| 304.26.06 TRANSPLANTING INTO PLACE |  |  |
| 1. If not specified in the Drawings, the location of the planting hole for advanced plants must be confirmed with the Superintendent before the excavation. | Planting Hole |  |
| 2. Each planting hole must be excavated to a depth and width sufficient to take the rootball plus 200 mm minimum clearance at the base and sides and to form a watering saucer suitable for the size of the plant. |  |  |
| 3. Where specified, root control barriers must be installed in accordance with the manufacturer’s instructions. | Control Barriers |  |
| 4. Rock and other unsuitable materials must be removed from the planting hole and not used as backfill. | Backfill |  |
| 5. The planting hole must be backfilled in 200 mm lifts with the specified soil mix, fertiliser and any specified soil additives and consolidated progressively by saturating with potable water. |  |  |
| 6. If not specified otherwise, a blended soil mix must be prepared for the plant that conforms to the requirements of AS 4419 for organic sandy loam soils. |  |  |
| 7. Between backfill lifts the plant hole must be flooded with sufficient potable water to consolidate the soil and eliminate air pockets. The watering saucer must be filled and the root ball thoroughly soaked immediately after planting. | Watering |  |
| 8. If not specified otherwise in the Drawings, stakes and/or guys must be installed such that the plant is held firmly with its trunk vertical. Cables in contact with the plant trunk must be covered with rubber hose or similar, to avoid damage to the plant tissue. | Supporting Cables and Stakes |  |
| 9. Tree grates; frames and/or guards must be installed as shown in the drawings. Grates must be placed flush with the pavement and guards plumb. | Tree Grates and Frames |  |
| 304.26.07 PLANTING BOXES AND CONTAINERS |  |  |
| 1. Planter boxes must be cleaned of any builder rubble, cement and or other materials injurious to plant health. The inside surfaces must be sealed as specified and in accordance with the sealant manufacturer’s instructions. | Planter Boxes |  |
| 2. If not specified, a blended soil mix must be prepared for raised planting beds and planter boxes that conform to the requirements of AS 4419 for organic sandy loam soils. The planter box must be backfilled with the specified soil mix, fertiliser and any specified soil additives and consolidated progressively by saturating with potable water. The soil level must be topped up to achieve the nominal finished surface level specified in the Drawings. |  |  |
| 3. Plants must be placed and planted as specified in the Drawings. |  |  |
| 304.27 GRASSING |  |  |
| 304.27.01 General |  |  |
| 1. Grass to be established by turfing or by establishment from rhizomes (runners, stolons or sprigs) or by direct seeding or hydro-seeding must be as specified, using the species, variety and quantity specified in Annexure 304B. | General |  |
| 2. The Contractor must carry out all grassing operations using horticultural best practice and equipment to achieve the completion criteria nominated in Annexure 304C. |  |  |
| 3. Not less than 5 working days prior to commencing any grassing operations on site, the Contractor must certify to the Superintendent that: | HOLD POINT |  |
| a) The nominated areas are correctly defined. |  |  |
| b) No obstructions, obstacles, hazards or factors likely to cause delays or failures of the operations have been identified. |  |  |
| c) The soil surfaces are ready for the grassing operations. |  |  |
| d) Certificates are provided for each batch. |  |  |
| e) Details of the procedures, materials and equipment to be used are documented. |  |  |
| f) A program for the grassing operations is documented and submitted for approval. |  |  |
| The Contractor must confirm with the Superintendent any changes to the operations that may be necessary following approval. |  |  |
| 4. Grass turf and grass runners must be kept moist at all times during transport and site storage and must be laid within 24 hours of being cut. | Delivery on Site |  |
| 5. Grassing must be undertaken as soon as practical following construction activities to match the seasonal rainfall unless nominated otherwise in Annexure 304B. | Timing |  |
| 6. Grassing must only proceed after the completion of all necessary preliminary works including weed control, minor earthworks, surface preparation, topsoiling and soil improvements, and the installation and commission of any specified irrigation systems. |  |  |
| 7. Areas to be grassed must be treated to remove all existing grass and weeds prior to the grassing. | Soil Preparation |  |
| 8. 50 mm of clean topsoil, soil additives and/or conditioners must be applied to the surface and thoroughly mixed by rotor tilling the soil to achieve a loose and friable condition, suitable for fine grading and rolling. |  |  |
| 9. The surface to be grassed must be free from debris and have a grade to allow water to drain with no surface ponding. | Surface Grading |  |
| 10. The finish must be smooth and rolled to obtain an even well consolidated surface with no irregularities, depressions, hollows or abrupt changes in grades or levels. |  |  |
| 11. All grading must be undertaken by hand or machine as appropriate, however only by hand within 500 mm of sprinklers or other fixed irrigation fixtures. |  |  |
| 12. 24 hours before the grassing operation, the area to be grassed must be watered thoroughly to a depth of 100 mm. | Watering |  |
| 304.27.02 GRASSING BY TURF |  |  |
| 1. The areas to be turfed must be prepared and graded to a nominal soil level 50 mm below the adjacent soil levels to ensure the finished turf level is 25 mm below the adjacent surface level. | Soil Preparation |  |
| 2. Before laying the turf, the Contractor must spread fertiliser suitable for turf grass establishment, over the surface and lightly rake the Fertiliser into the surface while maintaining correct levels. |  |  |
| 3. Immediately before laying turf, the soil must be watered to prevent drying out of grass roots. |  |  |
| 4. The turf runs must be placed in straight line with each subsequent row parallel to, and tightly butted against each, staggering the lateral joints. | Spreading and Rolling |  |
| 5. All joints must be tightly butted and the turf sods must not be stretched or overlapped. |  |  |
| 6. Turf edges must finish flush with adjoining surfaces. |  |  |
| 7. After placement the turf must be diagonally rolled and thoroughly watered to a depth of 100 mm within two hours of planting. |  |  |
| 304.27.03 grassing by stolons |  |  |
| 1. The soil surfaces to be grassed by the use of grass stolons, must be prepared and graded to provide a smooth, firm surface true to grade and finished flush with adjoining surfaces. | Soil Preparation |  |
| 2. Before spreading the stolons, the Contractor must spread fertiliser suitable for grass establishment, over the surface and lightly rake the fertiliser into the surface while maintaining correct levels. |  |  |
| 3. Grass must be planted at the rate of 1 square metre of turf shredded and applied as stolons over a maximum area of 10 square metres of soil, unless specified otherwise in the Drawings or Annexure 304B. | Grassing Rate |  |
| 4. The stolons must be spread in two equal directions in transverse directions over the area to be grassed to form an interlocking mat, with the spaces between the stolons not exceeding 300 mm in any direction. | Spreading |  |
| 5. The stolons must then be rotary hoed into the soil to a depth of between 50 mm to 100 mm. Where necessary in confined spaces, the stolons must be spaded in by hand. |  |  |
| 6. After planting, the area must be lightly raked and rolled to produce an even, level surface or plane, free of wheel marks, waves, depressions or other irregularities. | Rolling |  |
| 7. All areas must be thoroughly watered to a depth of 100 mm within two hours of planting. | Watering |  |
| 304.27.04 GRASSING BY SEED |  |  |
| 1. Grassing of areas from seed by hydro-seeding or by dry seeding must be as specified and using horticultural best practice. | Seeding |  |
| 304.27.05 CARE AND ESTABLISHMENT OF GRASSING |  |  |
| 1. The Contractor must protect all newly grassed areas from trespass and traffic until the grass is well established. Protective fencing must be clearly visible to all traffic day and night, and not constitute a safety hazard. | Protection |  |
| 2. All grass areas must be given additional applications of fertiliser in accordance with good horticultural practice during establishment. | Fertilising |  |
| 3. Grassed areas must be watered on a regular basis as required to establish and maintain grass growth in a healthy condition. | Watering |  |
| 4. All grassed areas must be mowed and edged as necessary to maintain a neat appearance in accordance with good horticultural practice during the Vegetation Establishment Period. Grass must be maintained within the nominal height range of 30 mm to 50 mm. | Mowing |  |
| 5. Once established, a top dressing of clean sand or topsoil as specified must be applied to a depth of 10 mm to take up any slight irregularities in the surface. | Top Dressing |  |
| 6. Where grass fails to establish the affected areas must be retreated in accordance with the relevant clauses. |  |  |
| 7. The Contractor must lift all failed turf and relay with new turf. | Replacement |  |
| 304.28 WATERING SYSTEM |  |  |
| 1. The Contractor must provide for a temporary water delivery system by sprinkler, water truck with a spray boom, or other method to distribute a uniform coverage of water to all areas of vegetation as required during the Vegetation Establishment Period. | Temporary Water Delivery System |  |
| 2. The Contractor must supply details of the system and water source prior to use at Practical Completion. | Details of Water Supply |  |
| 3. The watering system must be maintained in good working order to avoid leakage, loss of water and soil erosion. Water trucks must not be driven onto the landscaped areas. |  |  |
| 4. If not specified otherwise all areas of the works must be watered at sufficient frequency and rate to establish and maintain all planting, seeding and grassed areas and achieve the required standard specified for acceptance of the works. The watering rate can include any rainfall events. | Watering Rates and Frequency |  |
| 5. Watering of grass seeded areas must be applied in a fine spray to minimize disturbance or displacement of materials. The force of water (volume and pressure) must not cause displacement of soil. Watering for landscaped areas must not spray onto or flow across or pond on paved areas. |  |  |
| 304.29 REVEGETATION SIGNS |  |  |
| 1. Unless detailed otherwise in the Drawings the Contractor must supply and install a Main Roads Guide Sign, Drawing No. MR-GM-14 (Roadside Revegetation Sign, with the year of the works) in the locations nominated in the Drawings or Annexure 304B and in accordance with Specification 601 SIGNS. | Roadside Revegetation Signs |  |
| Establishment Period |  |  |
| 304.30 COMPLETION OF WORKS |  |  |
| 1. Prior to completion of the works the Contractor must remove all rubbish and surplus materials accumulated during construction and the Site must be left in a neat and tidy condition. | Tidying Up |  |
| 2. Prior to the commencement of the Establishment Period the Contractor must ensure that: | Completion of Works |  |
| a) Any areas of plantings or grassing by turf must have been installed for a minimum of 7 days. |  |  |
| b) Any areas of grassing by stolons must have been installed for a minimum of 14 days. |  |  |
| c) As constructed drawings detailing all seeding, planting and grassing works are signed by a suitably experienced and qualified person, in environmental, botanical, horticultural and/or related fields who is familiar with Main Roads requirements, have been prepared and presented to the Superintendent. |  |  |
| d) The irrigation system has run on a pre-defined automatic program for at least 7 full days prior to Completion of Works. |  |  |
| e) As constructed drawings (3 copies) of the irrigation system, signed by an engineer or suitably qualified person, have been prepared and presented to the Superintendent. |  |  |
| f) A complete operating manual and specifications for the irrigation system, including a parts list of all operating components, description and suppliers, plus an electronic copy, have been presented to the Superintendent. |  |  |
| g) A complete construction and installation warranty against faulty materials and workmanship for a minimum of 12 months from the date of Practical Completion is presented to the Superintendent. |  |  |
| h) A Vegetation Establishment Program for the Works is documented and submitted to the Superintendent for approval. |  |  |
| i) A monitoring program for the Works is documented and submitted to the Superintendent for approval. |  |  |
| 3. The Contractor must give the Superintendent at least 7 days notice that the works are ready to be inspected for completion. | Notice for Inspection |  |
| 4. The Contractor must certify to the Superintendent that all the revegetation and landscaping works have been completed in accordance with the requirements of the Contract and the Vegetation Establishment Program has commenced before seeking approval to commence the Establishment Period. | HOLD POINT |  |
| 304.31 VEGETATION ESTABLISHMENT |  |  |
| 1. The Contractor must establish and monitor the condition and development of the Works during the Establishment Period as nominated in Annexure 304A. | Establishment Period |  |
| 2. Prior to commencing the Establishment Period, the Contractor must provide to the Superintendent for approval, a detailed program of all activities including timing to be undertaken by the Contractor to establish the vegetation in accordance with this Specification. | Vegetation Establishment Program |  |
| 3. The approved Vegetation Establishment Program must include at least one monthly inspection of the Works and the Contractor must notify the Superintendent of any vandalism of the Works, any faults or defects to irrigation, or any other damage within 5 days of detection. |  |  |
| 4. The Contractor must be responsible for the operation, inspection and maintenance of the irrigation system until the end of the Establishment Period for the Works. The Contractor must adjust the height of all sprinkler heads, valve boxes and any other associated plant and equipment as directed by the Superintendent during the irrigation warranty period. | Irrigation System |  |
| 5. The designated activities to establish the works must include but not be limited to: | Designated Establishment Activities |  |
| a) Progressive weed control. |  |  |
| b) Mowing of grassed areas. |  |  |
| c) Inspection and Maintenance of irrigation systems. |  |  |
| d) Repair and replace any erosion rills in soil surfaces. |  |  |
| e) Repairs and replacement of damaged or failed areas of seeding or hydro-mulching or hydro-seeding. |  |  |
| f) Replacement of plants that have failed. |  |  |
| g) Repairs and replacement of damaged or failed areas of grassing. |  |  |
| h) Watering of all grassing and plantings as necessary. |  |  |
| i) Maintenance of tree stakes, tree ties, tree bags (including removal if required) and grates. |  |  |
| 6. Water must be applied to all plants as often and in sufficient amount as conditions may require to keep the plants in a healthy and growing condition until the end of the vegetation Establishment Period. |  |  |
| 7. Failed or damaged plants or plants that do not meet the acceptance criteria must be removed and replaced during the Establishment Period to the original plant specifications. The Superintendent may determine this requires an extension of the vegetation Establishment Period at the Contractor’s expense. | Replacement |  |
| 304.32 MONITORING PROGRAM |  |  |
| 1. The Contractor must undertake monitoring and reporting on the condition and development of the works during the Establishment Period as nominated in Annexure 304A. | Monitoring and Reporting |  |
| 2. Prior to commencing the Establishment Period, the Contractor must provide to the Superintendent, a detailed program of all the monitoring and reporting activities including timing to be undertaken by the Contractor. | Monitoring Program |  |
| 3. Each monitoring report must: | Monitoring Reports |  |
| a) Outline the works undertaken during the reporting period. |  |  |
| b) Compare development of revegetation and landscaping with the relevant outcome-based completion criteria (Annexure 304C). |  |  |
| c) Identify any follow up remedial works to be undertaken. |  |  |
| d) Set out a program for the remedial works. |  |  |
| 4. Electronic copies of each report must be supplied to the Superintendent within 14 days of the end of the reporting period. |  |  |
| 5. The final monitoring report at the end of the Vegetation Establishment Period must be included in the Hand-over report submitted at Final Completion. | Final Monitoring Report |  |
| 304.33–304.80 NOT USED |  |  |
| AS BUILT AND HANDOVER requirements |  |  |
| 304.81 HANDOVER REQUIREMENTS |  |  |
| 1. The Contractor must be responsible for preparing reproducible as constructed drawings of the works in accordance with Main Roads Design and Drawing Presentation standards. | As Constructed Drawings |  |
| 2. As Constructed Drawings must be completed detailing all seeding, planting and grassing works signed by a suitably experienced and qualified person, in environmental, botanical, horticultural and / or related fields who is familiar with Main Roads requirements. |  |  |
| 3. As Constructed Drawings must be completed detailing the irrigation system showing as constructed details, specifications and site measured locations of all main components from a permanent fixed structure. |  |  |
| 4. The Contractor must provide training in the setup and operation (function and programming procedures) of the irrigation system to nominated representatives of the Principal before the end of the Establishment Period. | Training in the Irrigation System |  |
| 5. The hand-over report must include: | Hand-Over Report |  |
| a) The Final monitoring report. |  |  |
| b) Record the location and details of any equipment such as irrigation installed as part of the landscaping and revegetation works. |  |  |
| c) Record any outstanding defects for correction and the proposed timing. |  |  |
| d) Provide a summary of activities undertaken during the Establishment Period and detail the recommended on-going maintenance activities for the Contract area. |  |  |
| 304.82 FINAL COMPLETION |  |  |
| 1. The Contractor must give the Superintendent at least 7 days notice that the works are ready to be inspected at the end of the Establishment Period. |  |  |
| 2. Acceptance of the works by the Superintendent at the end of the nominated Vegetation Establishment Period, shall be subject to | Final Completion |  |
| a) Satisfactory preparation and submission of monitoring reports. |  |  |
| b) Satisfactory preparation and submission of As Constructed Drawings |  |  |
| c) Satisfactory completion of all additional maintenance and remedial works as directed by the Superintendent. |  |  |
| d) The landscaping and revegetation Works meeting the completion criteria as detailed in Annexure 304C for final completion. |  |  |
| 304.83– 304.90 NOT USED |  |  |
| CONTRACT SPECIFIC REQUIREMENTS |  |  |
| 304.91– 304.99 NOT USED |  |  |

ANNEXURE 304A – SPECIFIC REQUIREMENTS

(Complete the blank template schedules to match the specific requirements of the Contract, and delete this note)

304A.1.	LIST OF CONTRACT DRAWINGS

| Drawing Number | Drawing Name |
| --- | --- |

304A.2.	The Establishment Period shall be: ……………...

304A.3.	The Defects Liability Period for the Irrigation System shall be: ….………..

304A.4.	Monitoring must occur during the Establishment Period and after Completion of the Works at:

Monitoring Requirements

304A.5.	The Completion Criteria for this project are nominated in Annexure 304C.

ANNEXURE 304B – MATERIAL REQUIREMENTS

(Complete the blank template schedules or insert drawing numbers to match the specific requirements of the Contract and delete this note)

304B.1.	PLANTING LIST

| SPECIES | SIZE | QUANTITY |
| --- | --- | --- |

304B.2.	SEED

(Insert N/A if no provenance requirements for the project)

| SPECIES | PROVENANCE | QUANTITY |
| --- | --- | --- |

304B.3.	Topsoil Respread REQUIREMENTS

| Type/Topsoil Condition | Location | Depth (mm) |
| --- | --- | --- |

304B.4.	TRANSPLANTING REQUIREMENTS

| Planting Location | Amount | Notes |
| --- | --- | --- |

304B.5.	GRASSING REQUIREMENTS

| Type | Details |
| --- | --- |
| Grass Turf |  |
| Grass Stolons |  |
| Grass Seed |  |

304B.6.	HYDRO-MULCH AND HYDRO-SEED MIX

| Ingredient | Material | Rate per ha |
| --- | --- | --- |
| Cellulose fibre mulch |  |  |
| Tacifier/Binder |  |  |
| Water | Potable |  |
| Fertiliser |  |  |
| Seed |  |  |

304B.7.	MULCH REQUIREMENTS

| Type/Mulch Size | Location | Depth (mm) |
| --- | --- | --- |

304B.8.	SURFACE PREPARATION AND SOIL IMPROVEMENTS

| Location | Details |
| --- | --- |

304B.9.	EROSION CONTROL REQUIREMENTS

| Location | Details |
| --- | --- |

304B.10.	Fauna Habitat Logs

| Placement Location | Amount | Notes |
| --- | --- | --- |

304B.11.	TIMING OF WORKS

| Item | Optimum Time Period | Notes |
| --- | --- | --- |
| Seeding |  |  |
| Planting |  |  |
| Grassing |  |  |
| Transplanting |  |  |
| Hydro-mulching |  |  |

304B.12.	WEED CONTROL REQUIREMENTS

The Contractor must identify all weed species within the Contract area and prepare a Weed Control Program in accordance with 204 ENVIRONMENTAL MANAGEMENT.  Weed species and locations include but are not limited to the listing below.

| Weed species | Timing of control | Control measures |
| --- | --- | --- |

Locations of designated weeds nominated for removal are summarised as:

| Co-ordinates or Chainage |  | Weed species | Treatment details |
| --- | --- | --- | --- |
| North | East |  |  |

304B.13.	REVEGETATION SIGNS

| Item | Number | Notes |
| --- | --- | --- |

ANNEXURE 304C – COMPLETION CRITERIA

(Complete the blank template schedules to match the specific requirements of the Contract and delete this note)

304C.1. ADVANCED PLANTINGS

| Criterion | Twelve weeks after Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Plants surviving (%) |  |  |  |
| Plants meeting acceptance criteria (%) |  |  |  |
| Weed free zone (radius) around base of each plant. |  |  |  |
| Healthy foliage cover of weeds (%) within each nominated planting zone. |  |  |  |

304C.2. PLANTINGS (IRRIGATED)

| Criterion | Twelve weeks after Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Plants surviving (%). |  |  |  |
| Surviving plants meeting acceptance criteria (%) |  |  |  |
| Weed free zone (radius) around base of each plant |  |  |  |
| Healthy foliage cover of weeds (%) within each nominated planting zone. |  |  |  |

304C.3. PLANTINGS (NOT IRRIGATED)

| Criterion | Twelve weeks after Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Plants surviving (%) within each representative plot. |  |  |  |
| Species richness (% of the species planted still present) within each nominated planting zone. |  |  |  |
| Surviving plants meeting acceptance criteria (%) |  |  |  |
| Healthy foliage cover of weeds (%) within each nominated planting zone. |  |  |  |
| Foliage cover (or demonstrated progress towards this level by monitoring reports). |  |  |  |

Two or more randomly selected representative plots (... m x ... m or equal area) per nominated planting zone within the project area.  Nominated planting zones are as shown in the Drawings.

Acceptance criteria for plants shall be:

a) 	Plants are well formed and exhibit signs of healthy growth

b) 	Plants are free of disease symptoms (eg yellowing, wilting, etc)

c) 	Plants are free from signs of insect pests

304C.4. IRRIGATION

Acceptance criteria for irrigation shall be full compliance with the specifications for product and material and construction requirements.

304C.5. HYDRO-MULCHING AND HYDRO-SEEDING

Acceptance criteria shall be full compliance with the specifications for product and material and construction requirements.

304C.6. EROSION CONTROL

| Criterion | Twelve weeks after Practical Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Maximum number of active rills > 150 mm in depth within each nominated zone. |  |  |  |

Acceptance criteria shall be full compliance with the specifications for product and material and construction requirements.

304C.7. WEED CONTROL

| Criterion | Twelve weeks after Practical Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Healthy foliage cover of weeds (%) within each representative plot. |  |  |  |
| Compliance with acceptance criteria (%). |  |  |  |

Two or more randomly selected representative plots (... m x ... m or equal area) per nominated zone within the project area.  Nominated planting/seeding and grassing zones are as shown in the Drawings.

Acceptance criteria for weed control shall be:

a) 	The approved weed control program is implemented as required.

b) 	Treated areas display signs of dying off within 14 days of application.

304C.8. GRASSING (IRRIGATED)

| Criterion | Twelve weeks after Practical Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Grass cover (%) within each representative plot. |  |  |  |
| Compliance with acceptance criteria (%). |  |  |  |

304C.9. GRASSING (NOT IRRIGATED)

| Criterion | Twelve weeks after Practical Completion | After one Autumn | At Final Completion |
| --- | --- | --- | --- |
| Grass cover (%) within each representative plot. |  |  |  |
| Compliance with acceptance criteria (%). |  |  |  |

Two or more randomly selected representative plots (..m x ..m or equal area) per nominated zone within the project area.  Nominated grassing zones are as shown in the drawings.

Acceptance criteria for grass shall be:

a) 	Grass is well formed and exhibits signs of healthy growth

b) 	Grass is free of disease symptoms (e.g. yellowing, wilting, etc.)

c) 	Grass is free from signs of insect pests

304C.10. DIRECT SEEDING OF PLANTS

| Criterion | Twelve weeks after Practical Completion | End of second Spring | At Final Completion |
| --- | --- | --- | --- |
| Mean number of stems (excluding weed species) / m2 within each representative plot. |  |  |  |
| Number of species within each representative plot. |  |  |  |
| Species richness (% of species sown) within each nominated seeding zone. |  |  |  |
| Presence of nominated key species in within each nominated seeding zone. |  |  |  |
| Bare soil areas (excluding weed species) > 1m2 within each representative plot. |  |  |  |
| Foliage cover (or demonstrated progress towards this level by monitoring reports). |  |  |  |

Two or more randomly selected representative plots (..m x ..m or equal area) per nominated seeding zone within the project area.  Nominated seeding zone are as shown in the drawings.

Acceptance criteria for individual seedlings from direct seeding shall be:

a) 	Plants are well formed and exhibits signs of healthy growth

b) 	Plants are free of disease symptoms (e.g. yellowing, wilting, etc.)

c) 	Plants are free from signs of insect pests

304C.11. REGENERATION FROM TOPSOIL

| Criterion | Twelve weeks after Completion | End of second Spring | At Final Completion |
| --- | --- | --- | --- |
| Mean number of stems (excluding weed species) / m2 within each representative plot. |  |  |  |
| Number of species within each representative plot. |  |  |  |
| Bare soil areas (excluding weed species) > 4m2 within each representative plot. |  |  |  |

Two or more randomly selected representative plots (..m x ..m or equal area) per nominated zone within the project area.  Nominated zones are as shown in the drawings.

SPECIFICATION 304 GUIDANCE NOTES

DELETE THESE GUIDANCE NOTES FROM FINAL DOCUMENT AFTER USING FOR REFERENCE

All edits to downloaded TDP documents should be tracked with deletions struck through e.g. example and insertions in italics e.g. example.  If all information relating to a clause is deleted then the clause number should be retained and the words "NOT USED" should be inserted.

The proposed documents with tracked changes is then submitted to the Project Manager for review, prior to printing the final batch of documents.  When this final printing is carried out, the tracked changes option is to be turned off.

The Custodian of this specification is the Manager Environment.

For more guidance on completing this specification and the historical Author’s Notes see “Environmental Procedure Specification 304 Landscaping & Revegetation” D18#843784.

SPECIFICATION AMENDMENT CHECKLIST

Specification Name:	No: 304  Revision No: ______Title:	LANDSCAPING & REVEGETATION

Project Manager:  Name: _____________Signature: ______________Date:________

Checked By:  Name: ________________Signature: ______________Date:________

Contract No: ______Contract Description: __________________________________

| ITEM | DESCRIPTION | SIGN OFF |
| --- | --- | --- |
| Note: All changes/amendments must be shown in Tracked Change mode until approved. |  |  |
| 1. | Project Manager has reviewed Specification and identified Additions and Amendments. |  |
| 2. | CONTRACT SPECIFIC REQUIREMENTS addressed? – Contract specific materials/products/clauses added? (Refer Specification Guidance Notes for guidance). |  |
| 3. | Any unlisted Materials/Products proposed and approved by the Project Manager? – if “Yes” provide details at 15. |  |
| 4. | Standard Clauses amended? – MUST SEEK approval from Manager Contracts |  |
| 5. | Clause deletions shown as ‘NOT USED’. |  |
| 6. | Appropriate INSPECTION & TESTING parameters included in Spec 201 (Test Methods, Minimum Testing Frequencies verified). |  |
| 7. | ANNEXURES completed (Refer Specification Guidance Notes). |  |
| 8. | HANDOVER and AS BUILT requirements addressed. |  |
| 9. | Main Roads QS has approved changes to SMM. |  |
| 10. | Project Manager certifies completed Specification reflects intent of the design. |  |
| 11. | Completed Specification – independent verification arranged by Project Manager |  |
| 12. | Project Manager’s review completed. |  |
| 13. | SPECIFICATION GUIDANCE NOTES deleted. |  |
| 14. | TABLE OF CONTENTS updated. |  |
| 15 | Supporting information prepared and submitted to Project Manager. |  |
| Further action necessary: |  |  |

Signed: 					(Project Manager)	Date: _______________